## Read Me
Website Project Master Task Library — India (small two-person studio)
Version | v1.0 · 28 Sep 2026 · default values, not absolute truths
What this is | A task library covering the full lifecycle from lead to maintenance. Delete rows that do not apply to a project; never delete MUST HAVE rows without a written reason.
Classification tags | [MUST HAVE] needed on every project of this type · [RECOMMENDED] strong best practice · [OPTIONAL] nice to have · [CONDITIONAL] only if the feature/situation exists · [POST-LAUNCH] after go-live / under maintenance
Legal vs practice | A [MUST HAVE] tag means the task is operationally essential, not that a law requires it. Legal requirements are discussed separately in the master document with sources.
Default points | Points ≈ midpoint of typical effort (hours) × complexity factor (Low 1.0, Medium 1.25, High 1.5), rounded; minimum 1. Per-page/per-item tasks show points per unit. 'Varies' effort tasks default to 1 and should be sized at planning.
Customising points | 1) Lock points at kickoff (J-08). 2) Change defaults only in quarterly calibration (BO-02), forward-looking only. 3) Per-project overrides need both partners' approval and a reason. 4) For per-unit tasks multiply by quantity (pages, products, templates).
Billable column | 'No — included' = part of the standard price. 'Yes — separate' = quote as an add-on. 'Conditional' = depends on what the proposal includes.
Owner roles | Sales, PM, Design, Content, FE (frontend), BE (backend), DevOps, QA, Either. In a two-person studio each partner covers several roles; the role says what kind of work it is, which helps calibrate points.
Sheets | Task Library (all 22 fields) · Contribution Library (Part 13 columns) · Category Summary (live formulas)

## Task Library
ID | Category code | Category | Task | Description | Why necessary | When | Prerequisites / dependencies | Typical owner | Deliverable / output | Evidence of completion | Client approval? | Classification | Complexity | Typical effort | Default points | Possible risks | Common mistakes | If skipped | In standard project? | Separate billable item? | Post-launch maintenance?
A-01 | A | Lead Generation | Build prospect list | List local businesses in a target niche/area with no site, an outdated site, or a site that fails mobile/speed checks; record name, contact, source, current URL | A pipeline of qualified leads is the only reliable source of projects | Business-level, ongoing | Ideal client profile agreed | Sales | Prospect sheet rows | CRM/sheet export with dates | No | [RECOMMENDED] | Low | 1–3 h per 20 leads | 2 | Scraping personal data without basis; wasted time on poor-fit niches | Listing everyone instead of a niche; no source tracking | Irregular, referral-only income | No | No — included in base price | No
A-02 | A | Lead Generation | Prospect mini-audit | Quick audit of prospect's site, Google Business Profile, socials: mobile view, speed, HTTPS, broken contact info; 3–5 concrete findings | Gives a specific, credible reason to talk | Pre-sales | A-01 | Sales | 1-page audit or screenshot set | Audit doc/screenshots linked to lead | No | [OPTIONAL] | Low | 0.5–1 h | 1 | Over-investing in leads that never reply | Generic audits; insulting tone | Weak, generic pitch | No | No — included in base price | No
A-03 | A | Lead Generation | Log lead with source and status | Create lead record: business, contact person, phone/email, source, date, next action, status | Lead source data shows which channels pay off; prevents double contact | Pre-sales | None | Either | Lead record | CRM/app entry with timestamp | No | [MUST HAVE] | Low | 5–10 min | 1 | Lost follow-ups | Keeping leads only in personal WhatsApp | Partners contact same lead twice; lost revenue | Yes | No — included in base price | No
A-04 | A | Lead Generation | Referral and partner outreach | Ask past clients, CAs, printers, photographers, marketers for referrals; track referrer | Referrals convert better and cost less | Business-level, ongoing | At least one delivered project | Sales | Referral log | Messages/call notes | No | [RECOMMENDED] | Low | 1–2 h/month | 2 | Promising referral fees without records | No referral tracking | Slower growth | No | No — included in base price | No
B-01 | B | Client Outreach | Write personalised outreach message | Draft first message referencing audit findings and a clear next step (15-min call) | Personalised, specific outreach gets replies; generic spam damages reputation | Pre-sales | A-02, A-03 | Sales | Message draft | Sent message copy/screenshot | No | [RECOMMENDED] | Low | 15–30 min | 1 | Spam complaints; WhatsApp account restriction for bulk messaging | Copy-paste bulk messages; no call to action | Low reply rate | No | No — included in base price | No
B-02 | B | Client Outreach | First contact and log outcome | Call/visit/message; record date, channel, who, outcome, next step | Creates the audit trail for who sourced the client | Pre-sales | B-01 | Sales | Contact log entry | Call log/meeting note | No | [MUST HAVE] | Low | 10–30 min | 1 | Disputes between partners about who brought the client | Not logging verbal conversations | Unclear lead credit; forgotten promises | Yes | No — included in base price | No
B-03 | B | Client Outreach | Follow-up sequence | Up to 2–3 spaced follow-ups with added value (example, audit point); stop after no response | Most deals need follow-up; a cap prevents harassment | Pre-sales | B-02 | Sales | Follow-up entries | Message copies with dates | No | [RECOMMENDED] | Low | 10 min each | 1 | Annoying prospects | Endless follow-ups; no stop rule | Lost warm leads | No | No — included in base price | No
B-04 | B | Client Outreach | Share portfolio and case studies | Send 2–3 relevant samples with outcome, scope and price band | Proof reduces perceived risk | Pre-sales | B-02 | Sales | Portfolio link/PDF | Sent link record | No | [RECOMMENDED] | Low | 15–30 min | 1 | Showing client work without permission | Showing unrelated work; outdated links | Harder to close | No | No — included in base price | No
C-01 | C | Sales | Qualification call | 15–30 min call covering need, decision-maker, budget range, timeline, existing assets | Filters out bad-fit and non-paying clients early | Pre-sales | B-02 | Sales | Qualification notes | Call note in app | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Talking to someone without authority | Skipping budget question; promising features on call | Wasted discovery and proposal time | Yes | No — included in base price | No
C-02 | C | Sales | Go/no-go decision | Decide proceed or decline using checklist: budget fit, timeline realism, legal business, red flags; record reason | Protects capacity and cashflow | Pre-sales | C-01 | Either | Decision record | Decision entry with reason | No | [RECOMMENDED] | Low | 10–20 min | 1 | Taking every project, including toxic ones | No written reason | Scope/payment disputes later | Yes | No — included in base price | No
C-03 | C | Sales | Sales meeting or demo | Present approach, process, timeline, samples; explain payment terms and ownership model upfront | Sets expectations before numbers are discussed | Pre-sales | C-02 | Sales | Meeting notes | Meeting record + attendee list | No | [RECOMMENDED] | Medium | 1–2 h incl. prep | 2 | Over-promising | Not explaining client responsibilities | Mismatched expectations | Yes | No — included in base price | No
C-04 | C | Sales | Pricing negotiation | Negotiate by adjusting scope, not just price; record every concession in writing | Discounts without scope change erode margin | Pre-sales | G-03 | Sales | Negotiation notes, revised proposal | Email/notes, version history | Yes | [RECOMMENDED] | Medium | 0.5–2 h | 2 | Verbal concessions later disputed | Cutting price but keeping scope | Unprofitable project | Cond | No — included in base price | No
C-05 | C | Sales | Client risk check | Check GSTIN (if B2B), business legitimacy, prohibited content/activities, previous vendor disputes | Avoid illegal sites and non-payers | Pre-sales | C-01 | Either | Risk checklist | Checklist entry | No | [RECOMMENDED] | Low | 15–30 min | 1 | Building sites for unlawful businesses | Ignoring red flags due to urgency | Legal exposure, non-payment | Yes | No — included in base price | No
D-01 | D | Discovery | Send discovery questionnaire | Send structured questionnaire (see Part 5) via form/doc with deadline | Collects facts before the call; reduces call time | Discovery | C-02 | PM | Completed questionnaire | Response file/link | No | [MUST HAVE] | Low | 15 min to send | 1 | Client ignores it | Too long; no deadline | Missing requirements discovered mid-build | Yes | No — included in base price | No
D-02 | D | Discovery | Discovery meeting | 60–90 min structured meeting walking through goals, pages, features, content, accounts, timeline, budget | Primary source of requirements | Discovery | D-01 | PM | Raw notes, recording (with consent) | Meeting record, attendees | No | [MUST HAVE] | Medium | 1.5–3 h incl. prep | 3 | Recording without consent; missing decision-maker | Letting client design the solution on the call | Wrong scope and estimate | Yes | No — included in base price | No
D-03 | D | Discovery | Discovery summary to client | Send written summary of what was understood, open questions, and next steps within 24–48 h | Creates written record client can correct | Discovery | D-02 | PM | Summary email/doc | Sent email | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Misunderstandings persisting | Not asking client to confirm | Disputes over what was said | Yes | No — included in base price | No
D-04 | D | Discovery | Identify decision-maker and single point of contact | Record who approves design, content, payments; one SPOC for feedback | Prevents conflicting feedback from multiple people | Discovery | D-02 | PM | Stakeholder list | Entry in project record | Yes | [MUST HAVE] | Low | 10–15 min | 1 | Late veto by an unseen owner | Accepting feedback from anyone | Endless revision loops | Yes | No — included in base price | No
D-05 | D | Discovery | Existing assets and accounts audit | Identify current domain registrar and registrant, hosting, email provider, DNS host, analytics, GBP, socials, and who holds logins | Ownership problems block launch; must be found early | Discovery | D-02 | PM | Asset & account register (draft) | Register doc | No | [MUST HAVE] | Medium | 1–2 h | 2 | Domain registered in a former vendor's name | Assuming client controls their domain | Launch blocked, emergency transfers | Yes | No — included in base price | No
E-01 | E | Requirements Gathering | Define goals and success metrics | Agree 2–4 measurable goals (e.g., enquiries/month, calls, bookings) and how they will be measured | Guides design priorities and later proves value | Requirements | D-03 | PM | Goals section in brief | Approved brief | Yes | [RECOMMENDED] | Low | 0.5–1 h | 1 | Vague goals lead to subjective acceptance | Promising outcomes (rankings, sales) | No objective measure of success | Yes | No — included in base price | No
E-02 | E | Requirements Gathering | Draft sitemap and page list | List every page with purpose and priority; mark template vs unique pages | Page count drives price and timeline | Requirements | D-03 | PM | Sitemap | Sitemap file/diagram | Yes | [MUST HAVE] | Low | 1–2 h | 2 | Page creep | Not distinguishing templated vs unique pages | Unbounded scope | Yes | No — included in base price | No
E-03 | E | Requirements Gathering | Feature list with priorities | List features (forms, booking, blog, gallery, payments, languages) marked Must/Should/Could/Won't | Separates core scope from optional add-ons | Requirements | D-03 | PM | Feature list | Requirements doc | Yes | [MUST HAVE] | Medium | 1–2 h | 2 | Hidden complex features | Writing features without acceptance criteria | Estimation errors | Yes | No — included in base price | No
E-04 | E | Requirements Gathering | Content responsibility matrix | For every page/section: who writes text, supplies images, approves, and by when | Content delays are the most common cause of late projects | Requirements | E-02 | PM | Content matrix | Matrix doc | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Developer silently becomes copywriter | Assuming client will write | Project stalls waiting for content | Yes | No — included in base price | No
E-05 | E | Requirements Gathering | Integration and third-party inventory | List every external service (maps, payments, booking, CRM, email), who creates the account, costs, and API limits | Third-party accounts must be in client's name and ready before build | Requirements | E-03 | PM | Integration register | Register doc | Yes | [MUST HAVE] | Medium | 1–2 h | 2 | Paid services on developer card | Creating accounts in developer's name | Ownership disputes, surprise costs | Yes | No — included in base price | No
E-06 | E | Requirements Gathering | Non-functional requirements | Agree supported browsers/devices, accessibility target, performance targets, languages, hosting region, uptime expectations | These drive testing effort and cost | Requirements | E-03 | PM | NFR section | Requirements doc | Yes | [MUST HAVE] | Medium | 0.5–1 h | 1 | Client assumes IE-era or all devices | Leaving targets unstated | Endless 'it looks wrong on my phone' disputes | Yes | No — included in base price | No
E-07 | E | Requirements Gathering | Requirements sign-off | Client confirms requirements document in writing (e-sign or email 'approved') | Baseline for all later change requests | Requirements | E-01..E-06 | PM | Signed requirements | Signed doc/email | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Client later claims features were 'obvious' | Oral approval only | No baseline for scope control | Yes | No — included in base price | No
F-01 | F | Scope Definition | Write inclusions list | Enumerate exactly what is delivered: pages, templates, features, integrations, content work, rounds, training, warranty days | Clear inclusions prevent 'I thought that was included' | Scope | E-07 | PM | Scope inclusions | Scope doc | Yes | [MUST HAVE] | Medium | 1–2 h | 2 | Ambiguous words like 'basic SEO' | Using vague nouns | Scope creep | Yes | No — included in base price | No
F-02 | F | Scope Definition | Write exclusions and assumptions | List what is NOT included (copywriting, logo, photos, paid ads, content entry beyond X pages, third-party fees) and assumptions (content supplied by date, one SPOC) | Exclusions carry as much weight as inclusions | Scope | F-01 | PM | Exclusions/assumptions list | Scope doc | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Unpriced work demanded later | Forgetting third-party fees and renewals | Unpaid extra work | Yes | No — included in base price | No
F-03 | F | Scope Definition | Define revision rounds | Specify number of rounds per stage, what a round is (one consolidated list), and what counts as a change request | Unlimited revisions are the top profit killer | Scope | F-01 | PM | Revision policy | Scope doc | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Piecemeal feedback treated as one round | Saying 'unlimited revisions' | Endless loops | Yes | No — included in base price | No
F-04 | F | Scope Definition | Define client responsibilities and feedback SLAs | Client duties: content, approvals within N working days, account creation, payments; effect of delay on timeline | Client delays must shift deadlines, not your margins | Scope | F-01 | PM | Responsibilities section | Scope doc | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Blame for client-caused delay | No consequence stated for delay | Timeline disputes | Yes | No — included in base price | No
F-05 | F | Scope Definition | Define milestones and acceptance criteria | Milestones (design, build, UAT, launch) with measurable acceptance tests and deemed-acceptance rule | Links payments to objective checkpoints | Scope | F-01 | PM | Milestone table | Scope doc | Yes | [MUST HAVE] | Medium | 0.5–1 h | 1 | Subjective 'not happy' rejections | Acceptance with no time limit | Payments stuck indefinitely | Yes | No — included in base price | No
G-01 | G | Proposal/Quotation | Bottom-up effort estimate | Estimate each task from the task library with low/high range, add risk buffer (10–25%) | Pricing from effort beats guessing | Proposal | F-01..F-05 | PM | Estimate sheet | Sheet with version | No | [MUST HAVE] | Medium | 1–3 h | 3 | Under-pricing | Forgetting QA, PM, communication time | Loss-making project | Yes | No — included in base price | No
G-02 | G | Proposal/Quotation | Price calculation | Convert effort to price; add third-party costs (pass-through or client-paid), GST if registered, contingency; set payment split | Makes margin and taxes explicit | Proposal | G-01 | PM | Pricing sheet | Sheet | No | [MUST HAVE] | Medium | 0.5–1 h | 1 | GST omitted from quoted price | Quoting inclusive/exclusive of GST ambiguously | Margin loss or tax dispute | Yes | No — included in base price | No
G-03 | G | Proposal/Quotation | Prepare proposal | Proposal with problem, solution, scope summary, timeline, price, payment schedule, ownership model, validity date | Sells and sets expectations | Proposal | G-02 | PM | Proposal PDF/doc | Versioned file | Yes | [MUST HAVE] | Medium | 2–4 h | 4 | Proposal contradicts scope doc | No validity date; no exclusions | Disputes, stale prices | Yes | No — included in base price | No
G-04 | G | Proposal/Quotation | Formal quotation | Itemised quotation with GSTIN/SAC and tax lines if registered, validity, terms reference | Some clients need a formal quote for internal approval/accounting | Proposal | G-02 | PM | Quotation | Quote number and file | Yes | [RECOMMENDED] | Low | 0.5 h | 1 | Tax details wrong | Mixing quote and invoice | Client accounting rejects it | Yes | No — included in base price | No
G-05 | G | Proposal/Quotation | Proposal walkthrough | Walk client through proposal; answer questions; log objections | Increases close rate, surfaces misunderstandings | Proposal | G-03 | Sales | Call notes | Meeting record | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Unrecorded promises | Adding scope verbally | Disputes | Yes | No — included in base price | No
G-06 | G | Proposal/Quotation | Revise proposal | Update scope/price after negotiation; increment version; mark superseded | Only one current version should exist | Proposal | C-04 | PM | Proposal v2+ | Version history | Yes | [CONDITIONAL] | Low | 0.5–2 h | 1 | Client signs outdated version | Editing without version numbers | Contract mismatch | Cond | No — included in base price | No
H-01 | H | Contract/Agreement | Adapt contract template | Start from lawyer-reviewed master services agreement; select project schedule; do not edit core clauses ad hoc | Consistent, reviewed terms reduce legal risk | Contract | G-03 accepted | PM | Draft contract | Draft file | No | [MUST HAVE] | Medium | 1–2 h | 2 | Using internet templates with foreign law | Changing clauses per client without review | Unenforceable or conflicting terms | Yes | No — included in base price | No
H-02 | H | Contract/Agreement | Fill statement of work schedule | Attach scope, milestones, payment schedule, revision policy, timeline, client duties as a schedule to the contract | Keeps legal terms stable and project details specific | Contract | H-01, F-01..F-05 | PM | SOW schedule | Contract annex | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Scope doc and contract disagree | Referring to 'as discussed' | Ambiguous obligations | Yes | No — included in base price | No
H-03 | H | Contract/Agreement | IP, ownership and licence check | Confirm clause: what is assigned (in writing, with duration/territory), what is licensed (pre-existing code, libraries, templates), third-party licences, portfolio rights | Indian copyright assignment has statutory formalities; silence creates default rules | Contract | H-01 | PM | IP clause checklist | Checklist entry | Yes | [MUST HAVE] | Medium | 0.5–1 h | 1 | Client assumes payment = ownership of everything incl. your reusable code | Assigning your reusable framework | Ownership dispute | Yes | No — included in base price | No
H-04 | H | Contract/Agreement | Confidentiality and data-processing terms | Add confidentiality; if you will access/process personal data (form leads, customers), add processor-style terms: purpose, security, deletion, breach notice | DPDP Act expects fiduciaries to use processors under a valid contract | Contract | H-01 | PM | Data terms | Contract clause | Yes | [CONDITIONAL] | Medium | 0.5–1 h | 1 | Handling client customer data without terms | Copy-pasting GDPR clauses | Liability exposure | Cond | No — included in base price | No
H-05 | H | Contract/Agreement | Execute contract | Both parties sign (e-sign/wet); store final PDF; record date, version, signatories and authority | A signed contract is the core evidence in any dispute | Contract | H-02..H-04 | PM | Signed contract | Signed PDF + audit trail | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Unsigned or wrong version | Starting work before signature | Weak enforceability | Yes | No — included in base price | No
H-06 | H | Contract/Agreement | Stamp duty check | Check applicable state stamp duty for the agreement type/value; pay via e-stamp if required | Unstamped instruments can be inadmissible in evidence until duty and penalty are paid | Contract | H-05 | PM | E-stamp certificate (if applicable) | Certificate file | No | [CONDITIONAL] | Low | 15–60 min | 1 | Evidence problems in court/arbitration | Assuming email contracts never need stamping | Delay and penalty when enforcing | Cond | No — included in base price | No
I-01 | I | Payment/Invoice | Raise advance invoice | Issue invoice for advance (e.g., 30–50%) with correct GST details if registered | Advance funds work and filters non-serious clients | Payment | H-05 | PM | Advance invoice | Invoice number/file | No | [MUST HAVE] | Low | 15–30 min | 1 | Starting without advance | Invoice without GSTIN/SAC when registered | Cash risk, tax non-compliance | Yes | No — included in base price | No
I-02 | I | Payment/Invoice | Confirm advance receipt | Match bank credit to invoice; issue receipt/acknowledgement; record TDS if deducted | Work starts only on confirmed funds | Payment | I-01 | PM | Receipt | Bank reference, receipt file | No | [MUST HAVE] | Low | 10–15 min | 1 | Fake payment screenshots | Trusting screenshots instead of bank credit | Unpaid work | Yes | No — included in base price | No
I-03 | I | Payment/Invoice | Milestone invoices | Invoice each milestone on acceptance or deemed acceptance | Keeps cashflow aligned with delivery | Payment | F-05 | PM | Milestone invoices | Invoice files | No | [MUST HAVE] | Low | 15 min each | 1 | Invoicing late | Waiting for 'final' before any invoice | Cashflow gaps | Yes | No — included in base price | No
I-04 | I | Payment/Invoice | TDS tracking and reconciliation | Record TDS deducted by client, check it appears in Form 26AS/AIS, request TDS certificate | You can only claim credit for TDS that is deposited and reported | Payment | I-02 | PM | TDS register | Register + certificates | No | [CONDITIONAL] | Low | 15 min/invoice | 1 | TDS deducted but not deposited | Not reconciling quarterly | Lost tax credit | Cond | No — included in base price | No
I-05 | I | Payment/Invoice | Payment follow-up | Polite reminders at due date, +7, +14 days; escalate per contract; log each | Late payment is common; a process removes awkwardness | Payment | I-03 | PM | Follow-up log | Messages/emails | No | [MUST HAVE] | Low | 10–20 min each | 1 | Relationship damage | Continuing work while overdue | Growing unpaid balance | Yes | No — included in base price | No
I-06 | I | Payment/Invoice | Record project expenses | Record every third-party purchase (theme, plugin, stock image, domain) with bill, payer, reimbursable flag | Expenses affect profit split and client billing | Payment | None | Either | Expense entries | Bills/receipts | No | [MUST HAVE] | Low | 5 min each | 1 | Partner paid personally without record | Losing bills | Unfair split; tax deduction loss | Yes | Conditional — depends on scope | No
J-01 | J | Project Setup | Create project record and folder structure | Create project in tracking app and shared drive with standard folders (01-Contract, 02-Brief, 03-Content, 04-Design, 05-Dev, 06-QA, 07-Launch, 08-Handover, 09-Finance) | Standard structure makes evidence findable and handover easy | Kickoff | H-05, I-02 | PM | Project record, folders | Folder link, app record | No | [MUST HAVE] | Low | 15–30 min | 1 | Files scattered across chats | Personal drives for client files | Lost evidence, messy handover | Yes | No — included in base price | No
J-02 | J | Project Setup | Create task board and milestones | Import default tasks from library, delete irrelevant ones, set owners, due dates, milestones | Visible plan avoids forgotten work and supports contribution tracking | Kickoff | J-01 | PM | Task board | Board snapshot | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Plan drifts from contract | Not removing irrelevant tasks | Missed deliverables | Yes | No — included in base price | No
J-03 | J | Project Setup | Set up client communication channel and rules | Choose official channels (email for decisions, WhatsApp group for quick coordination), response times, working hours, SPOC | Decisions buried in chats cause disputes | Kickoff | J-01 | PM | Communication plan | Kickoff note | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Late-night demands | Taking approvals over voice calls only | Lost decisions | Yes | No — included in base price | No
J-04 | J | Project Setup | Create repository | Create repo (ideally in a business-owned organization or client-owned org), branch protection, README stub, .gitignore excluding secrets | Version control is evidence and safety net | Kickoff | J-01 | FE/BE | Repository | Repo URL, first commit | No | [MUST HAVE] | Low | 15–30 min | 1 | Repo in personal account hard to transfer | Committing .env files | Leaked secrets; messy transfer | Yes | No — included in base price | No
J-05 | J | Project Setup | Set up dev and staging environments | Local dev setup, password-protected or noindex staging URL for client review | Client reviews must not be indexed or public | Kickoff | J-04 | DevOps | Staging URL | URL + access note | No | [MUST HAVE] | Medium | 1–3 h | 3 | Staging indexed by Google; client data on public staging | No auth on staging | Duplicate content, leaked unfinished site | Yes | No — included in base price | No
J-06 | J | Project Setup | Project credential vault | Create shared vault (password manager) for project credentials with item naming convention | Credentials must never live in chats or docs | Kickoff | J-01 | PM | Vault folder | Vault entry list (names only) | No | [MUST HAVE] | Low | 15–30 min | 1 | Credentials in WhatsApp | Sharing master passwords | Account compromise | Yes | No — included in base price | No
J-07 | J | Project Setup | Kickoff meeting | Walk through plan, timeline, responsibilities, content deadlines, communication rules, next steps; send notes | Aligns everyone at the start | Kickoff | J-02, J-03 | PM | Kickoff notes | Meeting record + sent notes | No | [MUST HAVE] | Low | 1–1.5 h incl. notes | 2 | Unclear first steps | No written follow-up | Misaligned expectations | Yes | No — included in base price | No
J-08 | J | Project Setup | Internal task assignment and point pre-estimate | Partners agree owners and default points for each task before work starts; lock the plan | Pre-agreement is the strongest defence against later point disputes | Kickoff | J-02 | Either (both confirm) | Locked task plan | App lock record with both confirmations | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Points assigned after the fact | One partner assigning all points | Split disputes | Yes | No — included in base price | No
K-01 | K | Client Communication | Weekly progress update | Short written update: done, next, blockers, decisions needed, client actions pending | Keeps client informed and documents delays | Throughout | J-07 | PM | Update message | Sent email/message | No | [RECOMMENDED] | Low | 15–30 min/week | 1 | Silence breeds anxiety | Only updating when asked | Trust erosion; delay disputes | Yes | No — included in base price | No
K-02 | K | Client Communication | Meeting scheduling and agenda | Send invite with agenda, goal, attendees, materials | Focused meetings are shorter | Throughout | None | PM | Invite + agenda | Calendar invite | No | [RECOMMENDED] | Low | 10 min | 1 | Unprepared meetings | No agenda | Wasted time | Yes | No — included in base price | No
K-03 | K | Client Communication | Meeting notes and action items | Notes within 24 h: decisions, actions with owner and due date, open questions; client asked to correct | Written record of what was decided | Throughout | Any meeting | PM | Notes | Sent notes | No | [MUST HAVE] | Low | 15–30 min | 1 | Disputed recollection | Notes not shared with client | 'We never agreed to that' | Yes | No — included in base price | No
K-04 | K | Client Communication | Decision log | Maintain log of decisions: date, decision, who approved, source link | Single source of truth for scope decisions | Throughout | J-01 | PM | Decision log | Log entries | No | [RECOMMENDED] | Low | 5 min/entry | 1 | Contradictory decisions | Decisions only in chat | Rework | Yes | No — included in base price | No
K-05 | K | Client Communication | Escalation handling | Handle serious issues (delays, payment, conflict) by call plus written summary with options | Structured escalation prevents disputes growing | As needed | None | PM | Escalation note | Note + client response | Optional | [CONDITIONAL] | Medium | 1–3 h | 2 | Emotional reactions | Arguing on WhatsApp | Relationship breakdown | Cond | No — included in base price | No
L-01 | L | Research | Industry and business research | Understand client's services, customer questions, regulatory/professional display norms to confirm with client | Informs structure and copy | Research | D-03 | Content/PM | Research notes | Notes doc with URLs | No | [RECOMMENDED] | Low | 1–3 h | 2 | Wrong assumptions | Skipping for 'simple' sites | Generic site | Yes | No — included in base price | No
L-02 | L | Research | Audience and user needs | Define 2–3 audience types, their key questions, devices, languages | Drives content hierarchy and CTAs | Research | D-03 | Design/Content | Audience notes | Doc | No | [RECOMMENDED] | Low | 1–2 h | 2 | Designing for the client's taste only | Skipping mobile-first reality | Poor conversion | Yes | No — included in base price | No
L-03 | L | Research | Keyword and local search research | Find search terms (service + locality), questions, and competitor terms; map to pages | Basis for on-page SEO | Research | E-02 | Content | Keyword map | Sheet | No | [RECOMMENDED] | Medium | 2–4 h | 4 | Promising rankings | Targeting impossible terms | Weak organic visibility | Cond | Conditional — depends on scope | No
L-04 | L | Research | Technical approach decision record | Decide stack (static, CMS, framework, hosting) with reasons: client skills, budget, maintenance, hosting costs | Wrong stack creates maintenance burden | Research | E-03, E-06 | FE/BE | Decision record | ADR doc | No | [MUST HAVE] | Medium | 1–2 h | 2 | Choosing trendy tools client can't maintain | Deciding by habit | High long-term cost | Yes | No — included in base price | No
L-05 | L | Research | Legal content needs check | List legal pages/disclosures the client must provide (privacy notice, terms, refund policy for e-commerce, grievance contact) and flag for client's lawyer | Legal text is the client's responsibility but must be planned | Research | E-03 | PM | Legal content list | Doc | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Developer drafting legal text as advice | Copying another site's privacy policy | Non-compliant site | Yes | No — included in base price | No
M-01 | M | Competitor Research | Identify competitors | Choose 3–5 direct/local competitors and 1–2 aspirational ones with client | Benchmarks expectations | Research | D-02 | Content/Design | Competitor list | Doc | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Copying competitors | Only picking big brands | Weak positioning | Yes | No — included in base price | No
M-02 | M | Competitor Research | Competitor site analysis | Review structure, messaging, CTAs, trust signals, pricing display, mobile experience; screenshots | Finds gaps and opportunities | Research | M-01 | Design/Content | Analysis doc | Doc + screenshots | No | [RECOMMENDED] | Medium | 2–3 h | 3 | Copyright issues if copying copy/assets | Copying rather than learning | Me-too website | Yes | No — included in base price | No
M-03 | M | Competitor Research | Competitor SEO snapshot | Note titles, key pages, GBP presence, reviews volume | Sets realistic SEO goals | Research | M-01 | Content | Snapshot | Sheet | No | [OPTIONAL] | Low | 1–2 h | 2 | Tool costs | Over-analysis | Unrealistic SEO promises | No | Conditional — depends on scope | No
N-01 | N | Brand Assets | Collect brand assets | Obtain logo (vector SVG/AI/PDF), colours, fonts, brand guide, photo library | Needed before design | Content | J-07 | Design | Asset folder | Folder listing | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Low-res logos | Working from screenshots of logo | Blurry, off-brand site | Yes | No — included in base price | No
N-02 | N | Brand Assets | Verify brand asset rights | Confirm client owns logo, has licences for fonts/photos they supply; record licence files | You may be publishing infringing material | Content | N-01 | PM | Rights checklist | Licence files | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Font licences not covering web use | Assuming Google-found images are free | Infringement claims | Yes | No — included in base price | No
N-03 | N | Brand Assets | Basic brand guide creation | Define palette, type pairing, logo usage if client has none | Consistency across site | Design | N-01 | Design | Mini brand guide | File | Yes | [CONDITIONAL] | Medium | 3–8 h | 7 | Scope creep into branding | Doing it free | Unpaid work | Cond | Yes — separate line item | No
N-04 | N | Brand Assets | Logo design | Logo concepts, refinement, final files and copyright assignment | Logo is a separate creative deliverable | Design | N-01 | Design | Logo files | Files + approval | Yes | [CONDITIONAL] | High | 8–20 h | 20 | Trademark conflicts | Bundling free logos | Unpaid work; TM disputes | Cond | Yes — separate line item | No
O-01 | O | Content Collection | Send content checklist with deadlines | Per page list of required text, images, videos, documents with due dates and format specs | Makes client obligations concrete | Content | E-04 | PM | Content checklist | Sent checklist | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Deadline slippage | No format/size guidance | Content delays | Yes | No — included in base price | No
O-02 | O | Content Collection | Collect content in shared folder | Receive files in organised folder; reject WhatsApp-compressed images where quality matters | Central source for build | Content | O-01 | PM | Content folder | Folder listing | No | [MUST HAVE] | Low | 1–2 h over project | 2 | Wrong/old versions used | Collecting via chat | Rework | Yes | No — included in base price | No
O-03 | O | Content Collection | Track content status | Mark each page item: pending/received/edited/approved | Visibility of blockers | Content | O-02 | PM | Content tracker | Tracker | No | [RECOMMENDED] | Low | 10 min/week | 1 | Invisible blockers | No tracker | Last-minute scramble | Yes | No — included in base price | No
O-04 | O | Content Collection | Image rights and consent check | Confirm source/licence for each image; photos of identifiable people/customers have consent; stock licence saved | Publishing unlicensed or non-consented images creates liability | Content | O-02 | Content | Media rights register | Register + licence files | Yes | [MUST HAVE] | Low | 0.5–2 h | 1 | Copyright notices from stock agencies | Using search-engine images | Takedowns, claims | Yes | No — included in base price | No
O-05 | O | Content Collection | Process and optimise media | Crop, resize, compress, convert (WebP/AVIF), rename descriptively, write alt text drafts | Performance and accessibility | Content | O-04 | FE/Content | Optimised media set | Folder + size report | No | [MUST HAVE] | Low | 1–4 h | 3 | Quality loss | Uploading 5 MB photos | Slow site | Yes | No — included in base price | Yes
O-06 | O | Content Collection | Chase missing content and record delays | Remind client per plan; log delay days; notify timeline impact in writing | Documents client-caused delays | Content | O-03 | PM | Delay log | Messages + log | No | [MUST HAVE] | Low | 10–20 min each | 1 | Blame for late launch | Silently waiting | Disputes over deadlines | Yes | No — included in base price | No
P-01 | P | Copywriting | Homepage copywriting | Write headline, value proposition, sections, CTAs based on research | Homepage drives first impression and conversion | Content | L-01, L-02 | Content | Homepage copy | Doc with version | Yes | [CONDITIONAL] | Medium | 3–6 h | 6 | Client rewrites everything | Writing before strategy | Weak messaging | Cond | Yes — separate line item | No
P-02 | P | Copywriting | Inner page copywriting | Write service/about/contact/FAQ copy | Complete content | Content | P-01 | Content | Page copy | Doc | Yes | [CONDITIONAL] | Medium | 1–3 h/page | 3 | Unbounded page count | Pricing per project not per page | Unpaid copy work | Cond | Yes — separate line item | No
P-03 | P | Copywriting | SEO copy optimisation | Integrate target keywords naturally in headings, intro, titles; avoid stuffing | Improves relevance | Content | L-03, P-01 | Content | Optimised copy | Doc diff | No | [RECOMMENDED] | Low | 0.5–1 h/page | 1 | Keyword stuffing | Ignoring readability | Lower rankings | Cond | Conditional — depends on scope | No
P-04 | P | Copywriting | UI microcopy | Button labels, form hints, error messages, success messages, empty states | Clarity and accessibility | Content | S-02 | Content/Design | Microcopy list | Doc | No | [RECOMMENDED] | Low | 1–2 h | 2 | Confusing errors | Leaving 'Submit' and 'Error' | Poor usability | Yes | No — included in base price | No
P-05 | P | Copywriting | Proofread and content approval | Proofread all copy; client approves final text in writing | Client is responsible for factual accuracy of their content | Content | P-01..P-04 or O-02 | Content/PM | Approved copy | Approval email/sign-off | Yes | [MUST HAVE] | Low | 1–2 h | 2 | Typos at launch; wrong prices/claims | No sign-off on factual content | Liability for wrong info | Yes | No — included in base price | No
P-06 | P | Copywriting | Translation | Translate content to additional language(s) by qualified translator; client review | Multilingual audiences | Content | P-05 | Content | Translated copy | Files + approval | Yes | [CONDITIONAL] | Medium | Varies by words | 5 | Machine-translation errors | No native review | Embarrassing errors | Cond | Yes — separate line item | No
Q-01 | Q | UX | Key user flows | Map flows for primary tasks (call, enquire, book, buy) from entry to success | Ensures site serves goals | Design | E-01, L-02 | Design | Flow diagrams | Diagram file | No | [RECOMMENDED] | Medium | 1–3 h | 2 | Designing pages without purpose | Skipping mobile flow | Low conversion | Yes | No — included in base price | No
Q-02 | Q | UX | Information architecture and navigation | Define navigation labels, hierarchy, footer links, URL structure | Findability | Design | E-02 | Design | IA/navigation spec | Doc/diagram | Yes | [MUST HAVE] | Medium | 1–2 h | 2 | Too many menu items | Internal jargon labels | Confusing site | Yes | No — included in base price | No
Q-03 | Q | UX | Page content hierarchy | For each template define section order and priority | Basis for wireframes | Design | Q-02 | Design | Content outlines | Doc | No | [RECOMMENDED] | Low | 1–2 h | 2 | Rework in wireframes | Starting visuals first | Weak structure | Yes | No — included in base price | No
Q-04 | Q | UX | Conversion points and CTAs plan | Place calls, WhatsApp, forms, booking CTAs; define tracking events | Links design to goals | Design | Q-01 | Design/PM | CTA plan | Doc | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Too many CTAs | No tracking plan | Can't measure results | Yes | No — included in base price | No
R-01 | R | Wireframes | Low-fidelity wireframes | Grey-box wireframes, mobile-first, for each unique template | Cheap to change; locks structure before visuals | Design | Q-03 | Design | Wireframes | Figma/file link | No | [RECOMMENDED] | Medium | 2–6 h | 5 | Client sees as final design | Adding colour too early | Expensive visual rework | Yes | No — included in base price | No
R-02 | R | Wireframes | Wireframe review with client | Walkthrough; collect consolidated feedback | Early alignment | Design | R-01 | Design/PM | Feedback list | Meeting notes | Yes | [RECOMMENDED] | Low | 0.5–1 h | 1 | Scope expansion | Accepting new pages as 'tweaks' | Scope creep | Yes | No — included in base price | No
R-03 | R | Wireframes | Wireframe revisions | Apply one consolidated round; record approval | Stable structure | Design | R-02 | Design | Revised wireframes | Version link + approval | Yes | [RECOMMENDED] | Low | 1–3 h | 2 | Endless rounds | Untracked changes | Delay | Yes | No — included in base price | No
S-01 | S | UI Design | Moodboard and style direction | 1–2 visual directions (colour, type, imagery, UI style) | Agrees look before detailed design | Design | N-01 | Design | Moodboard | Figma/file link | Yes | [RECOMMENDED] | Low | 1–3 h | 2 | Too many options | Offering 5 directions | Decision paralysis | Yes | No — included in base price | No
S-02 | S | UI Design | Homepage high-fidelity design | Desktop and mobile designs of homepage with real content | Sets visual language | Design | S-01, R-03 | Design | Homepage design | Figma link/export | Yes | [MUST HAVE] | High | 4–10 h | 10 | Lorem ipsum hides content issues | Designing desktop only | Mobile afterthought | Yes | No — included in base price | No
S-03 | S | UI Design | Inner page template designs | Designs for each unique template (service, about, contact, blog list/post, product) desktop+mobile | Complete design coverage | Design | S-02 | Design | Template designs | Figma link | Yes | [MUST HAVE] | Medium | 2–5 h/template | 4 | Template count creep | Designing every page instead of templates | Overrun | Yes | No — included in base price | No
S-04 | S | UI Design | Interaction and state designs | Hover, focus, active, disabled, loading, error, success, empty states for components | Developers otherwise improvise | Design | S-02 | Design | State specs | Figma frames | No | [RECOMMENDED] | Medium | 1–3 h | 2 | Inconsistent behaviour | Forgetting focus states | Accessibility failures | Yes | No — included in base price | No
S-05 | S | UI Design | Design accessibility check | Check contrast (4.5:1 text), target sizes (24px min), focus visibility, not relying on colour alone | Cheaper to fix in design | Design | S-02 | Design | Accessibility notes | Checker screenshots | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Brand colours fail contrast | Light grey text | Accessibility failures | Yes | No — included in base price | No
S-06 | S | UI Design | Design handoff specification | Export assets, document spacing, breakpoints, component names, interactions | Accurate implementation | Design | S-03 | Design | Handoff file | Figma dev link | No | [RECOMMENDED] | Low | 1–2 h | 2 | Misinterpretation | Assets not exported | Rework | Yes | No — included in base price | No
T-01 | T | Design System | Colour tokens | Define named colour tokens (primary, surface, text, border, states) incl. dark mode if needed | Consistency and easy changes | Design | S-01 | Design | Token list | Figma variables/file | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Hard-coded colours | No state colours | Inconsistent UI | Yes | No — included in base price | No
T-02 | T | Design System | Typography scale | Font families, sizes, weights, line heights for headings/body across breakpoints | Readability | Design | S-01 | Design | Type scale | File | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Too many font weights (slow) | Tiny mobile text | Poor readability | Yes | No — included in base price | No
T-03 | T | Design System | Spacing, grid and breakpoints | Spacing scale, container widths, breakpoints | Responsive consistency | Design | S-01 | Design | Layout spec | File | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Arbitrary spacing | Pixel-perfect only at one width | Inconsistent layout | Yes | No — included in base price | No
T-04 | T | Design System | Component library | Buttons, links, inputs, cards, nav, modals, accordions, alerts with variants/states | Speeds design and build | Design | T-01..T-03 | Design | Component set | Figma components | No | [RECOMMENDED] | Medium | 2–6 h | 5 | Over-engineering for small sites | Components without states | Inconsistent UI | Cond | No — included in base price | No
T-05 | T | Design System | Icons and image style | Choose licensed icon set and image treatment rules | Visual cohesion; licence clarity | Design | S-01 | Design | Icon/image guide | File + licence | No | [OPTIONAL] | Low | 0.5–1 h | 1 | Unlicensed icons | Mixing icon styles | Messy visuals | Cond | No — included in base price | No
U-01 | U | Client Design Approval | Design presentation | Present designs explaining rationale tied to goals | Better feedback quality | Design | S-02/S-03 | Design | Presentation notes | Meeting record | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Taste-based debates | Sending link with no context | Random feedback | Yes | No — included in base price | No
U-02 | U | Client Design Approval | Consolidated design feedback | Client sends one consolidated list per round from the decision-maker | Controls rounds | Design | U-01 | PM | Feedback list | Client email/doc | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Conflicting feedback | Accepting drip feedback | Round explosion | Yes | No — included in base price | No
U-03 | U | Client Design Approval | Design revision round | Apply agreed changes; classify out-of-scope items as change requests | Controlled iteration | Design | U-02 | Design | Revised designs | Version history | Yes | [MUST HAVE] | Medium | 1–6 h/round | 4 | Unlimited tweaks | Not counting rounds | Unpaid work | Yes | No — included in base price | No
U-04 | U | Client Design Approval | Written design sign-off | Client approves designs in writing; later visual changes are change requests | Freezes design before development | Design | U-03 | PM | Design approval | Signed approval/email | Yes | [MUST HAVE] | Low | 15 min | 1 | Redesign during development | Starting code before approval | Costly rework | Yes | No — included in base price | No
V-01 | V | Frontend Development | Initialize frontend project | Create project with chosen framework/generator, set Node version, scripts (dev/build/preview) | Reproducible foundation | Development | L-04, J-04 | FE | Project scaffold | Initial commit | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Wrong framework version | Unpinned runtime | Build breaks later | Yes | No — included in base price | No
V-02 | V | Frontend Development | Establish folder structure and conventions | Folders for components, pages, styles, assets, utils; naming rules in README | Maintainability, easier handover | Development | V-01 | FE | Structure + README section | Commit | No | [RECOMMENDED] | Low | 0.5 h | 1 | Chaotic codebase | No conventions | Hard handover | Yes | No — included in base price | No
V-03 | V | Frontend Development | Configure dependencies and lockfile | Add only needed packages; commit lockfile; record licences | Supply-chain and licence control | Development | V-01 | FE | package manifest + lockfile | Commit | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Vulnerable/abandoned packages | Installing heavy libs for small needs | Bloat, vulnerabilities | Yes | No — included in base price | Yes
V-04 | V | Frontend Development | Linting, formatting and pre-commit hooks | Configure linter/formatter and optional pre-commit checks | Consistent code between two developers | Development | V-01 | FE | Config files | Commit | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Style fights | Skipping on small projects | Messy diffs | Yes | No — included in base price | No
V-05 | V | Frontend Development | Global styles and CSS variables | Reset/normalize, CSS custom properties from tokens, base element styles | Consistent look | Development | T-01..T-03 | FE | Global stylesheet | Commit | No | [MUST HAVE] | Low | 1–2 h | 2 | Specificity conflicts | Hard-coding values everywhere | Inconsistent UI | Yes | No — included in base price | No
V-06 | V | Frontend Development | Typography and font loading | Implement type scale; self-host or optimise web fonts with font-display, subsetting, preload of critical font | Readability and performance | Development | T-02 | FE | Font setup | Commit + Lighthouse note | No | [MUST HAVE] | Low | 1–2 h | 2 | Layout shift from fonts; licence breach | Loading 6 weights | Slow, janky text | Yes | No — included in base price | No
V-07 | V | Frontend Development | Layout primitives | Containers, grid/flex utilities, section spacing, responsive breakpoints | Reuse across pages | Development | T-03 | FE | Layout components | Commit | No | [RECOMMENDED] | Low | 1–2 h | 2 | Inconsistent spacing | One-off layouts per page | Maintenance cost | Yes | No — included in base price | No
V-08 | V | Frontend Development | Header and desktop navigation | Logo, menu, active states, CTA button, skip link | Primary wayfinding | Development | V-05 | FE | Header component | Commit + screenshot | No | [MUST HAVE] | Medium | 1–3 h | 2 | Menu overflow | No active state; no skip link | Poor navigation | Yes | No — included in base price | No
V-09 | V | Frontend Development | Responsive mobile navigation | Accessible menu toggle (button with aria-expanded), focus management, close on Escape, scroll lock | Most local-business traffic is mobile | Development | V-08 | FE | Mobile nav | Commit + device screenshots | No | [MUST HAVE] | Medium | 2–4 h | 4 | Keyboard traps | Div as button; no Escape close | Unusable on mobile/for keyboard users | Yes | No — included in base price | No
V-10 | V | Frontend Development | Footer | Contact details, links, legal pages, social links, copyright line | Trust and legal link placement | Development | V-05 | FE | Footer component | Commit | No | [MUST HAVE] | Low | 1–2 h | 2 | Wrong contact info | Missing legal links | Trust/compliance gaps | Yes | No — included in base price | No
V-11 | V | Frontend Development | Build homepage sections | Implement each homepage section from design with real content | Core page | Development | U-04, V-05..V-10 | FE | Homepage | Commit + staging URL | No | [MUST HAVE] | High | 4–10 h | 10 | Pixel-drift from design | Building before content final | Rework | Yes | No — included in base price | No
V-12 | V | Frontend Development | Build inner page templates | Implement each approved template and populate pages | Complete site | Development | V-11 | FE | Page templates | Commits + staging URLs | No | [MUST HAVE] | Medium | 2–5 h/template | 4 | Template count creep | Copy-pasting instead of templates | Maintenance cost | Yes | No — included in base price | No
V-13 | V | Frontend Development | Reusable UI components | Buttons, cards, accordions, tabs, modals, carousels (only if needed) with accessible behaviour | Consistency and accessibility | Development | T-04 | FE | Components | Commits | No | [RECOMMENDED] | Medium | 2–6 h | 5 | Inaccessible carousels/modals | Auto-rotating sliders | Accessibility failures | Yes | No — included in base price | No
V-14 | V | Frontend Development | Responsive images | srcset/sizes, width/height attributes, lazy-load below fold, eager/priority for hero | LCP and CLS | Development | O-05 | FE | Image implementation | Commit + Lighthouse | No | [MUST HAVE] | Low | 1–2 h | 2 | Layout shift | Lazy-loading hero image | Poor Core Web Vitals | Yes | No — included in base price | No
V-15 | V | Frontend Development | Implement form UI | Accessible fields with visible labels, autocomplete attributes, input types, required indicators | Forms are the main conversion point | Development | AB-01 | FE | Form components | Commit | No | [MUST HAVE] | Medium | 1–3 h | 2 | Placeholder-as-label | Wrong input types on mobile | Lost leads | Yes | No — included in base price | No
V-16 | V | Frontend Development | Client-side validation | Inline validation with clear messages linked via aria-describedby; never the only validation | Better UX; server still validates | Development | V-15 | FE | Validation logic | Commit + test | No | [MUST HAVE] | Low | 1–2 h | 2 | Blocking valid Indian phone formats | Over-strict regex | Lost leads | Yes | No — included in base price | No
V-17 | V | Frontend Development | Loading states | Button disabled/spinner on submit, skeletons for async content, prevent double submit | Prevents duplicate submissions | Development | V-15 | FE | Loading UI | Commit | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Duplicate leads/orders | No feedback on slow networks | User confusion | Yes | No — included in base price | No
V-18 | V | Frontend Development | Error and empty states | Friendly network/server error messages, retry, empty lists | Resilience | Development | V-15 | FE | Error UI | Commit | No | [MUST HAVE] | Low | 1–2 h | 2 | Silent failures | Showing raw error text | Lost leads, leaked info | Yes | No — included in base price | No
V-19 | V | Frontend Development | Animations and transitions | Subtle transitions respecting prefers-reduced-motion; no layout-shifting animations | Polish without harming accessibility/perf | Development | V-11 | FE | Animations | Commit | No | [OPTIONAL] | Low | 1–3 h | 2 | Motion sickness, INP hit | Heavy animation libraries | Slower site | Cond | No — included in base price | No
V-20 | V | Frontend Development | 404 and error pages | Custom 404 with navigation/search; server error page | Recovers lost visitors | Development | V-08 | FE | 404/500 pages | Commit + URL test | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Soft-404 (200 status) | Default server page | Lost visitors, SEO issues | Yes | No — included in base price | No
V-21 | V | Frontend Development | Favicon, app icons and manifest | Favicon set, apple-touch-icon, theme colour, web manifest if relevant | Brand recognition in tabs/bookmarks | Development | N-01 | FE | Icon files | Commit | No | [MUST HAVE] | Low | 0.5 h | 1 | Missing icons look unprofessional | Only one favicon size | Generic browser icon | Yes | No — included in base price | No
V-22 | V | Frontend Development | API integration layer | Central fetch/client module with timeouts, error handling, typed responses | Maintainable data access | Development | Z-01 | FE | API client | Commit | No | [CONDITIONAL] | Medium | 1–3 h | 2 | Keys exposed in frontend | Calling third-party APIs with secret keys from browser | Leaked keys | Cond | No — included in base price | No
V-23 | V | Frontend Development | Consent banner UI | Consent UI for non-essential cookies/trackers where client chooses to use them; blocks tags until consent | Privacy expectations and DPDP consent principles | Development | AJ-01 | FE | Banner | Commit + test | Yes | [CONDITIONAL] | Medium | 2–4 h | 4 | Dark patterns (pre-ticked) | Banner that doesn't actually block scripts | Privacy complaints | Cond | Conditional — depends on scope | Yes
V-24 | V | Frontend Development | Print styles | Print stylesheet for menus, price lists, event pages | Some local businesses need printable pages | Development | V-12 | FE | Print CSS | Commit | No | [OPTIONAL] | Low | 0.5–1 h | 1 | None major | Forgetting when requested | Poor printouts | No | Conditional — depends on scope | No
V-25 | V | Frontend Development | Frontend tests | Component/unit tests for logic, basic end-to-end for key flows | Prevent regressions | Development | V-11..V-18 | FE | Tests | Test run output | No | [RECOMMENDED] | Medium | 2–6 h | 5 | False confidence | Testing only happy paths | Regressions | Cond | No — included in base price | No
W-01 | W | Backend Development | Initialize backend project | Scaffold server/serverless functions with runtime version, structure, scripts | Foundation | Development | L-04 | BE | Backend scaffold | Commit | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Unneeded backend for static sites | Building custom backend where a service suffices | Over-engineering | Cond | No — included in base price | No
W-02 | W | Backend Development | Environment configuration and secrets | .env.example with names only; secrets in host secret store; separate dev/staging/prod values | Secrets must never be in code or repo | Development | W-01 | BE | Config + .env.example | Commit (no secrets) | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Secrets committed | Sharing .env over WhatsApp | Credential leak | Yes | No — included in base price | Yes
W-03 | W | Backend Development | Data models and business logic | Implement entities (leads, bookings, products) and rules | Core behaviour | Development | X-02 | BE | Models/services | Commits + tests | No | [CONDITIONAL] | High | 3–12 h | 10 | Logic errors | Mixing logic into routes | Bugs, hard maintenance | Cond | No — included in base price | No
W-04 | W | Backend Development | API endpoints | Implement endpoints for forms, content, bookings with consistent responses | Frontend/backend contract | Development | Z-01, W-03 | BE | Endpoints | Commits + API docs | No | [CONDITIONAL] | Medium | 1–3 h/endpoint | 3 | Missing auth checks | No input validation | Vulnerabilities | Cond | No — included in base price | No
W-05 | W | Backend Development | Server-side validation and sanitisation | Validate type/length/format of every input; parameterised queries; encode output | Injection prevention | Development | W-04 | BE | Validation layer | Commit + tests | No | [MUST HAVE] | Medium | 1–3 h | 3 | XSS/SQL injection | Trusting client validation | Breach | Yes | No — included in base price | No
W-06 | W | Backend Development | Error handling and logging | Central error handler, structured logs without personal data/secrets, correlation IDs | Diagnose issues safely | Development | W-01 | BE | Logging setup | Commit + sample log | No | [MUST HAVE] | Low | 1–2 h | 2 | Logging passwords/PII | Stack traces to users | Leaks, blind debugging | Cond | No — included in base price | Yes
W-07 | W | Backend Development | Rate limiting and abuse protection | Limit form/login/API requests per IP/user | Prevents spam and brute force | Development | W-04 | BE | Rate limits | Config + test | No | [MUST HAVE] | Low | 1–2 h | 2 | Spam floods, SMS/email cost spikes | No limits on OTP/email endpoints | Abuse costs | Cond | No — included in base price | No
W-08 | W | Backend Development | File upload handling | Validate type (content not extension), size limits, virus scan if needed, private storage, random names | Uploads are a common attack vector | Development | W-04 | BE | Upload module | Commit + tests | No | [CONDITIONAL] | Medium | 2–5 h | 4 | Malware hosting, RCE | Storing uploads in web root | Compromise | Cond | No — included in base price | No
W-09 | W | Backend Development | Scheduled jobs | Cron/scheduled tasks (reminders, cleanup, backups) with monitoring | Automation | Development | W-03 | BE | Jobs | Config + logs | No | [CONDITIONAL] | Medium | 1–3 h | 2 | Silent failures | No alerting | Missed reminders | Cond | No — included in base price | Yes
W-10 | W | Backend Development | Backend tests | Unit/integration tests for logic and endpoints incl. auth failures | Confidence for changes | Development | W-04 | BE | Tests | Test output | No | [RECOMMENDED] | Medium | 2–6 h | 5 | False confidence | Only happy paths | Regressions | Cond | No — included in base price | No
X-01 | X | Database | Choose database and hosting | Select managed DB appropriate to scale/budget; region; backups included | Data durability | Development | L-04 | BE | Decision record | ADR entry | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Unmanaged DB with no backups | Free tiers that pause/delete | Data loss | Cond | No — included in base price | No
X-02 | X | Database | Schema design | Tables/collections, relations, constraints, ERD; data minimisation | Correct data model | Development | E-03 | BE | Schema + ERD | Migration files + diagram | No | [CONDITIONAL] | Medium | 1–4 h | 3 | Storing unnecessary personal data | No constraints | Data quality issues | Cond | No — included in base price | No
X-03 | X | Database | Migrations | Versioned migration scripts for schema changes | Reproducible deploys | Development | X-02 | BE | Migration scripts | Commits | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Manual prod changes | Editing prod schema by hand | Drift, outages | Cond | No — included in base price | Yes
X-04 | X | Database | Seed and test data | Non-personal sample data for dev/staging | Safe testing | Development | X-03 | BE | Seed script | Commit | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Real customer data in staging | Copying prod DB to dev | Privacy breach | Cond | No — included in base price | No
X-05 | X | Database | Indexes and constraints | Add indexes for queries; unique/foreign keys | Performance and integrity | Development | X-02 | BE | Index migration | Commit | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Slow queries | No indexes | Slow admin | Cond | No — included in base price | No
X-06 | X | Database | Least-privilege database users | App user with only required permissions; separate admin credentials | Limits blast radius | Development | X-01 | BE | DB users | Config record (no passwords) | No | [CONDITIONAL] | Low | 0.5 h | 1 | App running as DB superuser | One password everywhere | Larger breach impact | Cond | No — included in base price | No
X-07 | X | Database | Backup configuration and restore test | Automated backups with retention; perform one test restore | Backups you haven't restored are assumptions | Launch | X-01 | BE/DevOps | Backup config + restore report | Screenshot/log | No | [MUST HAVE] | Medium | 1–2 h | 2 | Corrupt/incomplete backups | Never testing restore | Unrecoverable loss | Cond | No — included in base price | Yes
Y-01 | Y | Authentication | Authentication strategy | Choose managed auth vs framework auth; define user types; passkey/OTP/password options | Secure login is hard to build from scratch | Development | E-03 | BE | Auth decision | ADR | No | [CONDITIONAL] | Medium | 1–2 h | 2 | Rolling your own crypto | Storing plaintext passwords | Breach | Cond | No — included in base price | No
Y-02 | Y | Authentication | Signup, login and logout | Implement flows with secure password hashing or provider; generic error messages | Core access | Development | Y-01 | BE/FE | Auth flows | Commits + tests | No | [CONDITIONAL] | Medium | 3–8 h | 7 | Account enumeration | Revealing 'email not found' | Security weakness | Cond | No — included in base price | No
Y-03 | Y | Authentication | Password reset and email verification | Single-use, expiring tokens; rate limited; no password in email | Account recovery safety | Development | Y-02, AC-01 | BE | Reset flow | Tests | No | [CONDITIONAL] | Medium | 2–4 h | 4 | Token reuse | Long-lived reset links | Account takeover | Cond | No — included in base price | No
Y-04 | Y | Authentication | Role-based authorization | Enforce roles/ownership on server for every protected route/object | Broken access control is the top web risk | Development | Y-02 | BE | Authorization checks | Tests incl. negative cases | No | [CONDITIONAL] | Medium | 2–6 h | 5 | IDOR | Hiding buttons instead of checking server-side | Data exposure | Cond | No — included in base price | No
Y-05 | Y | Authentication | Session and token security | Secure, HttpOnly, SameSite cookies; expiry; rotation on login; logout invalidation | Session hijack prevention | Development | Y-02 | BE | Session config | Config + tests | No | [CONDITIONAL] | Low | 1–2 h | 2 | Tokens in localStorage | Never-expiring sessions | Hijacking | Cond | No — included in base price | No
Y-06 | Y | Authentication | MFA for admin accounts | Enable MFA/2FA on admin logins (app, platform, CMS) | Admin compromise = site compromise | Development | Y-02 or AD-03 | BE | MFA enabled | Screenshot/settings record | No | [RECOMMENDED] | Low | 0.5–2 h | 1 | SMS-only MFA weaknesses | Shared admin account | Takeover | Cond | No — included in base price | Yes
Z-01 | Z | APIs | API contract and documentation | Document endpoints, request/response shapes, errors, auth | Shared understanding; handover | Development | E-03 | BE | API docs | Doc/OpenAPI file | No | [CONDITIONAL] | Medium | 1–3 h | 2 | Undocumented behaviour | Docs out of date | Hard maintenance | Cond | No — included in base price | No
Z-02 | Z | APIs | Implement and version APIs | Build to contract; version when breaking changes occur | Stability | Development | Z-01 | BE | API | Commits | No | [CONDITIONAL] | Medium | Varies | 5 | Breaking clients | No versioning | Outages | Cond | No — included in base price | No
Z-03 | Z | APIs | API key scoping and restriction | Restrict keys by domain/IP/API; separate keys per environment; server-side use only for secrets | Stolen keys cause bills and abuse | Development | AA-01 | BE | Key restriction record | Console screenshot | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Unrestricted Maps keys billed | One key for dev and prod | Unexpected charges | Cond | No — included in base price | Yes
AA-01 | AA | Third-party Integrations | Third-party account ownership check | Confirm each service account is created by/for the client (client email, client billing) with you as invited user | Prevents developer lock-in and billing disputes | Development | E-05 | PM | Account register entries | Register + invite emails | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Services on developer's card | Creating accounts 'temporarily' in own name | Painful migrations later | Yes | No — included in base price | No
AA-02 | AA | Third-party Integrations | Maps integration | Embed map or Maps API with restricted key; correct business location | Local businesses need directions | Development | AA-01 | FE | Map | Staging URL | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | API billing | Unrestricted key | Charges | Cond | No — included in base price | No
AA-03 | AA | Third-party Integrations | WhatsApp contact integration | Click-to-chat link with prefilled message, or Business Platform integration if requested | Preferred channel for Indian customers | Development | AA-01 | FE | WhatsApp CTA | Test record | No | [CONDITIONAL] | Low | 0.5 h (link) / 4–10 h (API) | 1 | Wrong number format | Personal number instead of business number | Missed enquiries | Cond | Conditional — depends on scope | No
AA-04 | AA | Third-party Integrations | Social media embeds | Links/feeds/embeds with performance and privacy consideration | Social proof | Development | AA-01 | FE | Embeds | Commit | No | [OPTIONAL] | Low | 0.5–2 h | 1 | Heavy third-party scripts | Embedding full feeds | Slow pages | Cond | No — included in base price | No
AA-05 | AA | Third-party Integrations | CRM or email marketing integration | Send leads/subscribers to client's CRM/list with consent recorded | Automates lead handling | Development | AA-01, AB-04 | BE | Integration | Test record | No | [CONDITIONAL] | Medium | 2–6 h | 5 | Consent not captured | Adding everyone to marketing list | Privacy complaints | Cond | Yes — separate line item | Yes
AA-06 | AA | Third-party Integrations | Integration failure handling | Timeouts, retries, fallback (e.g., store lead locally and email) and alerts | Third parties fail | Development | AA-02..AA-05 | BE | Fallback logic | Tests | No | [RECOMMENDED] | Medium | 1–3 h | 2 | Silent lead loss | Assuming APIs never fail | Lost business | Cond | No — included in base price | No
AB-01 | AB | Forms | Form specification and data minimisation | Define fields, required ones, purpose of each, where data goes, retention | Collect only what is needed | Development | E-03 | PM | Form spec | Doc | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Over-collection of personal data | Asking for DOB/Aadhaar unnecessarily | Privacy risk | Yes | No — included in base price | No
AB-02 | AB | Forms | Form submission handling | Deliver to email/DB/CRM reliably; store copy; notify client | Lead delivery is the site's job | Development | AB-01, AC-01 | BE | Handler | Test submissions | No | [MUST HAVE] | Medium | 1–3 h | 2 | Emails landing in spam | Only emailing, no storage | Lost leads | Yes | No — included in base price | Yes
AB-03 | AB | Forms | Spam protection | Honeypot, rate limit, time-trap, accessible CAPTCHA only if needed | Reduce spam without blocking users | Development | AB-02 | BE | Anti-spam | Config + test | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Blocking real users | Inaccessible image CAPTCHA | Lost leads | Yes | No — included in base price | Yes
AB-04 | AB | Forms | Notice and consent text on forms | Short notice of purpose with link to privacy notice; separate unticked opt-in for marketing | Aligns with DPDP notice/consent principles | Development | AB-01, BK-01 | PM/FE | Notice text | Screenshot | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Pre-ticked consent | Bundling marketing consent | Privacy complaints | Yes | No — included in base price | No
AB-05 | AB | Forms | Confirmation and conversion tracking | Success message/thank-you page; fire conversion event | Feedback to user; measurable goals | Development | AB-02, AJ-03 | FE | Confirmation + event | Analytics debug screenshot | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Double-counted conversions | Tracking on click not success | Wrong metrics | Yes | No — included in base price | No
AB-06 | AB | Forms | End-to-end form test | Submit every form on staging and production; verify email, storage, auto-reply | Most embarrassing failure is a silent form | QA | AB-02..AB-05 | QA | Test record | Test log + received emails | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Broken production SMTP | Testing only on staging | Lost leads | Yes | No — included in base price | Yes
AC-01 | AC | Email | Transactional email service setup | Configure sending service in client's account; verify sending domain | Reliable delivery | Development | AA-01 | BE/DevOps | Configured service | Console screenshot | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Using personal Gmail SMTP | Sending from free email domains | Spam folder | Cond | No — included in base price | Yes
AC-02 | AC | Email | SPF, DKIM and DMARC records | Add/merge SPF (one record), DKIM keys, DMARC policy for sending domain | Major mailbox providers expect authentication | Development | AC-01, AW-01 | DevOps | DNS records | DNS lookup output | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Multiple SPF records break mail | Overwriting client's existing MX/SPF | Email outage | Cond | No — included in base price | Yes
AC-03 | AC | Email | Email templates | Notification and auto-reply templates with plain-text version and business details | Professional, accessible emails | Development | AC-01 | FE/BE | Templates | Commit + test sends | Optional | [CONDITIONAL] | Low | 1–2 h | 2 | Broken rendering | Images-only emails | Poor delivery | Cond | No — included in base price | No
AC-04 | AC | Email | Deliverability test | Send tests to Gmail/Outlook/Yahoo; check spam placement and headers | Verify authentication works | QA | AC-02 | QA | Test report | Screenshots of headers | No | [MUST HAVE] | Low | 0.5 h | 1 | Leads in spam | Testing only to own domain | Silent lead loss | Cond | No — included in base price | Yes
AC-05 | AC | Email | Business mailbox setup | Set up client mailboxes on client's chosen provider; MX records | Often requested with website | Development | AW-01 | DevOps | Mailboxes | Admin console record | Yes | [CONDITIONAL] | Medium | 1–4 h | 3 | Email downtime during MX change | Changing MX without inventory | Email outage | Cond | Yes — separate line item | Yes
AD-01 | AD | CMS | CMS selection | Choose CMS (none, headless, WordPress, hosted builder) based on who edits and how often | Right tool for client's skills | Development | L-04 | FE/BE | Decision record | ADR | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Over-complex CMS | Choosing CMS client can't use | Support burden | Cond | No — included in base price | No
AD-02 | AD | CMS | Content model | Define collections/fields/validation for editable content | Structured, safe editing | Development | AD-01 | BE | Content model | Config/commit | No | [CONDITIONAL] | Medium | 2–5 h | 4 | Editors breaking layouts | Free-form rich text everywhere | Broken pages | Cond | No — included in base price | No
AD-03 | AD | CMS | Editor roles and permissions | Client admin, editor roles; developer account separate and removable | Least privilege and clean handover | Development | AD-01 | BE | Role config | Screenshot | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Everyone as admin | Sharing one admin login | Takeover risk | Cond | No — included in base price | Yes
AD-04 | AD | CMS | Content entry and migration | Enter/migrate agreed number of pages/items | Site populated | Development | AD-02, P-05 | Content | Populated CMS | Page count record | No | [CONDITIONAL] | Medium | 0.25–0.5 h/item | 3 | Unbounded data entry | Including unlimited entry | Unpaid work | Cond | Conditional — depends on scope | No
AD-05 | AD | CMS | Plugin/extension vetting and licences | Check maintenance status, security history, licence terms and renewal cost of each plugin | Plugins are a major vulnerability and licence risk | Development | AD-01 | BE | Plugin register | Register | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Nulled/pirated plugins | Using developer-licence on client site | Malware, licence breach | Cond | No — included in base price | Yes
AE-01 | AE | Admin Dashboard | Admin requirements | Define admin tasks, roles, data views, exports | Avoid over-building | Development | E-03 | PM | Admin spec | Doc | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Scope creep | Building features no one uses | Overrun | Cond | Yes — separate line item | No
AE-02 | AE | Admin Dashboard | Build admin screens | List/detail/edit screens with server-side authorization | Client manages data | Development | AE-01, Y-04 | FE/BE | Admin UI | Commits + screenshots | No | [CONDITIONAL] | High | 6–20 h | 18 | Access control bugs | Client-side only checks | Data exposure | Cond | Yes — separate line item | No
AE-03 | AE | Admin Dashboard | Audit log | Record who changed what and when for admin actions | Accountability | Development | AE-02 | BE | Audit log | Sample entries | No | [OPTIONAL] | Medium | 2–4 h | 4 | Storing excessive PII | No retention rule | Poor traceability | Cond | Yes — separate line item | No
AE-04 | AE | Admin Dashboard | Data export | CSV export of leads/orders for client | Client owns and uses their data | Development | AE-02 | BE | Export feature | Sample export | No | [OPTIONAL] | Low | 1–2 h | 2 | Export exposes data broadly | No access control | Leak | Cond | Yes — separate line item | No
AF-01 | AF | E-commerce | E-commerce platform decision | Choose hosted platform vs WooCommerce vs custom based on SKUs, budget, maintenance, payment and GST invoicing needs | Custom e-commerce is expensive and risky | Development | E-03 | PM/BE | Decision record | ADR | Yes | [CONDITIONAL] | Medium | 1–2 h | 2 | Custom cart where hosted fits | Ignoring transaction fees and renewals | Cost overrun | Cond | Yes — separate line item | No
AF-02 | AF | E-commerce | Product catalogue setup | Categories, attributes, variants, prices incl./excl. GST, images, stock | Accurate listings | Development | AF-01, O-02 | Content/BE | Catalogue | Product count record | No | [CONDITIONAL] | Medium | 0.25–0.5 h/product | 5 | Wrong prices | Unbounded product entry in fixed fee | Unpaid work, pricing errors | Cond | Yes — separate line item | Yes
AF-03 | AF | E-commerce | Cart and checkout | Cart, address, shipping choice, order summary with total price, explicit consent (no pre-ticked boxes) | Core purchase flow; e-commerce rules require clear consent and pricing | Development | AF-02, AH-02 | FE/BE | Checkout | E2E test record | No | [CONDITIONAL] | High | 6–16 h | 15 | Abandoned carts, hidden charges | Pre-ticked add-ons | Consumer complaints | Cond | Yes — separate line item | No
AF-04 | AF | E-commerce | Tax display and invoice generation | Show taxes correctly; generate GST-compliant invoices per client's CA instructions | Client's tax compliance | Development | AF-03 | BE | Invoice template | Sample invoice reviewed by client's CA | Yes | [CONDITIONAL] | Medium | 2–6 h | 5 | Wrong GST treatment | Developer deciding tax rules | Client tax exposure | Cond | Yes — separate line item | No
AF-05 | AF | E-commerce | Shipping and delivery rules | Zones, rates, delivery estimates, COD rules if offered | Accurate costs/expectations | Development | AF-02 | BE | Shipping config | Test orders | Yes | [CONDITIONAL] | Medium | 1–4 h | 3 | Undercharging shipping | Ignoring pincode serviceability | Losses | Cond | Yes — separate line item | Yes
AF-06 | AF | E-commerce | E-commerce mandatory disclosures | Display seller legal name, address, customer care and grievance officer contacts, return/refund/exchange/shipping/payment terms as supplied by client | Consumer Protection (E-Commerce) Rules require prominent disclosures | Development | BK-04 | PM/FE | Policy pages + footer details | Screenshots | Yes | [CONDITIONAL] | Low | 1–2 h | 2 | Non-compliance | Developer writing policies without client/lawyer | Regulatory complaints | Cond | No — included in base price | Yes
AF-07 | AF | E-commerce | Order notifications | Customer and admin emails/SMS for order placed/shipped/refunded | Transparency | Development | AC-01 | BE | Notification templates | Test emails | No | [CONDITIONAL] | Medium | 2–4 h | 4 | Missing notifications | No admin alert | Missed orders | Cond | Yes — separate line item | Yes
AG-01 | AG | Booking Systems | Booking tool decision | Choose embedded booking service vs custom based on complexity, payments, reminders | Custom booking is complex | Development | E-03 | PM | Decision record | ADR | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Reinventing calendars | Custom build for simple needs | Overrun | Cond | Yes — separate line item | No
AG-02 | AG | Booking Systems | Availability and slots configuration | Services, durations, buffers, staff, holidays, time zone (IST) | Correct availability | Development | AG-01 | BE | Booking config | Test bookings | Yes | [CONDITIONAL] | Medium | 1–4 h | 3 | Double bookings | Wrong time zone | Angry customers | Cond | Yes — separate line item | Yes
AG-03 | AG | Booking Systems | Booking confirmations and reminders | Email/SMS/WhatsApp confirmations, reschedule/cancel links | Reduces no-shows | Development | AG-02, AC-01 | BE | Templates | Test messages | No | [CONDITIONAL] | Medium | 1–3 h | 2 | Messaging costs | No cancel link | No-shows | Cond | Yes — separate line item | Yes
AG-04 | AG | Booking Systems | Calendar sync | Two-way sync with client's calendar | Avoid conflicts | Development | AG-02 | BE | Sync | Test event | No | [CONDITIONAL] | Medium | 1–3 h | 2 | Sync loops | Syncing to developer calendar | Conflicts | Cond | Yes — separate line item | Yes
AH-01 | AH | Payments | Payment gateway account (client-owned) | Client applies and completes KYC with gateway; developer gets restricted team access | Settlements must go to client's bank; KYC is the merchant's obligation | Development | AA-01 | Client + PM | Gateway account | Team invite email | Yes | [CONDITIONAL] | Low | 0.5–1 h (dev time) | 1 | Account in developer's name | Developer doing KYC for client | Legal/financial disputes | Cond | No — included in base price | No
AH-02 | AH | Payments | Integrate hosted/tokenised checkout | Use gateway's hosted page or SDK so card data never touches your server | Avoid handling card data | Development | AH-01 | BE/FE | Checkout integration | Test transactions | No | [CONDITIONAL] | Medium | 3–8 h | 7 | Storing card data | Building custom card forms | Serious compliance breach | Cond | Yes — separate line item | No
AH-03 | AH | Payments | Webhook signature verification and idempotency | Verify webhook signatures; confirm payment server-side; process each event once | Prevents fake 'paid' orders | Development | AH-02 | BE | Webhook handler | Tests incl. forged payload | No | [CONDITIONAL] | Medium | 2–4 h | 4 | Fraudulent orders | Trusting redirect URL as proof of payment | Revenue loss | Cond | No — included in base price | No
AH-04 | AH | Payments | Refund and failed-payment flows | Handle failures, pending, refunds and reconciliation | Real-world payments fail | Development | AH-03 | BE | Flows | Test cases | No | [CONDITIONAL] | Medium | 2–4 h | 4 | Stuck orders | Only coding success path | Support burden | Cond | No — included in base price | No
AH-05 | AH | Payments | Test-to-live switch | Swap to live keys stored as secrets; small real transaction test and refund | Confirms real settlement | Launch | AH-04 | BE | Live config | Live test txn record | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Test keys in production | Live keys in repo | No real payments | Cond | No — included in base price | No
AI-01 | AI | SEO | URL structure and slugs | Short, readable, lowercase, hyphenated URLs matching IA | SEO and usability | Development | Q-02 | FE | URL map | Sitemap | No | [MUST HAVE] | Low | 0.5 h | 1 | Changing URLs after launch | IDs in URLs | Lost rankings | Yes | No — included in base price | No
AI-02 | AI | SEO | Titles and meta descriptions | Unique title and description per page with brand and location where relevant | Search snippets | Development | P-05 | Content/FE | Meta list | Crawl report | No | [MUST HAVE] | Low | 10–15 min/page | 2 | Duplicate titles | Same title on all pages | Poor CTR | Yes | No — included in base price | No
AI-03 | AI | SEO | Heading hierarchy | One H1 per page, logical H2/H3 nesting | SEO and screen readers | Development | V-12 | FE | Correct headings | Crawl/a11y report | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Styling-driven headings | Multiple H1s for styling | Poor structure | Yes | No — included in base price | No
AI-04 | AI | SEO | Canonical tags | Self-referencing canonicals; handle www/non-www, trailing slash, parameters | Avoids duplicate content | Development | AY-02 | FE | Canonicals | Crawl report | No | [MUST HAVE] | Low | 0.5 h | 1 | Canonical to staging domain | Hard-coded staging URLs | Indexing issues | Yes | No — included in base price | No
AI-05 | AI | SEO | XML sitemap | Auto-generated sitemap with production URLs only | Helps discovery | Development | AI-01 | FE | sitemap.xml | Live URL | No | [MUST HAVE] | Low | 0.5 h | 1 | Staging URLs in sitemap | Including noindex pages | Crawl waste | Yes | No — included in base price | Yes
AI-06 | AI | SEO | robots.txt and staging noindex | Production robots allows crawling and lists sitemap; staging blocked/noindex + auth | Prevent staging indexing; allow production | Launch | J-05 | DevOps | robots.txt | Live URL check | No | [MUST HAVE] | Low | 0.5 h | 1 | Launching with Disallow: / | Copying staging robots to prod | Site not indexed | Yes | No — included in base price | No
AI-07 | AI | SEO | Structured data | LocalBusiness/Organization, breadcrumbs, FAQ/Product where accurate; validate | Rich results eligibility | Development | P-05 | FE | JSON-LD | Validator screenshot | No | [RECOMMENDED] | Low | 1–2 h | 2 | Misleading markup | Marking up content not on page | Manual actions | Yes | No — included in base price | Yes
AI-08 | AI | SEO | Open Graph and social cards | og:title, og:description, og:image (1200×630), twitter card | Good link previews on WhatsApp/social | Development | N-01 | FE | OG tags + image | Share preview screenshot | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Broken previews | No OG image | Poor sharing | Yes | No — included in base price | No
AI-09 | AI | SEO | Redirect map from old site | Map old URLs to new with 301 redirects; test | Preserves traffic and links | Launch | D-05 | FE/DevOps | Redirect map | Map + test results | No | [CONDITIONAL] | Medium | 1–4 h | 3 | Traffic loss | Redirecting everything to homepage | Lost rankings | Cond | No — included in base price | No
AI-10 | AI | SEO | Business profile consistency | Ensure name, address, phone match Google Business Profile and site; link website (client-owned profile) | Local SEO trust signals | Launch | D-05 | Content | NAP checklist | Screenshots | Yes | [RECOMMENDED] | Low | 0.5–1 h | 1 | Profile owned by agency/stranger | Creating profile in developer account | Lost control of profile | Cond | Conditional — depends on scope | Yes
AI-11 | AI | SEO | Search Console setup and sitemap submission | Client verifies property (DNS preferred) as owner; developer added as user; submit sitemap | Indexing monitoring owned by client | Launch | AV-01 | DevOps | Verified property | Screenshot of users page | No | [MUST HAVE] | Low | 0.5 h | 1 | Developer as sole verified owner | Leaving developer tokens after handover | Client locked out | Yes | No — included in base price | Yes
AJ-01 | AJ | Analytics | Analytics property in client's account | Create analytics account/property owned by client; developer as property-level user | Data ownership | Development | AA-01 | DevOps | Property | Access-management screenshot | No | [MUST HAVE] | Low | 0.5 h | 1 | Agency-owned property | Creating under developer's account | Data lost when relationship ends | Yes | No — included in base price | No
AJ-02 | AJ | Analytics | Install tag with consent handling | Install analytics tag; gate on consent if client adopts consent-based approach | Privacy-respecting measurement | Development | AJ-01, V-23 | FE | Tag install | Tag assistant screenshot | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Tracking before consent | Duplicate tags | Bad data, complaints | Yes | No — included in base price | No
AJ-03 | AJ | Analytics | Conversion and event tracking | Track form success, calls (tel: clicks), WhatsApp clicks, bookings, purchases | Proves value against goals | Development | Q-04 | FE | Event plan + implementation | Debug view screenshots | No | [RECOMMENDED] | Medium | 1–3 h | 2 | Wrong events | Tracking clicks not completions | Misleading metrics | Yes | No — included in base price | Yes
AJ-04 | AJ | Analytics | Verify analytics data | Check real-time/debug data for page views and events on production | Confirms tracking works | Launch | AJ-02, AJ-03 | QA | Verification record | Screenshot | No | [MUST HAVE] | Low | 0.5 h | 1 | Silent tracking failure | Checking only staging | No data | Yes | No — included in base price | No
AK-01 | AK | Accessibility | Set accessibility target | Agree target (e.g., WCAG 2.2 Level AA for templates and flows built by you) and what is out of scope (client-uploaded content) | Makes accessibility testable and contractual | Scope | E-06 | PM | Target statement | Scope doc | Yes | [RECOMMENDED] | Low | 15 min | 1 | Promising full 'compliance' | Undefined target | Disputes, legal risk | Yes | No — included in base price | No
AK-02 | AK | Accessibility | Semantic HTML and landmarks | Use header/nav/main/footer, buttons for actions, links for navigation, lists, tables correctly | Foundation for assistive tech | Development | V-08 | FE | Semantic markup | Code review note | No | [MUST HAVE] | Low | Built into dev | 1 | Div soup | Clickable divs | Screen reader failures | Yes | No — included in base price | No
AK-03 | AK | Accessibility | Keyboard navigation and focus | All interactive elements reachable by Tab, visible focus, logical order, no traps, focus not hidden by sticky headers | Keyboard users and WCAG 2.2 focus criteria | QA | V-13 | FE/QA | Keyboard test record | Test checklist | No | [MUST HAVE] | Low | 1–2 h | 2 | Invisible focus | outline:none | Unusable for keyboard users | Yes | No — included in base price | No
AK-04 | AK | Accessibility | Alt text and media alternatives | Meaningful alt for informative images, empty alt for decorative; captions/transcripts for video | Non-visual access | Content | O-05 | Content | Alt text list | Audit report | Optional | [MUST HAVE] | Low | 1–2 h | 2 | Alt='image' | Filename alt text | Accessibility failures | Yes | No — included in base price | Yes
AK-05 | AK | Accessibility | Colour contrast verification | Check text and UI component contrast in built site | Readability for low vision | QA | S-05 | QA | Contrast report | Tool output | No | [MUST HAVE] | Low | 0.5 h | 1 | Brand colour failures | Checking only design file | Accessibility failures | Yes | No — included in base price | No
AK-06 | AK | Accessibility | Accessible form labels and errors | Labels tied to inputs, error text announced, not colour-only, redundant entry avoided | Forms are the conversion point | QA | V-15, V-16 | FE/QA | Form a11y test | Checklist | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Unlabelled inputs | Placeholder-only labels | Lost users | Yes | No — included in base price | No
AK-07 | AK | Accessibility | Automated accessibility scan | Run automated checker on each template; fix issues | Catches ~30–40% of issues quickly | QA | V-12 | QA | Scan report | Report file | No | [MUST HAVE] | Low | 0.5–1 h | 1 | False sense of compliance | Treating a clean scan as 'accessible' | Missed issues | Yes | No — included in base price | Yes
AK-08 | AK | Accessibility | Screen reader smoke test | Test key flows with NVDA/VoiceOver/TalkBack: headings, landmarks, forms, menus | Real assistive-tech behaviour | QA | AK-02..AK-06 | QA | Test notes | Notes/recording | No | [RECOMMENDED] | Medium | 1–2 h | 2 | Unannounced errors/menus | Never testing with AT | Hidden failures | Yes | No — included in base price | No
AL-01 | AL | Performance | Performance budget | Set targets: LCP ≤2.5 s, INP ≤200 ms, CLS ≤0.1, page weight and JS limits | Makes performance testable | Scope | E-06 | FE | Budget | Scope/NFR doc | No | [RECOMMENDED] | Low | 15–30 min | 1 | Unmeasured bloat | No budget | Slow site | Yes | No — included in base price | No
AL-02 | AL | Performance | Image optimisation | Modern formats, correct dimensions, compression, CDN | Images dominate page weight | Development | O-05 | FE | Optimised images | Lighthouse report | No | [MUST HAVE] | Low | 1–2 h | 2 | Quality loss | Serving desktop images to phones | Slow LCP | Yes | No — included in base price | Yes
AL-03 | AL | Performance | Font optimisation | Subset, preload critical, limit weights, font-display | Faster text rendering, less shift | Development | V-06 | FE | Font config | Report | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | FOIT/CLS | Many weights | Slow render | Yes | No — included in base price | No
AL-04 | AL | Performance | JavaScript and CSS optimisation | Remove unused code, split bundles, defer non-critical scripts, audit third-party scripts | INP and load time | Development | V-11 | FE | Optimised bundles | Bundle report | No | [RECOMMENDED] | Medium | 1–3 h | 2 | Breaking functionality | Loading every library globally | Poor INP | Yes | No — included in base price | No
AL-05 | AL | Performance | Caching and CDN | Cache headers for static assets (hashed filenames), compression (Brotli/gzip), CDN | Repeat-visit speed | Launch | AX-01 | DevOps | Cache config | Header check output | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Stale content | Caching HTML too aggressively | Users see old site | Yes | No — included in base price | Yes
AL-06 | AL | Performance | Lab performance test (mobile) | Lighthouse/PageSpeed on mobile profile for key templates; fix major issues | Pre-launch check | QA | AL-02..AL-05 | QA | Report | Saved reports | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Optimising for score only | Testing only desktop on fast Wi-Fi | Slow for real users | Yes | No — included in base price | No
AL-07 | AL | Performance | Field data review | After traffic accrues, review Core Web Vitals field data (Search Console/CrUX) | Real-user performance | Post-launch | BA-03 | FE | Review note | Screenshot | No | [POST-LAUNCH] | Low | 0.5 h | 1 | Not enough traffic for data | Relying on lab only | Unknown real performance | No | Conditional — depends on scope | Yes
AM-01 | AM | Security | Dependency vulnerability audit | Run package audit/scanner; update or replace vulnerable packages | Supply-chain risk (OWASP A03:2025) | QA | V-03 | FE/BE | Audit output | Report | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Breaking updates | Ignoring audit warnings | Known vulnerabilities live | Yes | No — included in base price | Yes
AM-02 | AM | Security | Security headers | HSTS, Content-Security-Policy, X-Content-Type-Options, Referrer-Policy, frame-ancestors, Permissions-Policy | Hardening against common attacks | Launch | AX-01 | DevOps | Header config | Header scan output | No | [RECOMMENDED] | Medium | 1–3 h | 2 | CSP breaking scripts | Copy-paste CSP without testing | Weaker security | Yes | No — included in base price | Yes
AM-03 | AM | Security | Secrets scan | Scan repo history for keys/passwords; rotate anything found | Leaked secrets are exploited quickly | QA | J-04 | BE | Scan result | Report | No | [MUST HAVE] | Low | 0.5 h | 1 | Secrets in git history | Deleting file but not history/rotating key | Account abuse | Yes | No — included in base price | No
AM-04 | AM | Security | Injection and XSS review | Review inputs/outputs; parameterised queries; output encoding; test common payloads | OWASP A05 Injection | QA | W-05 | BE/QA | Review checklist | Checklist + test log | No | [MUST HAVE] | Medium | 1–2 h | 2 | Stored XSS in admin | Rendering raw HTML from users | Compromise | Cond | No — included in base price | No
AM-05 | AM | Security | Access control review | Try accessing other users' records, admin routes without auth, changing IDs | OWASP A01 Broken Access Control | QA | Y-04 | QA | Test log | Test cases | No | [MUST HAVE] | Medium | 1–2 h | 2 | Data exposure | Only UI-level checks | Breach | Cond | No — included in base price | No
AM-06 | AM | Security | Admin protection | MFA, strong unique passwords, login rate limits, remove default accounts, restrict admin by role | Admin is the highest-value target | Launch | Y-06 or AD-03 | DevOps | Hardening record | Settings screenshots | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Brute force | Default 'admin' usernames | Takeover | Yes | No — included in base price | Yes
AM-07 | AM | Security | File upload security test | Try disallowed types, oversized files, script files, path tricks | Upload abuse prevention | QA | W-08 | QA | Test log | Results | No | [CONDITIONAL] | Low | 0.5–1 h | 1 | Malware hosting | Trusting file extension | Compromise | Cond | No — included in base price | No
AM-08 | AM | Security | Error message and debug review | Debug mode off; no stack traces, versions or paths shown to users | Information leakage (misconfiguration) | Launch | AZ-01 | BE | Review record | Screenshot of error page | No | [MUST HAVE] | Low | 0.5 h | 1 | Leaking internals | Shipping debug mode | Easier attacks | Yes | No — included in base price | No
AM-09 | AM | Security | OWASP Top 10 checklist pass | Walk through OWASP Top 10:2025 categories relevant to the site; record status | Structured coverage of common risks | QA | AM-01..AM-08 | BE/QA | Checklist | Completed checklist | No | [RECOMMENDED] | Medium | 1–2 h | 2 | Box-ticking | Treating as a pen test | Missed risks | Cond | No — included in base price | No
AN-01 | AN | Responsive Design | Breakpoint testing | Test at 320, 360, 390, 414, 768, 1024, 1280, 1440, 1920+ widths | Layout integrity | QA | V-12 | QA | Test record | Screenshots | No | [MUST HAVE] | Low | 1–2 h | 2 | Overflow/horizontal scroll | Testing only 2 widths | Broken layouts | Yes | No — included in base price | No
AN-02 | AN | Responsive Design | Real device testing | Test on at least one mid-range Android (Chrome), one iPhone (Safari), one tablet | Emulators miss real issues | QA | AN-01 | QA | Device test log | Photos/screenshots | No | [MUST HAVE] | Low | 1–2 h | 2 | iOS Safari quirks | Only using DevTools emulation | Client finds bugs on own phone | Yes | No — included in base price | No
AN-03 | AN | Responsive Design | Touch targets and orientation | Targets ≥24px (aim 44px), spacing, landscape orientation, zoom not disabled | Usability and WCAG 2.2 target size | QA | AN-02 | QA | Checklist | Results | No | [MUST HAVE] | Low | 0.5 h | 1 | Mis-taps | Disabling pinch zoom | Frustration | Yes | No — included in base price | No
AO-01 | AO | Cross-browser Testing | Browser support matrix | Define supported browsers/versions in scope (latest 2 versions of Chrome, Edge, Firefox, Safari incl. iOS) | Limits testing scope | Scope | E-06 | PM | Matrix | Scope doc | Yes | [MUST HAVE] | Low | 15 min | 1 | Client expects ancient browser support | Leaving undefined | Endless bug claims | Yes | No — included in base price | No
AO-02 | AO | Cross-browser Testing | Cross-browser testing | Test key pages/flows in each matrix browser | Consistent experience | QA | AO-01 | QA | Test log | Screenshots | No | [MUST HAVE] | Medium | 1–3 h | 2 | Safari-only bugs | Testing only Chrome | Broken for iPhone users | Yes | No — included in base price | No
AO-03 | AO | Cross-browser Testing | Fix browser-specific issues | Resolve CSS/JS compatibility issues found | Consistency | QA | AO-02 | FE | Fixes | Commits | No | [MUST HAVE] | Medium | 1–4 h | 3 | Hacks that break others | Browser sniffing | Inconsistent site | Yes | No — included in base price | No
AP-01 | AP | QA | Tailor QA test plan | Copy master QA checklist, remove non-applicable items, add project-specific flows | Right-sized, complete testing | QA | E-07 | QA | Project QA checklist | Checklist file | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Missed flows | Using generic checklist unchanged | Gaps | Yes | No — included in base price | No
AP-02 | AP | QA | Functional testing | Test every link, button, form, navigation, search/filter, login flows per checklist | Catch defects before client does | QA | AP-01 | QA (not the builder where possible) | Test results | Completed checklist + bug list | No | [MUST HAVE] | Medium | 2–6 h | 5 | Self-testing blind spots | Developer testing own work only | Client finds basic bugs | Yes | No — included in base price | No
AP-03 | AP | QA | Content QA | Spelling, grammar, phone numbers (tap-to-call works), emails, address, prices, hours, social links, legal pages present | Wrong contact info is costly | QA | P-05 | Content/QA | Content QA sheet | Checklist | No | [MUST HAVE] | Low | 1–2 h | 2 | Wrong phone number live | Not checking against client source | Lost business | Yes | No — included in base price | Yes
AP-04 | AP | QA | Regression testing | Re-run key checks after fixes and before launch | Fixes break other things | QA | AQ-02 | QA | Regression record | Checklist | No | [MUST HAVE] | Low | 0.5–2 h | 1 | New bugs from fixes | Only retesting the fixed bug | Launch-day surprises | Yes | No — included in base price | Yes
AP-05 | AP | QA | UAT preparation | Prepare staging, test script and feedback template for client acceptance testing | Structured client testing | Review | AP-02 | PM | UAT pack | Sent pack | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Unstructured feedback | Just sending a link | Chaotic feedback | Yes | No — included in base price | No
AQ-01 | AQ | Bug Fixing | Bug triage | Log each issue with steps, expected/actual, device, severity (blocker/major/minor/cosmetic), classify bug vs change | Prioritises and separates defects from new requests | QA | AP-02 or AR-02 | PM/QA | Triaged bug list | Tracker entries | No | [MUST HAVE] | Low | 5 min/bug | 1 | Change requests disguised as bugs | Fixing without logging | Unpaid scope | Yes | No — included in base price | Yes
AQ-02 | AQ | Bug Fixing | Fix bugs | Resolve bugs by priority with commit references | Quality | QA | AQ-01 | FE/BE | Fixes | Commits linked to bug IDs | No | [MUST HAVE] | Varies | Varies | 1 | Regressions | Unlinked commits | No traceability | Yes | No — included in base price | Yes
AQ-03 | AQ | Bug Fixing | Verify and close bugs | Tester (ideally other partner) verifies on staging; closes with evidence | Independent verification | QA | AQ-02 | QA | Closed bugs | Tracker status + screenshot | No | [MUST HAVE] | Low | 5–10 min/bug | 1 | False closes | Closing own bugs without check | Bugs reappear | Yes | No — included in base price | Yes
AR-01 | AR | Client Review | Staging review walkthrough | Walk client through staging site, how to give feedback, deadline for round | Guided review is faster | Review | AP-05 | PM | Meeting notes | Meeting record | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Client reviews on wrong URL/cache | No deadline | Delays | Yes | No — included in base price | No
AR-02 | AR | Client Review | Collect consolidated client feedback | One list from decision-maker per round with page, issue, screenshot | Controls rounds | Review | AR-01 | PM | Feedback list | Client doc/email | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Drip feedback | Accepting WhatsApp voice notes as feedback | Lost items | Yes | No — included in base price | No
AR-03 | AR | Client Review | Classify feedback | Mark each item: bug (free), in-scope revision (counts toward round), change request (priced) | Fair and transparent | Review | AR-02 | PM | Classified list | Doc sent to client | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Client disagreement | Classifying silently | Scope disputes | Yes | No — included in base price | No
AS-01 | AS | Revisions | Revision round 1 | Implement in-scope revisions from round 1; send summary of changes | Delivers agreed refinements | Review | AR-03 | FE/Design | Updated staging | Change summary + commits | Yes | [MUST HAVE] | Medium | 2–8 h | 6 | Scope sneaks in | Not listing what changed | Repeat requests | Yes | No — included in base price | No
AS-02 | AS | Revisions | Revision round 2 | Final in-scope round | Closure | Review | AS-01 | FE/Design | Updated staging | Change summary | Yes | [RECOMMENDED] | Low | 1–4 h | 3 | Endless rounds | Allowing 'round 2.5' | Unpaid work | Yes | No — included in base price | No
AS-03 | AS | Revisions | Revision count notice | Tell client when included rounds are used and how further changes are billed | Transparency before extra charges | Review | AS-01 | PM | Notice | Sent message | No | [MUST HAVE] | Low | 10 min | 1 | Surprise invoices | Billing without prior notice | Payment disputes | Yes | No — included in base price | No
AT-01 | AT | Scope Changes | Log change request | Record requested change: description, requester, date, reason, priority | Every change needs a record | Any | E-07 | PM | CR entry | CR form | No | [MUST HAVE] | Low | 10–15 min | 1 | Verbal 'small' changes pile up | Just doing it | Unpaid work | Yes | No — included in base price | No
AT-02 | AT | Scope Changes | Change impact assessment | Estimate effort, cost, timeline and risk impact; note dependencies | Informed decision for client | Any | AT-01 | PM/Dev | Impact note | CR form | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Underestimating | Quoting on the spot | Losses | Yes | No — included in base price | No
AT-03 | AT | Scope Changes | Change order approval and invoice | Client approves CR in writing (price, timeline shift); add to invoice schedule | Converts requests into paid work | Any | AT-02 | PM | Approved CR | Signed CR/email | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Doing work before approval | No timeline adjustment | Unpaid work, deadline disputes | Yes | Yes — separate line item | No
AU-01 | AU | Deployment | CI/CD pipeline | Automated build/test/deploy from main branch to staging/prod (host-native or CI) | Repeatable, auditable deploys | Launch | J-04 | DevOps | Pipeline | Pipeline run log | No | [RECOMMENDED] | Medium | 1–3 h | 2 | Secrets in pipeline logs | Manual FTP deploys | Error-prone deploys | Cond | No — included in base price | Yes
AU-02 | AU | Deployment | Production build and environment variables | Set production env vars in host secret store; build with production settings | Correct configuration | Launch | W-02 | DevOps | Prod config | Checklist (names only) | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Staging keys in prod | Pasting secrets into code | Broken or leaked integrations | Yes | No — included in base price | No
AU-03 | AU | Deployment | Deploy to production | Deploy tagged release; record version, time, deployer | Launch step | Launch | AU-02, BA-01 | DevOps | Live deployment | Deploy log + release tag | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Deploying untested build | Deploying Friday night | Outage | Yes | No — included in base price | Yes
AU-04 | AU | Deployment | Rollback plan | Documented and tested way to revert to previous release and restore DB | Recover quickly from bad deploys | Launch | AU-01 | DevOps | Rollback doc | Doc + test note | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Long outage | No previous build retained | Extended downtime | Yes | No — included in base price | Yes
AV-01 | AV | Domain | Domain registration or ownership confirmation | Domain registered by client (their registrar account, client as registrant) or client confirms existing ownership; record expiry date | Whoever controls the domain controls the website | Launch | D-05 | PM | Domain record | WHOIS/registrar screenshot, invoice in client name | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Developer-registered domain disputes | Registering in developer's name 'to save time' | Client loses domain | Yes | No — included in base price | Yes
AV-02 | AV | Domain | Registrar account security | Client enables MFA, registrar lock, auto-renew, valid recovery email/phone | Domain hijack and expiry prevention | Launch | AV-01 | Client + PM | Security checklist | Settings screenshots | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Expiry, hijack | Recovery email is developer's | Site goes offline | Yes | No — included in base price | Yes
AV-03 | AV | Domain | Record renewal dates | Record domain, SSL (if manual), hosting, licence renewals in register and reminders | Renewals are the most forgotten item | Launch | AV-01 | PM | Renewal register | Register | No | [MUST HAVE] | Low | 15–30 min | 1 | Expired domain | Relying on memory | Outage, domain loss | Yes | No — included in base price | Yes
AW-01 | AW | DNS | DNS record inventory and plan | Export current DNS (MX, TXT, SPF, DKIM, verification, subdomains) before changes; plan new records; lower TTL 24–48 h ahead | Avoid breaking email/other services | Launch | AV-01 | DevOps | DNS plan + backup export | Export file | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Deleting MX records | Changing nameservers without copying records | Email outage | Yes | No — included in base price | No
AW-02 | AW | DNS | DNS cutover | Apply records (A/AAAA/CNAME) in client-controlled DNS | Point domain to new site | Launch | AW-01, AU-03 | DevOps | Updated DNS | Before/after lookup output | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Downtime during propagation | Cutover at peak hours | Outage | Yes | No — included in base price | No
AW-03 | AW | DNS | Propagation check and cleanup | Verify from multiple resolvers; restore normal TTL; remove obsolete records | Stable DNS | Launch | AW-02 | DevOps | Clean DNS | Lookup outputs | No | [MUST HAVE] | Low | 0.5 h | 1 | Dangling records (subdomain takeover) | Leaving old CNAMEs to deleted services | Security risk | Yes | No — included in base price | Yes
AX-01 | AX | Hosting | Hosting selection and sizing | Choose host by stack, traffic, region, backups, support, cost, renewal price | Reliability and cost | Development | L-04 | DevOps | Hosting decision | ADR + price note | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Cheap first-year, expensive renewal | Ignoring renewal pricing | Surprise costs | Yes | No — included in base price | No
AX-02 | AX | Hosting | Hosting account in client's name | Client creates account and billing; developer invited as member/collaborator | Client ownership and billing clarity | Launch | AX-01 | Client + PM | Hosting account | Invite email, billing screenshot | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Developer card billed forever | Hosting under agency account | Lock-in disputes | Yes | No — included in base price | Yes
AX-03 | AX | Hosting | Server hardening | For VPS: OS updates, firewall, SSH keys only, no root login, fail2ban/equivalent, automatic security updates | Unmanaged servers get compromised | Launch | AX-01 | DevOps | Hardening checklist | Checklist + config | No | [CONDITIONAL] | High | 3–8 h | 8 | Compromise | Password SSH login | Breach | Cond | Yes — separate line item | Yes
AY-01 | AY | SSL/HTTPS | TLS certificate issuance and auto-renewal | Issue certificate (host-managed or ACME) for apex and www; confirm auto-renew | HTTPS required by browsers and users | Launch | AW-02 | DevOps | Valid certificate | Browser/SSL check | No | [MUST HAVE] | Low | 0.5 h | 1 | Expired certificate | Manual certs without reminders | Browser warnings | Yes | No — included in base price | Yes
AY-02 | AY | SSL/HTTPS | HTTPS and canonical host redirects | 301 HTTP→HTTPS and non-canonical host (www or apex) to canonical; HSTS when stable | Single secure URL | Launch | AY-01 | DevOps | Redirect rules | curl/redirect test output | No | [MUST HAVE] | Low | 0.5 h | 1 | Redirect loops | Mixed www/non-www | Duplicate content | Yes | No — included in base price | No
AY-03 | AY | SSL/HTTPS | Mixed content check | Ensure all assets load over HTTPS | Avoid warnings/blocked assets | Launch | AY-02 | QA | Check result | Console screenshot | No | [MUST HAVE] | Low | 0.25 h | 1 | Broken images/scripts | Hard-coded http:// URLs | Security warnings | Yes | No — included in base price | No
AZ-01 | AZ | Production Environment | Production configuration review | Debug off, correct env, logging level, error pages, timezone, email sender | Misconfiguration is OWASP A02 | Launch | AU-02 | DevOps | Review checklist | Checklist | No | [MUST HAVE] | Low | 0.5 h | 1 | Debug mode live | Copying dev config | Leaks | Yes | No — included in base price | No
AZ-02 | AZ | Production Environment | Storage permissions | Buckets private by default; public only for public assets; signed URLs for private files | Prevents data exposure | Launch | W-08 | DevOps | Storage config | Policy screenshot | No | [CONDITIONAL] | Low | 0.5 h | 1 | Public bucket leaks | Whole bucket public | Data breach | Cond | No — included in base price | Yes
AZ-03 | AZ | Production Environment | Uptime monitoring | Monitor homepage and key endpoint; alerts to client and/or maintainer | Know about outages first | Launch | AU-03 | DevOps | Monitor | Monitor screenshot | No | [RECOMMENDED] | Low | 0.25–0.5 h | 1 | Unnoticed downtime | Alerts only to developer after handover | Long outages | Cond | No — included in base price | Yes
AZ-04 | AZ | Production Environment | Error monitoring | Capture frontend/backend errors with PII scrubbing | Detect bugs in production | Launch | AU-03 | DevOps | Error monitoring | Dashboard screenshot | No | [OPTIONAL] | Low | 0.5–1 h | 1 | Capturing personal data | No scrubbing | Privacy issues | Cond | No — included in base price | Yes
BA-01 | BA | Launch | Run pre-launch checklist | Complete launch checklist (SEO, forms, analytics, legal pages, redirects, backups, robots) | Launch-day errors are public | Launch | AP-04, AS-final | QA/PM | Completed checklist | Checklist file | No | [MUST HAVE] | Low | 1–2 h | 2 | Skipped items | Doing it from memory | Public mistakes | Yes | No — included in base price | No
BA-02 | BA | Launch | Final approval and launch window | Client gives written final approval; agree go-live date/time (avoid Friday evening, festivals) | Approval before public launch | Launch | BA-01 | PM | Final approval + schedule | Signed approval/email | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Launching unapproved | Verbal go-ahead | Disputes | Yes | No — included in base price | No
BA-03 | BA | Launch | Go-live | Execute deploy + DNS cutover per plan; monitor | Launch | Launch | BA-02, AU-03, AW-02 | DevOps | Live website | Timestamped log | No | [MUST HAVE] | Low | 1–2 h | 2 | Downtime | No one monitoring after cutover | Extended outage | Yes | No — included in base price | No
BA-04 | BA | Launch | Staging lockdown | Ensure staging remains password-protected/noindexed or is taken down | Avoid duplicate content and leaks | Launch | BA-03 | DevOps | Staging status | Check result | No | [MUST HAVE] | Low | 0.25 h | 1 | Staging indexed | Forgetting staging | SEO duplicate, leaks | Yes | No — included in base price | No
BA-05 | BA | Launch | Launch announcement support | Draft announcement post/email/WhatsApp status for client | Drives initial traffic | Launch | BA-03 | Content | Draft copy | File | Optional | [OPTIONAL] | Low | 0.5–1 h | 1 | Scope creep into marketing | Doing unpaid social media | Unpaid work | No | Yes — separate line item | No
BB-01 | BB | Post-launch Testing | Production smoke test | Test key pages, navigation, mobile view, HTTPS on live domain | Confirm live site works | Launch | BA-03 | QA | Smoke test record | Checklist + screenshots | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Env-specific failures | Testing only staging | Broken live site | Yes | No — included in base price | Yes
BB-02 | BB | Post-launch Testing | Live forms, emails and payments test | Real submissions and (if applicable) small live payment + refund on production | Integrations often differ in production | Launch | BB-01 | QA | Test record | Received emails, txn IDs | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Silent failure | Assuming staging result applies | Lost leads/orders | Yes | No — included in base price | Yes
BB-03 | BB | Post-launch Testing | Indexing check | Submit sitemap, inspect homepage URL in Search Console, confirm no noindex | Get discovered | Launch | AI-11 | Content | Check record | Screenshot | No | [MUST HAVE] | Low | 0.25–0.5 h | 1 | Site not indexed | Leftover noindex | Invisible site | Yes | No — included in base price | Yes
BB-04 | BB | Post-launch Testing | Post-launch monitoring review | Review errors, uptime, analytics, form deliveries, Search Console coverage over first 7–14 days | Early issue detection | Post-launch | BA-03 | DevOps/QA | Review note | Note + screenshots | No | [RECOMMENDED] | Low | 1–2 h | 2 | Unnoticed issues | No review | Silent failures | Yes | No — included in base price | Yes
BC-01 | BC | Handover | Prepare handover package | Assemble docs, account register, licence register, design files, source code access, backups, maintenance options | Complete, organised transfer | Handover | BD-01..BD-04 | PM | Handover package | Package folder | No | [MUST HAVE] | Medium | 2–4 h | 4 | Missing items | Handing over only a URL | Client dependent on you | Yes | No — included in base price | No
BC-02 | BC | Handover | Handover meeting | Walk through site, accounts, how to get help, what warranty covers, renewals | Shared understanding | Handover | BC-01 | PM | Meeting notes | Meeting record | No | [MUST HAVE] | Low | 1–1.5 h | 2 | Misunderstanding responsibilities | No agenda | Support confusion | Yes | No — included in base price | No
BC-03 | BC | Handover | Handover acknowledgement | Client signs acknowledgement listing items received and access confirmed | Evidence of completed delivery | Handover | BC-02 | PM | Signed acknowledgement | Signed form | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Later claims of non-delivery | No signed record | Disputes | Yes | No — included in base price | No
BD-01 | BD | Documentation | Technical README | Setup, build, deploy steps, env var names (not values), architecture, dependencies, known issues | Maintainability by anyone | Handover | V-01 | FE/BE | README | Repo file | No | [MUST HAVE] | Medium | 1–3 h | 2 | Secrets in docs | Writing it at the last minute | Lock-in | Yes | No — included in base price | Yes
BD-02 | BD | Documentation | Client user guide | How to edit content, add images, manage forms/leads, common tasks with screenshots | Client independence | Handover | AD-04 | Content | User guide | File | No | [RECOMMENDED] | Low | 1–3 h | 2 | Outdated guide | Too technical | Constant support calls | Yes | No — included in base price | No
BD-03 | BD | Documentation | Account and asset register | Every account/service: owner, URL, purpose, who has access, renewal date, cost, where credentials are stored (not the credentials) | Master ownership record | Handover | D-05 | PM | Register | Register file | Yes | [MUST HAVE] | Low | 1–2 h | 2 | Missing services | Including passwords in the register | Lost control | Yes | No — included in base price | Yes
BD-04 | BD | Documentation | Third-party licence register | List fonts, images, icons, themes, plugins, libraries with licence type, licensee, proof, renewal | Licence compliance and transfer | Handover | O-04, AD-05, V-03 | PM | Licence register | Register + licence files | No | [MUST HAVE] | Low | 1–2 h | 2 | Licence in developer's name | Not recording licensee | Infringement | Yes | No — included in base price | Yes
BE-01 | BE | Training | CMS/admin training session | Live training on content edits and admin tasks; record with consent | Client self-sufficiency | Handover | BD-02 | Content/FE | Recording + notes | Recording link | No | [RECOMMENDED] | Low | 1–2 h | 2 | Forgotten training | No recording | Support load | Cond | No — included in base price | No
BE-02 | BE | Training | Training follow-up | Answer follow-up questions within agreed window | Adoption | Handover | BE-01 | Either | Q&A log | Messages | No | [OPTIONAL] | Low | 0.5–1 h | 1 | Endless free training | No window defined | Unpaid support | Cond | No — included in base price | No
BF-01 | BF | Final Payment | Final invoice | Invoice remaining balance plus approved change orders, less advance | Close finances | Handover | BA-02 | PM | Final invoice | Invoice file | No | [MUST HAVE] | Low | 15–30 min | 1 | Missed change orders | Forgetting CRs | Revenue loss | Yes | No — included in base price | No
BF-02 | BF | Final Payment | Final payment confirmation | Confirm bank credit, issue receipt, update ledger | Trigger for ownership transfer | Handover | BF-01 | PM | Receipt | Bank ref + receipt | No | [MUST HAVE] | Low | 15 min | 1 | Transferring before payment | Accepting screenshots | Unpaid project | Yes | No — included in base price | No
BF-03 | BF | Final Payment | Collect TDS certificate | Request TDS certificate for amounts deducted; reconcile with AIS/26AS | Claim tax credit | Closure | I-04 | PM | Certificate | File | No | [CONDITIONAL] | Low | 15 min | 1 | Lost credit | Not following up | Tax loss | Cond | No — included in base price | No
BG-01 | BG | Ownership Transfer | Domain control confirmation | Confirm client is registrant and sole account holder; developer removed from registrar; if transfer needed, initiate with auth code (TAC/EPP) securely | Domain = control of website | Ownership | BF-02 | PM + Client | Confirmation | WHOIS/RDAP + registrar screenshots | Yes | [MUST HAVE] | Low | 0.5–2 h | 1 | Transfer locks delay | Sending auth code over chat | Client can't control site | Yes | No — included in base price | No
BG-02 | BG | Ownership Transfer | Hosting/cloud ownership transfer | Transfer project/team ownership or confirm client-owned account; downgrade/remove developer access | Control of runtime and billing | Ownership | BF-02 | DevOps + Client | Transferred account | Owner screenshot | Yes | [MUST HAVE] | Low | 0.5–2 h | 1 | Billing still on developer card | Forgetting billing transfer | Lock-in | Yes | No — included in base price | No
BG-03 | BG | Ownership Transfer | Repository transfer | Transfer repo to client org/account or deliver full archive; confirm client admin; remove developer collaborator if not maintaining | Client owns source code | Ownership | BF-02, BD-01 | FE/BE | Transferred repo | Repo settings screenshot | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Developer auto-retained as collaborator | Assuming transfer removes access | Unintended developer access | Yes | No — included in base price | No
BG-04 | BG | Ownership Transfer | Analytics and Search Console ownership | Confirm client is GA Administrator and verified Search Console owner; remove developer tokens/access or downgrade | Data control | Ownership | BF-02 | DevOps | Ownership confirmation | Access screenshots | Yes | [MUST HAVE] | Low | 0.5 h | 1 | Developer tokens left re-verify access | Removing user but not verification token | Lingering access | Yes | No — included in base price | No
BG-05 | BG | Ownership Transfer | Third-party accounts transfer | For each service in register: confirm client owner, billing, API key ownership; transfer anything created by developer | Complete independence | Ownership | BD-03 | PM | Updated register | Register with 'transferred' status | Yes | [MUST HAVE] | Medium | 1–3 h | 2 | Forgotten service | Ignoring 'small' services (SMTP, maps) | Outages later | Yes | No — included in base price | No
BG-06 | BG | Ownership Transfer | Credential rotation | Rotate all passwords/keys the developer knew: admin, DB, SMTP, API keys, webhooks secrets; update env vars; test | Removes residual developer knowledge | Ownership | BG-01..BG-05 | DevOps + Client | Rotation checklist | Checklist with dates (no secrets) | Yes | [MUST HAVE] | Medium | 1–3 h | 2 | Breaking integrations | Rotating without updating env vars | Outage | Yes | No — included in base price | No
BG-07 | BG | Ownership Transfer | Developer access removal or downgrade | Remove or reduce developer access per maintenance agreement; document what remains and why | Least privilege | Ownership | BG-06 | PM | Access record | Access list screenshots | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Unintended access | Forgetting CMS/hosting users | Liability | Yes | No — included in base price | No
BG-08 | BG | Ownership Transfer | Execute copyright assignment/licence | Sign assignment for commissioned deliverables (specifying work, rights, duration, territory, consideration) and licence for pre-existing/reusable components | Indian law requires written signed assignment | Ownership | BF-02 | PM | Signed assignment | Signed document | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Defaults (5 years/India only) apply if silent | Relying on invoice or chat | Ownership dispute | Yes | No — included in base price | No
BG-09 | BG | Ownership Transfer | Ownership transfer confirmation | Client signs checklist confirming each item transferred and tested | Closes ownership questions | Ownership | BG-01..BG-08 | PM | Signed confirmation | Signed form | Yes | [MUST HAVE] | Low | 15–30 min | 1 | Later disputes | No evidence | Disputes | Yes | No — included in base price | No
BH-01 | BH | Maintenance | Maintenance agreement proposal | Offer AMC tiers: updates, backups, monitoring, content edit hours, response times, exclusions, price; separate contract | Maintenance is recurring revenue and clarifies post-launch duties | Handover | BC-02 | PM | AMC proposal/agreement | Signed AMC or declined note | Yes | [RECOMMENDED] | Low | 1–2 h | 2 | Implied free lifetime support | No written AMC | Unpaid support forever | Yes | Yes — separate line item | Yes
BH-02 | BH | Maintenance | Monthly updates | Update dependencies/CMS/plugins on staging, test, deploy | Unpatched sites get hacked | Maintenance | BH-01 | FE/BE | Update log | Changelog + commits | No | [POST-LAUNCH] | Medium | 1–3 h/month | 2 | Update breaks site | Updating directly in production | Outage or compromise | No | Yes — separate line item | Yes
BH-03 | BH | Maintenance | Backup verification | Confirm backups ran; quarterly test restore | Backups fail silently | Maintenance | X-07 | DevOps | Backup log | Screenshot/log | No | [POST-LAUNCH] | Low | 0.5 h/month | 1 | Unrecoverable data | Never testing restores | Data loss | No | Yes — separate line item | Yes
BH-04 | BH | Maintenance | Monitoring review | Review uptime, errors, security alerts, form delivery | Early detection | Maintenance | AZ-03 | DevOps | Monthly note | Report | No | [POST-LAUNCH] | Low | 0.5–1 h/month | 1 | Unnoticed failures | Alerts to nobody | Outages | No | Yes — separate line item | Yes
BH-05 | BH | Maintenance | Renewal reminders | Remind client 30/14/7 days before domain, hosting, licence renewals | Prevents expiry | Maintenance | AV-03 | PM | Reminder log | Messages | No | [POST-LAUNCH] | Low | 10 min/month | 1 | Expired domain | Relying on registrar emails to old addresses | Outage | Yes | No — included in base price | Yes
BH-06 | BH | Maintenance | Monthly maintenance report | Summary: updates, uptime, backups, issues, hours used, recommendations | Demonstrates value; supports renewal | Maintenance | BH-02..BH-04 | PM | Report | Sent report | No | [POST-LAUNCH] | Low | 0.5–1 h/month | 1 | Client doubts value | No reporting | AMC cancellation | No | Yes — separate line item | Yes
BI-01 | BI | Support | Warranty/defect period support | Fix defects reported within warranty window (e.g., 30 days) that are genuine bugs in delivered work | Professional standard; contractual | Post-launch | BA-03 | FE/BE | Fix log | Tickets + commits | No | [MUST HAVE] | Varies | Varies | 1 | Warranty used for new features | Undefined warranty scope | Unpaid work | Yes | No — included in base price | Yes
BI-02 | BI | Support | Support ticket handling | Log requests, classify (defect/AMC/billable), respond within agreed times | Organised support | Post-launch | BH-01 | Either | Ticket log | Tickets | No | [POST-LAUNCH] | Low | Varies | 1 | Chaotic WhatsApp support | No classification | Unpaid work | No | Conditional — depends on scope | Yes
BI-03 | BI | Support | Small content edits | Content edits within AMC hours; beyond that billed | Common request | Post-launch | BH-01 | Content | Edit log | Tickets | No | [POST-LAUNCH] | Low | 0.25–1 h each | 1 | Hours creep | Not logging time | Unpaid work | No | Conditional — depends on scope | Yes
BJ-01 | BJ | Project Closure | Project retrospective | Partners review estimate vs actual, what went well/badly, update templates and default points | Continuous improvement | Closure | BG-09 | Either (both) | Retro notes | Notes | No | [RECOMMENDED] | Low | 1 h | 1 | Repeating mistakes | Skipping when busy | Same losses repeat | Yes | No — included in base price | No
BJ-02 | BJ | Project Closure | Final contribution calculation and sign-off | Freeze tasks/points, resolve open disputes, both partners approve contribution percentages | Fair split; prevents post-project manipulation | Closure | BJ-01 | Either (both) | Contribution statement | App lock + both approvals | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Disputes | Editing points after payment | Partnership conflict | Yes | No — included in base price | No
BJ-03 | BJ | Project Closure | Profit distribution record | Calculate net profit (revenue − expenses − reserves − taxes set aside), distribute per statement, record payments | Transparent money flow | Closure | BJ-02, BF-02 | PM | Distribution record | Bank refs | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Tax mistakes | Distributing gross receipts | Cash shortfall | Yes | No — included in base price | No
BJ-04 | BJ | Project Closure | Archive project records | Archive contract, approvals, invoices, CRs, handover docs, evidence per retention policy | Legal/tax retention and dispute defence | Closure | BJ-03 | PM | Archive | Archive location record | No | [MUST HAVE] | Low | 0.5–1 h | 1 | Evidence lost | Keeping only in chats | No defence in disputes | Yes | No — included in base price | No
BJ-05 | BJ | Project Closure | Testimonial and portfolio permission | Request testimonial/review and written permission to show the work | Marketing; portfolio rights clarity | Closure | BG-09 | Sales | Testimonial + permission | Email/message | Optional | [RECOMMENDED] | Low | 15–30 min | 1 | Using work without permission | Assuming right to showcase | Client objection | Yes | No — included in base price | No
BJ-06 | BJ | Project Closure | Close project and revoke internal access | Close tasks, archive board, remove temporary accounts/vault items no longer needed | Security and tidiness | Closure | BJ-04 | PM | Closed project | App status | No | [MUST HAVE] | Low | 0.5 h | 1 | Stale credentials | Leaving vault items forever | Security risk | Yes | No — included in base price | No
BK-01 | BK | Legal & Compliance Pages (added) | Privacy notice (client-owned) | Obtain privacy notice from client (ideally lawyer-reviewed) covering what forms/analytics collect, purposes, contact; publish and link | Personal data is collected via forms/analytics; DPDP notice obligations fully apply from May 2027 | Content | AB-01 | Client + PM | Published notice | Page URL + client approval | Yes | [MUST HAVE] | Low | 0.5–1 h (dev) | 1 | Developer-authored legal text treated as advice | Copying another company's policy | Non-compliance | Yes | No — included in base price | Yes
BK-02 | BK | Legal & Compliance Pages (added) | Terms of use (client-owned) | Publish client-provided website terms | Sets rules for site use | Content | P-05 | Client + PM | Published terms | Page URL | Yes | [RECOMMENDED] | Low | 0.5 h (dev) | 1 | Inaccurate terms | Generic templates | Weak protection | Cond | No — included in base price | No
BK-03 | BK | Legal & Compliance Pages (added) | Cookie/tracker notice | Explain cookies/trackers used; link from consent banner | Transparency | Content | V-23 | Client + PM | Notice section | Page URL | Yes | [CONDITIONAL] | Low | 0.5 h | 1 | Undisclosed trackers | Listing trackers not used or omitting used ones | Complaints | Cond | No — included in base price | Yes
BK-04 | BK | Legal & Compliance Pages (added) | Refund, cancellation and shipping policies | Publish client-provided policies for e-commerce/paid bookings; link at checkout | E-commerce rules require clear return/refund/delivery info; gateways also require them | Content | AF-01 or AG-01 | Client + PM | Policy pages | URLs | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Gateway activation blocked | Missing policies | Non-compliance | Cond | No — included in base price | Yes
BK-05 | BK | Legal & Compliance Pages (added) | Contact and grievance details | Display business legal name, address, contact channels; grievance officer where required | Trust; required for e-commerce entities | Content | P-05 | Client + PM | Contact details | Screenshot | Yes | [MUST HAVE] | Low | 0.25 h | 1 | Wrong details | Personal numbers of staff | Complaints | Yes | No — included in base price | Yes
BL-01 | BL | Backup & Recovery (added) | Backup policy and schedule | Define what (files, DB, CMS uploads), how often, retention, where (separate account/region), who restores | Recovery planning | Launch | X-07 | DevOps | Backup policy | Doc | Yes | [MUST HAVE] | Low | 0.5–1 h | 1 | Backups on same server | Only host snapshots | Data loss | Yes | No — included in base price | Yes
BL-02 | BL | Backup & Recovery (added) | Off-site/second copy | Keep a copy outside the primary host, owned by client | Host failure/account lockout | Launch | BL-01 | DevOps | Off-site backup | Log | No | [RECOMMENDED] | Low | 0.5–1 h | 1 | Copy in developer's personal drive | Storing client data personally | Privacy/ownership issues | Cond | Conditional — depends on scope | Yes
BL-03 | BL | Backup & Recovery (added) | Restore drill | Restore to a test environment and verify site works | Proves recoverability | Launch | BL-01 | DevOps | Drill report | Report | No | [RECOMMENDED] | Medium | 1–2 h | 2 | Untestable backups | Never tested | Unrecoverable | Cond | No — included in base price | Yes
BM-01 | BM | Localisation (added) | Language strategy | Decide languages, URL structure (subfolders), language switcher, hreflang, who translates | Multilingual SEO and UX | Requirements | E-03 | PM | Strategy | Doc | Yes | [CONDITIONAL] | Low | 0.5–1 h | 1 | Auto-translate widgets | Mixed-language pages | Poor UX/SEO | Cond | Yes — separate line item | No
BM-02 | BM | Localisation (added) | Implement internationalisation | Translation files/CMS fields, hreflang, lang attributes, Indic font support | Correct rendering of Indian scripts | Development | BM-01 | FE | i18n implementation | Commits | No | [CONDITIONAL] | Medium | 3–8 h | 7 | Broken Indic rendering | Missing lang attribute | Accessibility/SEO issues | Cond | Yes — separate line item | Yes
BM-03 | BM | Localisation (added) | Translation QA | Native speaker reviews rendered pages | Quality | QA | BM-02 | Content | QA notes | Checklist | Yes | [CONDITIONAL] | Low | 1–2 h | 2 | Embarrassing errors | Reviewing text only, not rendered | Poor brand image | Cond | Yes — separate line item | No
BN-01 | BN | Internal Finance & Tax Admin (added) | Project P&L sheet | Track revenue, GST collected (if registered), TDS, expenses, reserves, net profit | Basis for profit split and taxes | Throughout | I-01 | PM | P&L | Sheet | No | [MUST HAVE] | Low | 0.5 h/month | 1 | Distributing tax money | Mixing personal and business accounts | Tax trouble, disputes | Yes | No — included in base price | No
BN-02 | BN | Internal Finance & Tax Admin (added) | Tax records and CA handoff | Provide invoices, expenses, TDS data to CA for GST returns/income tax as applicable | Compliance | Throughout | I-01..I-06 | PM | CA pack | Sent pack | No | [CONDITIONAL] | Low | 0.5–1 h/month | 1 | Late filing penalties | Last-minute scramble | Penalties | Yes | No — included in base price | No
BN-03 | BN | Internal Finance & Tax Admin (added) | Partner expense reimbursement | Reimburse partner-paid business expenses against bills before profit split | Fairness | Closure | I-06 | PM | Reimbursement record | Bank refs | No | [MUST HAVE] | Low | 15 min | 1 | Double counting | Counting expense as both reimbursement and contribution | Disputes | Yes | No — included in base price | No
BO-01 | BO | Partner Governance (added) | Contribution dispute review | Structured review of disputed task claims using evidence; decide per dispute rules | Keeps partnership healthy | Closure | BJ-02 | Either (both) | Dispute decision | Dispute record | No | [CONDITIONAL] | Low | 0.5–2 h | 1 | Resentment | Debating without evidence | Partnership breakdown | Cond | No — included in base price | No
BO-02 | BO | Partner Governance (added) | Points calibration review | Quarterly compare points vs actual effort across projects; adjust defaults going forward only | Keeps defaults realistic | Business-level, quarterly | BJ-01 | Either (both) | Updated defaults | Changelog of defaults | No | [RECOMMENDED] | Low | 1–2 h | 1 | Retroactive changes | Changing past projects | Distrust | No | No — included in base price | No

## Contribution Library
ID | Category | Task | Description | Default Points | Complexity | Estimated Effort | Evidence | Client Approval | Mandatory/Optional/Conditional | Typical Owner | Dependencies | Billable? | Post-launch?
A-01 | Lead Generation | Build prospect list | List local businesses in a target niche/area with no site, an outdated site, or a site that fails mobile/speed checks; record name, contact, source, current URL | 2 | Low | 1–3 h per 20 leads | CRM/sheet export with dates | No | [RECOMMENDED] | Sales | — | No — included in base price | No
A-02 | Lead Generation | Prospect mini-audit | Quick audit of prospect's site, Google Business Profile, socials: mobile view, speed, HTTPS, broken contact info; 3–5 concrete findings | 1 | Low | 0.5–1 h | Audit doc/screenshots linked to lead | No | [OPTIONAL] | Sales | A-01 | No — included in base price | No
A-03 | Lead Generation | Log lead with source and status | Create lead record: business, contact person, phone/email, source, date, next action, status | 1 | Low | 5–10 min | CRM/app entry with timestamp | No | [MUST HAVE] | Either | — | No — included in base price | No
A-04 | Lead Generation | Referral and partner outreach | Ask past clients, CAs, printers, photographers, marketers for referrals; track referrer | 2 | Low | 1–2 h/month | Messages/call notes | No | [RECOMMENDED] | Sales | — | No — included in base price | No
B-01 | Client Outreach | Write personalised outreach message | Draft first message referencing audit findings and a clear next step (15-min call) | 1 | Low | 15–30 min | Sent message copy/screenshot | No | [RECOMMENDED] | Sales | A-02, A-03 | No — included in base price | No
B-02 | Client Outreach | First contact and log outcome | Call/visit/message; record date, channel, who, outcome, next step | 1 | Low | 10–30 min | Call log/meeting note | No | [MUST HAVE] | Sales | B-01 | No — included in base price | No
B-03 | Client Outreach | Follow-up sequence | Up to 2–3 spaced follow-ups with added value (example, audit point); stop after no response | 1 | Low | 10 min each | Message copies with dates | No | [RECOMMENDED] | Sales | B-02 | No — included in base price | No
B-04 | Client Outreach | Share portfolio and case studies | Send 2–3 relevant samples with outcome, scope and price band | 1 | Low | 15–30 min | Sent link record | No | [RECOMMENDED] | Sales | B-02 | No — included in base price | No
C-01 | Sales | Qualification call | 15–30 min call covering need, decision-maker, budget range, timeline, existing assets | 1 | Low | 0.5–1 h | Call note in app | No | [MUST HAVE] | Sales | B-02 | No — included in base price | No
C-02 | Sales | Go/no-go decision | Decide proceed or decline using checklist: budget fit, timeline realism, legal business, red flags; record reason | 1 | Low | 10–20 min | Decision entry with reason | No | [RECOMMENDED] | Either | C-01 | No — included in base price | No
C-03 | Sales | Sales meeting or demo | Present approach, process, timeline, samples; explain payment terms and ownership model upfront | 2 | Medium | 1–2 h incl. prep | Meeting record + attendee list | No | [RECOMMENDED] | Sales | C-02 | No — included in base price | No
C-04 | Sales | Pricing negotiation | Negotiate by adjusting scope, not just price; record every concession in writing | 2 | Medium | 0.5–2 h | Email/notes, version history | Yes | [RECOMMENDED] | Sales | G-03 | No — included in base price | No
C-05 | Sales | Client risk check | Check GSTIN (if B2B), business legitimacy, prohibited content/activities, previous vendor disputes | 1 | Low | 15–30 min | Checklist entry | No | [RECOMMENDED] | Either | C-01 | No — included in base price | No
D-01 | Discovery | Send discovery questionnaire | Send structured questionnaire (see Part 5) via form/doc with deadline | 1 | Low | 15 min to send | Response file/link | No | [MUST HAVE] | PM | C-02 | No — included in base price | No
D-02 | Discovery | Discovery meeting | 60–90 min structured meeting walking through goals, pages, features, content, accounts, timeline, budget | 3 | Medium | 1.5–3 h incl. prep | Meeting record, attendees | No | [MUST HAVE] | PM | D-01 | No — included in base price | No
D-03 | Discovery | Discovery summary to client | Send written summary of what was understood, open questions, and next steps within 24–48 h | 1 | Low | 0.5–1 h | Sent email | Yes | [MUST HAVE] | PM | D-02 | No — included in base price | No
D-04 | Discovery | Identify decision-maker and single point of contact | Record who approves design, content, payments; one SPOC for feedback | 1 | Low | 10–15 min | Entry in project record | Yes | [MUST HAVE] | PM | D-02 | No — included in base price | No
D-05 | Discovery | Existing assets and accounts audit | Identify current domain registrar and registrant, hosting, email provider, DNS host, analytics, GBP, socials, and who holds logins | 2 | Medium | 1–2 h | Register doc | No | [MUST HAVE] | PM | D-02 | No — included in base price | No
E-01 | Requirements Gathering | Define goals and success metrics | Agree 2–4 measurable goals (e.g., enquiries/month, calls, bookings) and how they will be measured | 1 | Low | 0.5–1 h | Approved brief | Yes | [RECOMMENDED] | PM | D-03 | No — included in base price | No
E-02 | Requirements Gathering | Draft sitemap and page list | List every page with purpose and priority; mark template vs unique pages | 2 | Low | 1–2 h | Sitemap file/diagram | Yes | [MUST HAVE] | PM | D-03 | No — included in base price | No
E-03 | Requirements Gathering | Feature list with priorities | List features (forms, booking, blog, gallery, payments, languages) marked Must/Should/Could/Won't | 2 | Medium | 1–2 h | Requirements doc | Yes | [MUST HAVE] | PM | D-03 | No — included in base price | No
E-04 | Requirements Gathering | Content responsibility matrix | For every page/section: who writes text, supplies images, approves, and by when | 1 | Low | 0.5–1 h | Matrix doc | Yes | [MUST HAVE] | PM | E-02 | No — included in base price | No
E-05 | Requirements Gathering | Integration and third-party inventory | List every external service (maps, payments, booking, CRM, email), who creates the account, costs, and API limits | 2 | Medium | 1–2 h | Register doc | Yes | [MUST HAVE] | PM | E-03 | No — included in base price | No
E-06 | Requirements Gathering | Non-functional requirements | Agree supported browsers/devices, accessibility target, performance targets, languages, hosting region, uptime expectations | 1 | Medium | 0.5–1 h | Requirements doc | Yes | [MUST HAVE] | PM | E-03 | No — included in base price | No
E-07 | Requirements Gathering | Requirements sign-off | Client confirms requirements document in writing (e-sign or email 'approved') | 1 | Low | 15–30 min | Signed doc/email | Yes | [MUST HAVE] | PM | E-01, E-02, E-03, E-04, E-05, E-06 | No — included in base price | No
F-01 | Scope Definition | Write inclusions list | Enumerate exactly what is delivered: pages, templates, features, integrations, content work, rounds, training, warranty days | 2 | Medium | 1–2 h | Scope doc | Yes | [MUST HAVE] | PM | E-07 | No — included in base price | No
F-02 | Scope Definition | Write exclusions and assumptions | List what is NOT included (copywriting, logo, photos, paid ads, content entry beyond X pages, third-party fees) and assumptions (content supplied by date, one SPOC) | 1 | Low | 0.5–1 h | Scope doc | Yes | [MUST HAVE] | PM | F-01 | No — included in base price | No
F-03 | Scope Definition | Define revision rounds | Specify number of rounds per stage, what a round is (one consolidated list), and what counts as a change request | 1 | Low | 15–30 min | Scope doc | Yes | [MUST HAVE] | PM | F-01 | No — included in base price | No
F-04 | Scope Definition | Define client responsibilities and feedback SLAs | Client duties: content, approvals within N working days, account creation, payments; effect of delay on timeline | 1 | Low | 15–30 min | Scope doc | Yes | [MUST HAVE] | PM | F-01 | No — included in base price | No
F-05 | Scope Definition | Define milestones and acceptance criteria | Milestones (design, build, UAT, launch) with measurable acceptance tests and deemed-acceptance rule | 1 | Medium | 0.5–1 h | Scope doc | Yes | [MUST HAVE] | PM | F-01 | No — included in base price | No
G-01 | Proposal/Quotation | Bottom-up effort estimate | Estimate each task from the task library with low/high range, add risk buffer (10–25%) | 3 | Medium | 1–3 h | Sheet with version | No | [MUST HAVE] | PM | F-01, F-02, F-03, F-04, F-05 | No — included in base price | No
G-02 | Proposal/Quotation | Price calculation | Convert effort to price; add third-party costs (pass-through or client-paid), GST if registered, contingency; set payment split | 1 | Medium | 0.5–1 h | Sheet | No | [MUST HAVE] | PM | G-01 | No — included in base price | No
G-03 | Proposal/Quotation | Prepare proposal | Proposal with problem, solution, scope summary, timeline, price, payment schedule, ownership model, validity date | 4 | Medium | 2–4 h | Versioned file | Yes | [MUST HAVE] | PM | G-02 | No — included in base price | No
G-04 | Proposal/Quotation | Formal quotation | Itemised quotation with GSTIN/SAC and tax lines if registered, validity, terms reference | 1 | Low | 0.5 h | Quote number and file | Yes | [RECOMMENDED] | PM | G-02 | No — included in base price | No
G-05 | Proposal/Quotation | Proposal walkthrough | Walk client through proposal; answer questions; log objections | 1 | Low | 0.5–1 h | Meeting record | No | [RECOMMENDED] | Sales | G-03 | No — included in base price | No
G-06 | Proposal/Quotation | Revise proposal | Update scope/price after negotiation; increment version; mark superseded | 1 | Low | 0.5–2 h | Version history | Yes | [CONDITIONAL] | PM | C-04 | No — included in base price | No
H-01 | Contract/Agreement | Adapt contract template | Start from lawyer-reviewed master services agreement; select project schedule; do not edit core clauses ad hoc | 2 | Medium | 1–2 h | Draft file | No | [MUST HAVE] | PM | G-03 | No — included in base price | No
H-02 | Contract/Agreement | Fill statement of work schedule | Attach scope, milestones, payment schedule, revision policy, timeline, client duties as a schedule to the contract | 1 | Low | 0.5–1 h | Contract annex | Yes | [MUST HAVE] | PM | H-01, F-01, F-02, F-03, F-04, F-05 | No — included in base price | No
H-03 | Contract/Agreement | IP, ownership and licence check | Confirm clause: what is assigned (in writing, with duration/territory), what is licensed (pre-existing code, libraries, templates), third-party licences, portfolio rights | 1 | Medium | 0.5–1 h | Checklist entry | Yes | [MUST HAVE] | PM | H-01 | No — included in base price | No
H-04 | Contract/Agreement | Confidentiality and data-processing terms | Add confidentiality; if you will access/process personal data (form leads, customers), add processor-style terms: purpose, security, deletion, breach notice | 1 | Medium | 0.5–1 h | Contract clause | Yes | [CONDITIONAL] | PM | H-01 | No — included in base price | No
H-05 | Contract/Agreement | Execute contract | Both parties sign (e-sign/wet); store final PDF; record date, version, signatories and authority | 1 | Low | 15–30 min | Signed PDF + audit trail | Yes | [MUST HAVE] | PM | H-02, H-03, H-04 | No — included in base price | No
H-06 | Contract/Agreement | Stamp duty check | Check applicable state stamp duty for the agreement type/value; pay via e-stamp if required | 1 | Low | 15–60 min | Certificate file | No | [CONDITIONAL] | PM | H-05 | No — included in base price | No
I-01 | Payment/Invoice | Raise advance invoice | Issue invoice for advance (e.g., 30–50%) with correct GST details if registered | 1 | Low | 15–30 min | Invoice number/file | No | [MUST HAVE] | PM | H-05 | No — included in base price | No
I-02 | Payment/Invoice | Confirm advance receipt | Match bank credit to invoice; issue receipt/acknowledgement; record TDS if deducted | 1 | Low | 10–15 min | Bank reference, receipt file | No | [MUST HAVE] | PM | I-01 | No — included in base price | No
I-03 | Payment/Invoice | Milestone invoices | Invoice each milestone on acceptance or deemed acceptance | 1 | Low | 15 min each | Invoice files | No | [MUST HAVE] | PM | F-05 | No — included in base price | No
I-04 | Payment/Invoice | TDS tracking and reconciliation | Record TDS deducted by client, check it appears in Form 26AS/AIS, request TDS certificate | 1 | Low | 15 min/invoice | Register + certificates | No | [CONDITIONAL] | PM | I-02 | No — included in base price | No
I-05 | Payment/Invoice | Payment follow-up | Polite reminders at due date, +7, +14 days; escalate per contract; log each | 1 | Low | 10–20 min each | Messages/emails | No | [MUST HAVE] | PM | I-03 | No — included in base price | No
I-06 | Payment/Invoice | Record project expenses | Record every third-party purchase (theme, plugin, stock image, domain) with bill, payer, reimbursable flag | 1 | Low | 5 min each | Bills/receipts | No | [MUST HAVE] | Either | — | Conditional — depends on scope | No
J-01 | Project Setup | Create project record and folder structure | Create project in tracking app and shared drive with standard folders (01-Contract, 02-Brief, 03-Content, 04-Design, 05-Dev, 06-QA, 07-Launch, 08-Handover, 09-Finance) | 1 | Low | 15–30 min | Folder link, app record | No | [MUST HAVE] | PM | H-05, I-02 | No — included in base price | No
J-02 | Project Setup | Create task board and milestones | Import default tasks from library, delete irrelevant ones, set owners, due dates, milestones | 1 | Low | 0.5–1 h | Board snapshot | No | [MUST HAVE] | PM | J-01 | No — included in base price | No
J-03 | Project Setup | Set up client communication channel and rules | Choose official channels (email for decisions, WhatsApp group for quick coordination), response times, working hours, SPOC | 1 | Low | 15–30 min | Kickoff note | Yes | [MUST HAVE] | PM | J-01 | No — included in base price | No
J-04 | Project Setup | Create repository | Create repo (ideally in a business-owned organization or client-owned org), branch protection, README stub, .gitignore excluding secrets | 1 | Low | 15–30 min | Repo URL, first commit | No | [MUST HAVE] | FE/BE | J-01 | No — included in base price | No
J-05 | Project Setup | Set up dev and staging environments | Local dev setup, password-protected or noindex staging URL for client review | 3 | Medium | 1–3 h | URL + access note | No | [MUST HAVE] | DevOps | J-04 | No — included in base price | No
J-06 | Project Setup | Project credential vault | Create shared vault (password manager) for project credentials with item naming convention | 1 | Low | 15–30 min | Vault entry list (names only) | No | [MUST HAVE] | PM | J-01 | No — included in base price | No
J-07 | Project Setup | Kickoff meeting | Walk through plan, timeline, responsibilities, content deadlines, communication rules, next steps; send notes | 2 | Low | 1–1.5 h incl. notes | Meeting record + sent notes | No | [MUST HAVE] | PM | J-02, J-03 | No — included in base price | No
J-08 | Project Setup | Internal task assignment and point pre-estimate | Partners agree owners and default points for each task before work starts; lock the plan | 1 | Low | 0.5–1 h | App lock record with both confirmations | No | [MUST HAVE] | Either (both confirm) | J-02 | No — included in base price | No
K-01 | Client Communication | Weekly progress update | Short written update: done, next, blockers, decisions needed, client actions pending | 1 | Low | 15–30 min/week | Sent email/message | No | [RECOMMENDED] | PM | J-07 | No — included in base price | No
K-02 | Client Communication | Meeting scheduling and agenda | Send invite with agenda, goal, attendees, materials | 1 | Low | 10 min | Calendar invite | No | [RECOMMENDED] | PM | — | No — included in base price | No
K-03 | Client Communication | Meeting notes and action items | Notes within 24 h: decisions, actions with owner and due date, open questions; client asked to correct | 1 | Low | 15–30 min | Sent notes | No | [MUST HAVE] | PM | — | No — included in base price | No
K-04 | Client Communication | Decision log | Maintain log of decisions: date, decision, who approved, source link | 1 | Low | 5 min/entry | Log entries | No | [RECOMMENDED] | PM | J-01 | No — included in base price | No
K-05 | Client Communication | Escalation handling | Handle serious issues (delays, payment, conflict) by call plus written summary with options | 2 | Medium | 1–3 h | Note + client response | Optional | [CONDITIONAL] | PM | — | No — included in base price | No
L-01 | Research | Industry and business research | Understand client's services, customer questions, regulatory/professional display norms to confirm with client | 2 | Low | 1–3 h | Notes doc with URLs | No | [RECOMMENDED] | Content/PM | D-03 | No — included in base price | No
L-02 | Research | Audience and user needs | Define 2–3 audience types, their key questions, devices, languages | 2 | Low | 1–2 h | Doc | No | [RECOMMENDED] | Design/Content | D-03 | No — included in base price | No
L-03 | Research | Keyword and local search research | Find search terms (service + locality), questions, and competitor terms; map to pages | 4 | Medium | 2–4 h | Sheet | No | [RECOMMENDED] | Content | E-02 | Conditional — depends on scope | No
L-04 | Research | Technical approach decision record | Decide stack (static, CMS, framework, hosting) with reasons: client skills, budget, maintenance, hosting costs | 2 | Medium | 1–2 h | ADR doc | No | [MUST HAVE] | FE/BE | E-03, E-06 | No — included in base price | No
L-05 | Research | Legal content needs check | List legal pages/disclosures the client must provide (privacy notice, terms, refund policy for e-commerce, grievance contact) and flag for client's lawyer | 1 | Low | 0.5–1 h | Doc | Yes | [MUST HAVE] | PM | E-03 | No — included in base price | No
M-01 | Competitor Research | Identify competitors | Choose 3–5 direct/local competitors and 1–2 aspirational ones with client | 1 | Low | 0.5–1 h | Doc | No | [RECOMMENDED] | Content/Design | D-02 | No — included in base price | No
M-02 | Competitor Research | Competitor site analysis | Review structure, messaging, CTAs, trust signals, pricing display, mobile experience; screenshots | 3 | Medium | 2–3 h | Doc + screenshots | No | [RECOMMENDED] | Design/Content | M-01 | No — included in base price | No
M-03 | Competitor Research | Competitor SEO snapshot | Note titles, key pages, GBP presence, reviews volume | 2 | Low | 1–2 h | Sheet | No | [OPTIONAL] | Content | M-01 | Conditional — depends on scope | No
N-01 | Brand Assets | Collect brand assets | Obtain logo (vector SVG/AI/PDF), colours, fonts, brand guide, photo library | 1 | Low | 0.5–1 h | Folder listing | No | [MUST HAVE] | Design | J-07 | No — included in base price | No
N-02 | Brand Assets | Verify brand asset rights | Confirm client owns logo, has licences for fonts/photos they supply; record licence files | 1 | Low | 0.5–1 h | Licence files | Yes | [MUST HAVE] | PM | N-01 | No — included in base price | No
N-03 | Brand Assets | Basic brand guide creation | Define palette, type pairing, logo usage if client has none | 7 | Medium | 3–8 h | File | Yes | [CONDITIONAL] | Design | N-01 | Yes — separate line item | No
N-04 | Brand Assets | Logo design | Logo concepts, refinement, final files and copyright assignment | 20 | High | 8–20 h | Files + approval | Yes | [CONDITIONAL] | Design | N-01 | Yes — separate line item | No
O-01 | Content Collection | Send content checklist with deadlines | Per page list of required text, images, videos, documents with due dates and format specs | 1 | Low | 0.5–1 h | Sent checklist | No | [MUST HAVE] | PM | E-04 | No — included in base price | No
O-02 | Content Collection | Collect content in shared folder | Receive files in organised folder; reject WhatsApp-compressed images where quality matters | 2 | Low | 1–2 h over project | Folder listing | No | [MUST HAVE] | PM | O-01 | No — included in base price | No
O-03 | Content Collection | Track content status | Mark each page item: pending/received/edited/approved | 1 | Low | 10 min/week | Tracker | No | [RECOMMENDED] | PM | O-02 | No — included in base price | No
O-04 | Content Collection | Image rights and consent check | Confirm source/licence for each image; photos of identifiable people/customers have consent; stock licence saved | 1 | Low | 0.5–2 h | Register + licence files | Yes | [MUST HAVE] | Content | O-02 | No — included in base price | No
O-05 | Content Collection | Process and optimise media | Crop, resize, compress, convert (WebP/AVIF), rename descriptively, write alt text drafts | 3 | Low | 1–4 h | Folder + size report | No | [MUST HAVE] | FE/Content | O-04 | No — included in base price | Yes
O-06 | Content Collection | Chase missing content and record delays | Remind client per plan; log delay days; notify timeline impact in writing | 1 | Low | 10–20 min each | Messages + log | No | [MUST HAVE] | PM | O-03 | No — included in base price | No
P-01 | Copywriting | Homepage copywriting | Write headline, value proposition, sections, CTAs based on research | 6 | Medium | 3–6 h | Doc with version | Yes | [CONDITIONAL] | Content | L-01, L-02 | Yes — separate line item | No
P-02 | Copywriting | Inner page copywriting | Write service/about/contact/FAQ copy | 3 | Medium | 1–3 h/page | Doc | Yes | [CONDITIONAL] | Content | P-01 | Yes — separate line item | No
P-03 | Copywriting | SEO copy optimisation | Integrate target keywords naturally in headings, intro, titles; avoid stuffing | 1 | Low | 0.5–1 h/page | Doc diff | No | [RECOMMENDED] | Content | L-03, P-01 | Conditional — depends on scope | No
P-04 | Copywriting | UI microcopy | Button labels, form hints, error messages, success messages, empty states | 2 | Low | 1–2 h | Doc | No | [RECOMMENDED] | Content/Design | S-02 | No — included in base price | No
P-05 | Copywriting | Proofread and content approval | Proofread all copy; client approves final text in writing | 2 | Low | 1–2 h | Approval email/sign-off | Yes | [MUST HAVE] | Content/PM | P-01, P-02, P-03, P-04, O-02 | No — included in base price | No
P-06 | Copywriting | Translation | Translate content to additional language(s) by qualified translator; client review | 5 | Medium | Varies by words | Files + approval | Yes | [CONDITIONAL] | Content | P-05 | Yes — separate line item | No
Q-01 | UX | Key user flows | Map flows for primary tasks (call, enquire, book, buy) from entry to success | 2 | Medium | 1–3 h | Diagram file | No | [RECOMMENDED] | Design | E-01, L-02 | No — included in base price | No
Q-02 | UX | Information architecture and navigation | Define navigation labels, hierarchy, footer links, URL structure | 2 | Medium | 1–2 h | Doc/diagram | Yes | [MUST HAVE] | Design | E-02 | No — included in base price | No
Q-03 | UX | Page content hierarchy | For each template define section order and priority | 2 | Low | 1–2 h | Doc | No | [RECOMMENDED] | Design | Q-02 | No — included in base price | No
Q-04 | UX | Conversion points and CTAs plan | Place calls, WhatsApp, forms, booking CTAs; define tracking events | 1 | Low | 0.5–1 h | Doc | No | [RECOMMENDED] | Design/PM | Q-01 | No — included in base price | No
R-01 | Wireframes | Low-fidelity wireframes | Grey-box wireframes, mobile-first, for each unique template | 5 | Medium | 2–6 h | Figma/file link | No | [RECOMMENDED] | Design | Q-03 | No — included in base price | No
R-02 | Wireframes | Wireframe review with client | Walkthrough; collect consolidated feedback | 1 | Low | 0.5–1 h | Meeting notes | Yes | [RECOMMENDED] | Design/PM | R-01 | No — included in base price | No
R-03 | Wireframes | Wireframe revisions | Apply one consolidated round; record approval | 2 | Low | 1–3 h | Version link + approval | Yes | [RECOMMENDED] | Design | R-02 | No — included in base price | No
S-01 | UI Design | Moodboard and style direction | 1–2 visual directions (colour, type, imagery, UI style) | 2 | Low | 1–3 h | Figma/file link | Yes | [RECOMMENDED] | Design | N-01 | No — included in base price | No
S-02 | UI Design | Homepage high-fidelity design | Desktop and mobile designs of homepage with real content | 10 | High | 4–10 h | Figma link/export | Yes | [MUST HAVE] | Design | S-01, R-03 | No — included in base price | No
S-03 | UI Design | Inner page template designs | Designs for each unique template (service, about, contact, blog list/post, product) desktop+mobile | 4 | Medium | 2–5 h/template | Figma link | Yes | [MUST HAVE] | Design | S-02 | No — included in base price | No
S-04 | UI Design | Interaction and state designs | Hover, focus, active, disabled, loading, error, success, empty states for components | 2 | Medium | 1–3 h | Figma frames | No | [RECOMMENDED] | Design | S-02 | No — included in base price | No
S-05 | UI Design | Design accessibility check | Check contrast (4.5:1 text), target sizes (24px min), focus visibility, not relying on colour alone | 1 | Low | 0.5–1 h | Checker screenshots | No | [MUST HAVE] | Design | S-02 | No — included in base price | No
S-06 | UI Design | Design handoff specification | Export assets, document spacing, breakpoints, component names, interactions | 2 | Low | 1–2 h | Figma dev link | No | [RECOMMENDED] | Design | S-03 | No — included in base price | No
T-01 | Design System | Colour tokens | Define named colour tokens (primary, surface, text, border, states) incl. dark mode if needed | 1 | Low | 0.5–1 h | Figma variables/file | No | [RECOMMENDED] | Design | S-01 | No — included in base price | No
T-02 | Design System | Typography scale | Font families, sizes, weights, line heights for headings/body across breakpoints | 1 | Low | 0.5–1 h | File | No | [RECOMMENDED] | Design | S-01 | No — included in base price | No
T-03 | Design System | Spacing, grid and breakpoints | Spacing scale, container widths, breakpoints | 1 | Low | 0.5–1 h | File | No | [RECOMMENDED] | Design | S-01 | No — included in base price | No
T-04 | Design System | Component library | Buttons, links, inputs, cards, nav, modals, accordions, alerts with variants/states | 5 | Medium | 2–6 h | Figma components | No | [RECOMMENDED] | Design | T-01, T-02, T-03 | No — included in base price | No
T-05 | Design System | Icons and image style | Choose licensed icon set and image treatment rules | 1 | Low | 0.5–1 h | File + licence | No | [OPTIONAL] | Design | S-01 | No — included in base price | No
U-01 | Client Design Approval | Design presentation | Present designs explaining rationale tied to goals | 1 | Low | 0.5–1 h | Meeting record | No | [RECOMMENDED] | Design | S-02, S-03 | No — included in base price | No
U-02 | Client Design Approval | Consolidated design feedback | Client sends one consolidated list per round from the decision-maker | 1 | Low | 0.5 h | Client email/doc | Yes | [MUST HAVE] | PM | U-01 | No — included in base price | No
U-03 | Client Design Approval | Design revision round | Apply agreed changes; classify out-of-scope items as change requests | 4 | Medium | 1–6 h/round | Version history | Yes | [MUST HAVE] | Design | U-02 | No — included in base price | No
U-04 | Client Design Approval | Written design sign-off | Client approves designs in writing; later visual changes are change requests | 1 | Low | 15 min | Signed approval/email | Yes | [MUST HAVE] | PM | U-03 | No — included in base price | No
V-01 | Frontend Development | Initialize frontend project | Create project with chosen framework/generator, set Node version, scripts (dev/build/preview) | 1 | Low | 0.5–1 h | Initial commit | No | [MUST HAVE] | FE | L-04, J-04 | No — included in base price | No
V-02 | Frontend Development | Establish folder structure and conventions | Folders for components, pages, styles, assets, utils; naming rules in README | 1 | Low | 0.5 h | Commit | No | [RECOMMENDED] | FE | V-01 | No — included in base price | No
V-03 | Frontend Development | Configure dependencies and lockfile | Add only needed packages; commit lockfile; record licences | 1 | Low | 0.5–1 h | Commit | No | [MUST HAVE] | FE | V-01 | No — included in base price | Yes
V-04 | Frontend Development | Linting, formatting and pre-commit hooks | Configure linter/formatter and optional pre-commit checks | 1 | Low | 0.5–1 h | Commit | No | [RECOMMENDED] | FE | V-01 | No — included in base price | No
V-05 | Frontend Development | Global styles and CSS variables | Reset/normalize, CSS custom properties from tokens, base element styles | 2 | Low | 1–2 h | Commit | No | [MUST HAVE] | FE | T-01, T-02, T-03 | No — included in base price | No
V-06 | Frontend Development | Typography and font loading | Implement type scale; self-host or optimise web fonts with font-display, subsetting, preload of critical font | 2 | Low | 1–2 h | Commit + Lighthouse note | No | [MUST HAVE] | FE | T-02 | No — included in base price | No
V-07 | Frontend Development | Layout primitives | Containers, grid/flex utilities, section spacing, responsive breakpoints | 2 | Low | 1–2 h | Commit | No | [RECOMMENDED] | FE | T-03 | No — included in base price | No
V-08 | Frontend Development | Header and desktop navigation | Logo, menu, active states, CTA button, skip link | 2 | Medium | 1–3 h | Commit + screenshot | No | [MUST HAVE] | FE | V-05 | No — included in base price | No
V-09 | Frontend Development | Responsive mobile navigation | Accessible menu toggle (button with aria-expanded), focus management, close on Escape, scroll lock | 4 | Medium | 2–4 h | Commit + device screenshots | No | [MUST HAVE] | FE | V-08 | No — included in base price | No
V-10 | Frontend Development | Footer | Contact details, links, legal pages, social links, copyright line | 2 | Low | 1–2 h | Commit | No | [MUST HAVE] | FE | V-05 | No — included in base price | No
V-11 | Frontend Development | Build homepage sections | Implement each homepage section from design with real content | 10 | High | 4–10 h | Commit + staging URL | No | [MUST HAVE] | FE | U-04, V-05, V-06, V-07, V-08, V-09, V-10 | No — included in base price | No
V-12 | Frontend Development | Build inner page templates | Implement each approved template and populate pages | 4 | Medium | 2–5 h/template | Commits + staging URLs | No | [MUST HAVE] | FE | V-11 | No — included in base price | No
V-13 | Frontend Development | Reusable UI components | Buttons, cards, accordions, tabs, modals, carousels (only if needed) with accessible behaviour | 5 | Medium | 2–6 h | Commits | No | [RECOMMENDED] | FE | T-04 | No — included in base price | No
V-14 | Frontend Development | Responsive images | srcset/sizes, width/height attributes, lazy-load below fold, eager/priority for hero | 2 | Low | 1–2 h | Commit + Lighthouse | No | [MUST HAVE] | FE | O-05 | No — included in base price | No
V-15 | Frontend Development | Implement form UI | Accessible fields with visible labels, autocomplete attributes, input types, required indicators | 2 | Medium | 1–3 h | Commit | No | [MUST HAVE] | FE | AB-01 | No — included in base price | No
V-16 | Frontend Development | Client-side validation | Inline validation with clear messages linked via aria-describedby; never the only validation | 2 | Low | 1–2 h | Commit + test | No | [MUST HAVE] | FE | V-15 | No — included in base price | No
V-17 | Frontend Development | Loading states | Button disabled/spinner on submit, skeletons for async content, prevent double submit | 1 | Low | 0.5–1 h | Commit | No | [MUST HAVE] | FE | V-15 | No — included in base price | No
V-18 | Frontend Development | Error and empty states | Friendly network/server error messages, retry, empty lists | 2 | Low | 1–2 h | Commit | No | [MUST HAVE] | FE | V-15 | No — included in base price | No
V-19 | Frontend Development | Animations and transitions | Subtle transitions respecting prefers-reduced-motion; no layout-shifting animations | 2 | Low | 1–3 h | Commit | No | [OPTIONAL] | FE | V-11 | No — included in base price | No
V-20 | Frontend Development | 404 and error pages | Custom 404 with navigation/search; server error page | 1 | Low | 0.5–1 h | Commit + URL test | No | [MUST HAVE] | FE | V-08 | No — included in base price | No
V-21 | Frontend Development | Favicon, app icons and manifest | Favicon set, apple-touch-icon, theme colour, web manifest if relevant | 1 | Low | 0.5 h | Commit | No | [MUST HAVE] | FE | N-01 | No — included in base price | No
V-22 | Frontend Development | API integration layer | Central fetch/client module with timeouts, error handling, typed responses | 2 | Medium | 1–3 h | Commit | No | [CONDITIONAL] | FE | Z-01 | No — included in base price | No
V-23 | Frontend Development | Consent banner UI | Consent UI for non-essential cookies/trackers where client chooses to use them; blocks tags until consent | 4 | Medium | 2–4 h | Commit + test | Yes | [CONDITIONAL] | FE | AJ-01 | Conditional — depends on scope | Yes
V-24 | Frontend Development | Print styles | Print stylesheet for menus, price lists, event pages | 1 | Low | 0.5–1 h | Commit | No | [OPTIONAL] | FE | V-12 | Conditional — depends on scope | No
V-25 | Frontend Development | Frontend tests | Component/unit tests for logic, basic end-to-end for key flows | 5 | Medium | 2–6 h | Test run output | No | [RECOMMENDED] | FE | V-11, V-12, V-13, V-14, V-15, V-16, V-17, V-18 | No — included in base price | No
W-01 | Backend Development | Initialize backend project | Scaffold server/serverless functions with runtime version, structure, scripts | 1 | Low | 0.5–1 h | Commit | No | [CONDITIONAL] | BE | L-04 | No — included in base price | No
W-02 | Backend Development | Environment configuration and secrets | .env.example with names only; secrets in host secret store; separate dev/staging/prod values | 1 | Low | 0.5–1 h | Commit (no secrets) | No | [MUST HAVE] | BE | W-01 | No — included in base price | Yes
W-03 | Backend Development | Data models and business logic | Implement entities (leads, bookings, products) and rules | 10 | High | 3–12 h | Commits + tests | No | [CONDITIONAL] | BE | X-02 | No — included in base price | No
W-04 | Backend Development | API endpoints | Implement endpoints for forms, content, bookings with consistent responses | 3 | Medium | 1–3 h/endpoint | Commits + API docs | No | [CONDITIONAL] | BE | Z-01, W-03 | No — included in base price | No
W-05 | Backend Development | Server-side validation and sanitisation | Validate type/length/format of every input; parameterised queries; encode output | 3 | Medium | 1–3 h | Commit + tests | No | [MUST HAVE] | BE | W-04 | No — included in base price | No
W-06 | Backend Development | Error handling and logging | Central error handler, structured logs without personal data/secrets, correlation IDs | 2 | Low | 1–2 h | Commit + sample log | No | [MUST HAVE] | BE | W-01 | No — included in base price | Yes
W-07 | Backend Development | Rate limiting and abuse protection | Limit form/login/API requests per IP/user | 2 | Low | 1–2 h | Config + test | No | [MUST HAVE] | BE | W-04 | No — included in base price | No
W-08 | Backend Development | File upload handling | Validate type (content not extension), size limits, virus scan if needed, private storage, random names | 4 | Medium | 2–5 h | Commit + tests | No | [CONDITIONAL] | BE | W-04 | No — included in base price | No
W-09 | Backend Development | Scheduled jobs | Cron/scheduled tasks (reminders, cleanup, backups) with monitoring | 2 | Medium | 1–3 h | Config + logs | No | [CONDITIONAL] | BE | W-03 | No — included in base price | Yes
W-10 | Backend Development | Backend tests | Unit/integration tests for logic and endpoints incl. auth failures | 5 | Medium | 2–6 h | Test output | No | [RECOMMENDED] | BE | W-04 | No — included in base price | No
X-01 | Database | Choose database and hosting | Select managed DB appropriate to scale/budget; region; backups included | 1 | Low | 0.5–1 h | ADR entry | No | [CONDITIONAL] | BE | L-04 | No — included in base price | No
X-02 | Database | Schema design | Tables/collections, relations, constraints, ERD; data minimisation | 3 | Medium | 1–4 h | Migration files + diagram | No | [CONDITIONAL] | BE | E-03 | No — included in base price | No
X-03 | Database | Migrations | Versioned migration scripts for schema changes | 1 | Low | 0.5–1 h | Commits | No | [CONDITIONAL] | BE | X-02 | No — included in base price | Yes
X-04 | Database | Seed and test data | Non-personal sample data for dev/staging | 1 | Low | 0.5–1 h | Commit | No | [CONDITIONAL] | BE | X-03 | No — included in base price | No
X-05 | Database | Indexes and constraints | Add indexes for queries; unique/foreign keys | 1 | Low | 0.5–1 h | Commit | No | [CONDITIONAL] | BE | X-02 | No — included in base price | No
X-06 | Database | Least-privilege database users | App user with only required permissions; separate admin credentials | 1 | Low | 0.5 h | Config record (no passwords) | No | [CONDITIONAL] | BE | X-01 | No — included in base price | No
X-07 | Database | Backup configuration and restore test | Automated backups with retention; perform one test restore | 2 | Medium | 1–2 h | Screenshot/log | No | [MUST HAVE] | BE/DevOps | X-01 | No — included in base price | Yes
Y-01 | Authentication | Authentication strategy | Choose managed auth vs framework auth; define user types; passkey/OTP/password options | 2 | Medium | 1–2 h | ADR | No | [CONDITIONAL] | BE | E-03 | No — included in base price | No
Y-02 | Authentication | Signup, login and logout | Implement flows with secure password hashing or provider; generic error messages | 7 | Medium | 3–8 h | Commits + tests | No | [CONDITIONAL] | BE/FE | Y-01 | No — included in base price | No
Y-03 | Authentication | Password reset and email verification | Single-use, expiring tokens; rate limited; no password in email | 4 | Medium | 2–4 h | Tests | No | [CONDITIONAL] | BE | Y-02, AC-01 | No — included in base price | No
Y-04 | Authentication | Role-based authorization | Enforce roles/ownership on server for every protected route/object | 5 | Medium | 2–6 h | Tests incl. negative cases | No | [CONDITIONAL] | BE | Y-02 | No — included in base price | No
Y-05 | Authentication | Session and token security | Secure, HttpOnly, SameSite cookies; expiry; rotation on login; logout invalidation | 2 | Low | 1–2 h | Config + tests | No | [CONDITIONAL] | BE | Y-02 | No — included in base price | No
Y-06 | Authentication | MFA for admin accounts | Enable MFA/2FA on admin logins (app, platform, CMS) | 1 | Low | 0.5–2 h | Screenshot/settings record | No | [RECOMMENDED] | BE | Y-02, AD-03 | No — included in base price | Yes
Z-01 | APIs | API contract and documentation | Document endpoints, request/response shapes, errors, auth | 2 | Medium | 1–3 h | Doc/OpenAPI file | No | [CONDITIONAL] | BE | E-03 | No — included in base price | No
Z-02 | APIs | Implement and version APIs | Build to contract; version when breaking changes occur | 5 | Medium | Varies | Commits | No | [CONDITIONAL] | BE | Z-01 | No — included in base price | No
Z-03 | APIs | API key scoping and restriction | Restrict keys by domain/IP/API; separate keys per environment; server-side use only for secrets | 1 | Low | 0.5–1 h | Console screenshot | No | [MUST HAVE] | BE | AA-01 | No — included in base price | Yes
AA-01 | Third-party Integrations | Third-party account ownership check | Confirm each service account is created by/for the client (client email, client billing) with you as invited user | 1 | Low | 0.5–1 h | Register + invite emails | Yes | [MUST HAVE] | PM | E-05 | No — included in base price | No
AA-02 | Third-party Integrations | Maps integration | Embed map or Maps API with restricted key; correct business location | 1 | Low | 0.5–1 h | Staging URL | No | [CONDITIONAL] | FE | AA-01 | No — included in base price | No
AA-03 | Third-party Integrations | WhatsApp contact integration | Click-to-chat link with prefilled message, or Business Platform integration if requested | 1 | Low | 0.5 h (link) / 4–10 h (API) | Test record | No | [CONDITIONAL] | FE | AA-01 | Conditional — depends on scope | No
AA-04 | Third-party Integrations | Social media embeds | Links/feeds/embeds with performance and privacy consideration | 1 | Low | 0.5–2 h | Commit | No | [OPTIONAL] | FE | AA-01 | No — included in base price | No
AA-05 | Third-party Integrations | CRM or email marketing integration | Send leads/subscribers to client's CRM/list with consent recorded | 5 | Medium | 2–6 h | Test record | No | [CONDITIONAL] | BE | AA-01, AB-04 | Yes — separate line item | Yes
AA-06 | Third-party Integrations | Integration failure handling | Timeouts, retries, fallback (e.g., store lead locally and email) and alerts | 2 | Medium | 1–3 h | Tests | No | [RECOMMENDED] | BE | AA-02, AA-03, AA-04, AA-05 | No — included in base price | No
AB-01 | Forms | Form specification and data minimisation | Define fields, required ones, purpose of each, where data goes, retention | 1 | Low | 0.5–1 h | Doc | Yes | [MUST HAVE] | PM | E-03 | No — included in base price | No
AB-02 | Forms | Form submission handling | Deliver to email/DB/CRM reliably; store copy; notify client | 2 | Medium | 1–3 h | Test submissions | No | [MUST HAVE] | BE | AB-01, AC-01 | No — included in base price | Yes
AB-03 | Forms | Spam protection | Honeypot, rate limit, time-trap, accessible CAPTCHA only if needed | 1 | Low | 0.5–1 h | Config + test | No | [MUST HAVE] | BE | AB-02 | No — included in base price | Yes
AB-04 | Forms | Notice and consent text on forms | Short notice of purpose with link to privacy notice; separate unticked opt-in for marketing | 1 | Low | 0.5 h | Screenshot | Yes | [MUST HAVE] | PM/FE | AB-01, BK-01 | No — included in base price | No
AB-05 | Forms | Confirmation and conversion tracking | Success message/thank-you page; fire conversion event | 1 | Low | 0.5–1 h | Analytics debug screenshot | No | [RECOMMENDED] | FE | AB-02, AJ-03 | No — included in base price | No
AB-06 | Forms | End-to-end form test | Submit every form on staging and production; verify email, storage, auto-reply | 1 | Low | 0.5–1 h | Test log + received emails | No | [MUST HAVE] | QA | AB-02, AB-03, AB-04, AB-05 | No — included in base price | Yes
AC-01 | Email | Transactional email service setup | Configure sending service in client's account; verify sending domain | 1 | Low | 0.5–1 h | Console screenshot | No | [CONDITIONAL] | BE/DevOps | AA-01 | No — included in base price | Yes
AC-02 | Email | SPF, DKIM and DMARC records | Add/merge SPF (one record), DKIM keys, DMARC policy for sending domain | 1 | Low | 0.5–1 h | DNS lookup output | No | [MUST HAVE] | DevOps | AC-01, AW-01 | No — included in base price | Yes
AC-03 | Email | Email templates | Notification and auto-reply templates with plain-text version and business details | 2 | Low | 1–2 h | Commit + test sends | Optional | [CONDITIONAL] | FE/BE | AC-01 | No — included in base price | No
AC-04 | Email | Deliverability test | Send tests to Gmail/Outlook/Yahoo; check spam placement and headers | 1 | Low | 0.5 h | Screenshots of headers | No | [MUST HAVE] | QA | AC-02 | No — included in base price | Yes
AC-05 | Email | Business mailbox setup | Set up client mailboxes on client's chosen provider; MX records | 3 | Medium | 1–4 h | Admin console record | Yes | [CONDITIONAL] | DevOps | AW-01 | Yes — separate line item | Yes
AD-01 | CMS | CMS selection | Choose CMS (none, headless, WordPress, hosted builder) based on who edits and how often | 1 | Low | 0.5–1 h | ADR | Yes | [CONDITIONAL] | FE/BE | L-04 | No — included in base price | No
AD-02 | CMS | Content model | Define collections/fields/validation for editable content | 4 | Medium | 2–5 h | Config/commit | No | [CONDITIONAL] | BE | AD-01 | No — included in base price | No
AD-03 | CMS | Editor roles and permissions | Client admin, editor roles; developer account separate and removable | 1 | Low | 0.5–1 h | Screenshot | No | [CONDITIONAL] | BE | AD-01 | No — included in base price | Yes
AD-04 | CMS | Content entry and migration | Enter/migrate agreed number of pages/items | 3 | Medium | 0.25–0.5 h/item | Page count record | No | [CONDITIONAL] | Content | AD-02, P-05 | Conditional — depends on scope | No
AD-05 | CMS | Plugin/extension vetting and licences | Check maintenance status, security history, licence terms and renewal cost of each plugin | 1 | Low | 0.5–1 h | Register | No | [CONDITIONAL] | BE | AD-01 | No — included in base price | Yes
AE-01 | Admin Dashboard | Admin requirements | Define admin tasks, roles, data views, exports | 1 | Low | 0.5–1 h | Doc | Yes | [CONDITIONAL] | PM | E-03 | Yes — separate line item | No
AE-02 | Admin Dashboard | Build admin screens | List/detail/edit screens with server-side authorization | 18 | High | 6–20 h | Commits + screenshots | No | [CONDITIONAL] | FE/BE | AE-01, Y-04 | Yes — separate line item | No
AE-03 | Admin Dashboard | Audit log | Record who changed what and when for admin actions | 4 | Medium | 2–4 h | Sample entries | No | [OPTIONAL] | BE | AE-02 | Yes — separate line item | No
AE-04 | Admin Dashboard | Data export | CSV export of leads/orders for client | 2 | Low | 1–2 h | Sample export | No | [OPTIONAL] | BE | AE-02 | Yes — separate line item | No
AF-01 | E-commerce | E-commerce platform decision | Choose hosted platform vs WooCommerce vs custom based on SKUs, budget, maintenance, payment and GST invoicing needs | 2 | Medium | 1–2 h | ADR | Yes | [CONDITIONAL] | PM/BE | E-03 | Yes — separate line item | No
AF-02 | E-commerce | Product catalogue setup | Categories, attributes, variants, prices incl./excl. GST, images, stock | 5 | Medium | 0.25–0.5 h/product | Product count record | No | [CONDITIONAL] | Content/BE | AF-01, O-02 | Yes — separate line item | Yes
AF-03 | E-commerce | Cart and checkout | Cart, address, shipping choice, order summary with total price, explicit consent (no pre-ticked boxes) | 15 | High | 6–16 h | E2E test record | No | [CONDITIONAL] | FE/BE | AF-02, AH-02 | Yes — separate line item | No
AF-04 | E-commerce | Tax display and invoice generation | Show taxes correctly; generate GST-compliant invoices per client's CA instructions | 5 | Medium | 2–6 h | Sample invoice reviewed by client's CA | Yes | [CONDITIONAL] | BE | AF-03 | Yes — separate line item | No
AF-05 | E-commerce | Shipping and delivery rules | Zones, rates, delivery estimates, COD rules if offered | 3 | Medium | 1–4 h | Test orders | Yes | [CONDITIONAL] | BE | AF-02 | Yes — separate line item | Yes
AF-06 | E-commerce | E-commerce mandatory disclosures | Display seller legal name, address, customer care and grievance officer contacts, return/refund/exchange/shipping/payment terms as supplied by client | 2 | Low | 1–2 h | Screenshots | Yes | [CONDITIONAL] | PM/FE | BK-04 | No — included in base price | Yes
AF-07 | E-commerce | Order notifications | Customer and admin emails/SMS for order placed/shipped/refunded | 4 | Medium | 2–4 h | Test emails | No | [CONDITIONAL] | BE | AC-01 | Yes — separate line item | Yes
AG-01 | Booking Systems | Booking tool decision | Choose embedded booking service vs custom based on complexity, payments, reminders | 1 | Low | 0.5–1 h | ADR | Yes | [CONDITIONAL] | PM | E-03 | Yes — separate line item | No
AG-02 | Booking Systems | Availability and slots configuration | Services, durations, buffers, staff, holidays, time zone (IST) | 3 | Medium | 1–4 h | Test bookings | Yes | [CONDITIONAL] | BE | AG-01 | Yes — separate line item | Yes
AG-03 | Booking Systems | Booking confirmations and reminders | Email/SMS/WhatsApp confirmations, reschedule/cancel links | 2 | Medium | 1–3 h | Test messages | No | [CONDITIONAL] | BE | AG-02, AC-01 | Yes — separate line item | Yes
AG-04 | Booking Systems | Calendar sync | Two-way sync with client's calendar | 2 | Medium | 1–3 h | Test event | No | [CONDITIONAL] | BE | AG-02 | Yes — separate line item | Yes
AH-01 | Payments | Payment gateway account (client-owned) | Client applies and completes KYC with gateway; developer gets restricted team access | 1 | Low | 0.5–1 h (dev time) | Team invite email | Yes | [CONDITIONAL] | Client + PM | AA-01 | No — included in base price | No
AH-02 | Payments | Integrate hosted/tokenised checkout | Use gateway's hosted page or SDK so card data never touches your server | 7 | Medium | 3–8 h | Test transactions | No | [CONDITIONAL] | BE/FE | AH-01 | Yes — separate line item | No
AH-03 | Payments | Webhook signature verification and idempotency | Verify webhook signatures; confirm payment server-side; process each event once | 4 | Medium | 2–4 h | Tests incl. forged payload | No | [CONDITIONAL] | BE | AH-02 | No — included in base price | No
AH-04 | Payments | Refund and failed-payment flows | Handle failures, pending, refunds and reconciliation | 4 | Medium | 2–4 h | Test cases | No | [CONDITIONAL] | BE | AH-03 | No — included in base price | No
AH-05 | Payments | Test-to-live switch | Swap to live keys stored as secrets; small real transaction test and refund | 1 | Low | 0.5–1 h | Live test txn record | Yes | [CONDITIONAL] | BE | AH-04 | No — included in base price | No
AI-01 | SEO | URL structure and slugs | Short, readable, lowercase, hyphenated URLs matching IA | 1 | Low | 0.5 h | Sitemap | No | [MUST HAVE] | FE | Q-02 | No — included in base price | No
AI-02 | SEO | Titles and meta descriptions | Unique title and description per page with brand and location where relevant | 2 | Low | 10–15 min/page | Crawl report | No | [MUST HAVE] | Content/FE | P-05 | No — included in base price | No
AI-03 | SEO | Heading hierarchy | One H1 per page, logical H2/H3 nesting | 1 | Low | 0.5–1 h | Crawl/a11y report | No | [MUST HAVE] | FE | V-12 | No — included in base price | No
AI-04 | SEO | Canonical tags | Self-referencing canonicals; handle www/non-www, trailing slash, parameters | 1 | Low | 0.5 h | Crawl report | No | [MUST HAVE] | FE | AY-02 | No — included in base price | No
AI-05 | SEO | XML sitemap | Auto-generated sitemap with production URLs only | 1 | Low | 0.5 h | Live URL | No | [MUST HAVE] | FE | AI-01 | No — included in base price | Yes
AI-06 | SEO | robots.txt and staging noindex | Production robots allows crawling and lists sitemap; staging blocked/noindex + auth | 1 | Low | 0.5 h | Live URL check | No | [MUST HAVE] | DevOps | J-05 | No — included in base price | No
AI-07 | SEO | Structured data | LocalBusiness/Organization, breadcrumbs, FAQ/Product where accurate; validate | 2 | Low | 1–2 h | Validator screenshot | No | [RECOMMENDED] | FE | P-05 | No — included in base price | Yes
AI-08 | SEO | Open Graph and social cards | og:title, og:description, og:image (1200×630), twitter card | 1 | Low | 0.5–1 h | Share preview screenshot | No | [MUST HAVE] | FE | N-01 | No — included in base price | No
AI-09 | SEO | Redirect map from old site | Map old URLs to new with 301 redirects; test | 3 | Medium | 1–4 h | Map + test results | No | [CONDITIONAL] | FE/DevOps | D-05 | No — included in base price | No
AI-10 | SEO | Business profile consistency | Ensure name, address, phone match Google Business Profile and site; link website (client-owned profile) | 1 | Low | 0.5–1 h | Screenshots | Yes | [RECOMMENDED] | Content | D-05 | Conditional — depends on scope | Yes
AI-11 | SEO | Search Console setup and sitemap submission | Client verifies property (DNS preferred) as owner; developer added as user; submit sitemap | 1 | Low | 0.5 h | Screenshot of users page | No | [MUST HAVE] | DevOps | AV-01 | No — included in base price | Yes
AJ-01 | Analytics | Analytics property in client's account | Create analytics account/property owned by client; developer as property-level user | 1 | Low | 0.5 h | Access-management screenshot | No | [MUST HAVE] | DevOps | AA-01 | No — included in base price | No
AJ-02 | Analytics | Install tag with consent handling | Install analytics tag; gate on consent if client adopts consent-based approach | 1 | Low | 0.5–1 h | Tag assistant screenshot | Yes | [CONDITIONAL] | FE | AJ-01, V-23 | No — included in base price | No
AJ-03 | Analytics | Conversion and event tracking | Track form success, calls (tel: clicks), WhatsApp clicks, bookings, purchases | 2 | Medium | 1–3 h | Debug view screenshots | No | [RECOMMENDED] | FE | Q-04 | No — included in base price | Yes
AJ-04 | Analytics | Verify analytics data | Check real-time/debug data for page views and events on production | 1 | Low | 0.5 h | Screenshot | No | [MUST HAVE] | QA | AJ-02, AJ-03 | No — included in base price | No
AK-01 | Accessibility | Set accessibility target | Agree target (e.g., WCAG 2.2 Level AA for templates and flows built by you) and what is out of scope (client-uploaded content) | 1 | Low | 15 min | Scope doc | Yes | [RECOMMENDED] | PM | E-06 | No — included in base price | No
AK-02 | Accessibility | Semantic HTML and landmarks | Use header/nav/main/footer, buttons for actions, links for navigation, lists, tables correctly | 1 | Low | Built into dev | Code review note | No | [MUST HAVE] | FE | V-08 | No — included in base price | No
AK-03 | Accessibility | Keyboard navigation and focus | All interactive elements reachable by Tab, visible focus, logical order, no traps, focus not hidden by sticky headers | 2 | Low | 1–2 h | Test checklist | No | [MUST HAVE] | FE/QA | V-13 | No — included in base price | No
AK-04 | Accessibility | Alt text and media alternatives | Meaningful alt for informative images, empty alt for decorative; captions/transcripts for video | 2 | Low | 1–2 h | Audit report | Optional | [MUST HAVE] | Content | O-05 | No — included in base price | Yes
AK-05 | Accessibility | Colour contrast verification | Check text and UI component contrast in built site | 1 | Low | 0.5 h | Tool output | No | [MUST HAVE] | QA | S-05 | No — included in base price | No
AK-06 | Accessibility | Accessible form labels and errors | Labels tied to inputs, error text announced, not colour-only, redundant entry avoided | 1 | Low | 0.5–1 h | Checklist | No | [MUST HAVE] | FE/QA | V-15, V-16 | No — included in base price | No
AK-07 | Accessibility | Automated accessibility scan | Run automated checker on each template; fix issues | 1 | Low | 0.5–1 h | Report file | No | [MUST HAVE] | QA | V-12 | No — included in base price | Yes
AK-08 | Accessibility | Screen reader smoke test | Test key flows with NVDA/VoiceOver/TalkBack: headings, landmarks, forms, menus | 2 | Medium | 1–2 h | Notes/recording | No | [RECOMMENDED] | QA | AK-02, AK-03, AK-04, AK-05, AK-06 | No — included in base price | No
AL-01 | Performance | Performance budget | Set targets: LCP ≤2.5 s, INP ≤200 ms, CLS ≤0.1, page weight and JS limits | 1 | Low | 15–30 min | Scope/NFR doc | No | [RECOMMENDED] | FE | E-06 | No — included in base price | No
AL-02 | Performance | Image optimisation | Modern formats, correct dimensions, compression, CDN | 2 | Low | 1–2 h | Lighthouse report | No | [MUST HAVE] | FE | O-05 | No — included in base price | Yes
AL-03 | Performance | Font optimisation | Subset, preload critical, limit weights, font-display | 1 | Low | 0.5–1 h | Report | No | [RECOMMENDED] | FE | V-06 | No — included in base price | No
AL-04 | Performance | JavaScript and CSS optimisation | Remove unused code, split bundles, defer non-critical scripts, audit third-party scripts | 2 | Medium | 1–3 h | Bundle report | No | [RECOMMENDED] | FE | V-11 | No — included in base price | No
AL-05 | Performance | Caching and CDN | Cache headers for static assets (hashed filenames), compression (Brotli/gzip), CDN | 1 | Low | 0.5–1 h | Header check output | No | [RECOMMENDED] | DevOps | AX-01 | No — included in base price | Yes
AL-06 | Performance | Lab performance test (mobile) | Lighthouse/PageSpeed on mobile profile for key templates; fix major issues | 1 | Low | 0.5–1 h | Saved reports | No | [MUST HAVE] | QA | AL-02, AL-03, AL-04, AL-05 | No — included in base price | No
AL-07 | Performance | Field data review | After traffic accrues, review Core Web Vitals field data (Search Console/CrUX) | 1 | Low | 0.5 h | Screenshot | No | [POST-LAUNCH] | FE | BA-03 | Conditional — depends on scope | Yes
AM-01 | Security | Dependency vulnerability audit | Run package audit/scanner; update or replace vulnerable packages | 1 | Low | 0.5–1 h | Report | No | [MUST HAVE] | FE/BE | V-03 | No — included in base price | Yes
AM-02 | Security | Security headers | HSTS, Content-Security-Policy, X-Content-Type-Options, Referrer-Policy, frame-ancestors, Permissions-Policy | 2 | Medium | 1–3 h | Header scan output | No | [RECOMMENDED] | DevOps | AX-01 | No — included in base price | Yes
AM-03 | Security | Secrets scan | Scan repo history for keys/passwords; rotate anything found | 1 | Low | 0.5 h | Report | No | [MUST HAVE] | BE | J-04 | No — included in base price | No
AM-04 | Security | Injection and XSS review | Review inputs/outputs; parameterised queries; output encoding; test common payloads | 2 | Medium | 1–2 h | Checklist + test log | No | [MUST HAVE] | BE/QA | W-05 | No — included in base price | No
AM-05 | Security | Access control review | Try accessing other users' records, admin routes without auth, changing IDs | 2 | Medium | 1–2 h | Test cases | No | [MUST HAVE] | QA | Y-04 | No — included in base price | No
AM-06 | Security | Admin protection | MFA, strong unique passwords, login rate limits, remove default accounts, restrict admin by role | 1 | Low | 0.5–1 h | Settings screenshots | No | [MUST HAVE] | DevOps | Y-06, AD-03 | No — included in base price | Yes
AM-07 | Security | File upload security test | Try disallowed types, oversized files, script files, path tricks | 1 | Low | 0.5–1 h | Results | No | [CONDITIONAL] | QA | W-08 | No — included in base price | No
AM-08 | Security | Error message and debug review | Debug mode off; no stack traces, versions or paths shown to users | 1 | Low | 0.5 h | Screenshot of error page | No | [MUST HAVE] | BE | AZ-01 | No — included in base price | No
AM-09 | Security | OWASP Top 10 checklist pass | Walk through OWASP Top 10:2025 categories relevant to the site; record status | 2 | Medium | 1–2 h | Completed checklist | No | [RECOMMENDED] | BE/QA | AM-01, AM-02, AM-03, AM-04, AM-05, AM-06, AM-07, AM-08 | No — included in base price | No
AN-01 | Responsive Design | Breakpoint testing | Test at 320, 360, 390, 414, 768, 1024, 1280, 1440, 1920+ widths | 2 | Low | 1–2 h | Screenshots | No | [MUST HAVE] | QA | V-12 | No — included in base price | No
AN-02 | Responsive Design | Real device testing | Test on at least one mid-range Android (Chrome), one iPhone (Safari), one tablet | 2 | Low | 1–2 h | Photos/screenshots | No | [MUST HAVE] | QA | AN-01 | No — included in base price | No
AN-03 | Responsive Design | Touch targets and orientation | Targets ≥24px (aim 44px), spacing, landscape orientation, zoom not disabled | 1 | Low | 0.5 h | Results | No | [MUST HAVE] | QA | AN-02 | No — included in base price | No
AO-01 | Cross-browser Testing | Browser support matrix | Define supported browsers/versions in scope (latest 2 versions of Chrome, Edge, Firefox, Safari incl. iOS) | 1 | Low | 15 min | Scope doc | Yes | [MUST HAVE] | PM | E-06 | No — included in base price | No
AO-02 | Cross-browser Testing | Cross-browser testing | Test key pages/flows in each matrix browser | 2 | Medium | 1–3 h | Screenshots | No | [MUST HAVE] | QA | AO-01 | No — included in base price | No
AO-03 | Cross-browser Testing | Fix browser-specific issues | Resolve CSS/JS compatibility issues found | 3 | Medium | 1–4 h | Commits | No | [MUST HAVE] | FE | AO-02 | No — included in base price | No
AP-01 | QA | Tailor QA test plan | Copy master QA checklist, remove non-applicable items, add project-specific flows | 1 | Low | 0.5–1 h | Checklist file | No | [MUST HAVE] | QA | E-07 | No — included in base price | No
AP-02 | QA | Functional testing | Test every link, button, form, navigation, search/filter, login flows per checklist | 5 | Medium | 2–6 h | Completed checklist + bug list | No | [MUST HAVE] | QA (not the builder where possible) | AP-01 | No — included in base price | No
AP-03 | QA | Content QA | Spelling, grammar, phone numbers (tap-to-call works), emails, address, prices, hours, social links, legal pages present | 2 | Low | 1–2 h | Checklist | No | [MUST HAVE] | Content/QA | P-05 | No — included in base price | Yes
AP-04 | QA | Regression testing | Re-run key checks after fixes and before launch | 1 | Low | 0.5–2 h | Checklist | No | [MUST HAVE] | QA | AQ-02 | No — included in base price | Yes
AP-05 | QA | UAT preparation | Prepare staging, test script and feedback template for client acceptance testing | 1 | Low | 0.5–1 h | Sent pack | No | [RECOMMENDED] | PM | AP-02 | No — included in base price | No
AQ-01 | Bug Fixing | Bug triage | Log each issue with steps, expected/actual, device, severity (blocker/major/minor/cosmetic), classify bug vs change | 1 | Low | 5 min/bug | Tracker entries | No | [MUST HAVE] | PM/QA | AP-02, AR-02 | No — included in base price | Yes
AQ-02 | Bug Fixing | Fix bugs | Resolve bugs by priority with commit references | 1 | Varies | Varies | Commits linked to bug IDs | No | [MUST HAVE] | FE/BE | AQ-01 | No — included in base price | Yes
AQ-03 | Bug Fixing | Verify and close bugs | Tester (ideally other partner) verifies on staging; closes with evidence | 1 | Low | 5–10 min/bug | Tracker status + screenshot | No | [MUST HAVE] | QA | AQ-02 | No — included in base price | Yes
AR-01 | Client Review | Staging review walkthrough | Walk client through staging site, how to give feedback, deadline for round | 1 | Low | 0.5–1 h | Meeting record | No | [RECOMMENDED] | PM | AP-05 | No — included in base price | No
AR-02 | Client Review | Collect consolidated client feedback | One list from decision-maker per round with page, issue, screenshot | 1 | Low | 0.5 h | Client doc/email | Yes | [MUST HAVE] | PM | AR-01 | No — included in base price | No
AR-03 | Client Review | Classify feedback | Mark each item: bug (free), in-scope revision (counts toward round), change request (priced) | 1 | Low | 0.5–1 h | Doc sent to client | Yes | [MUST HAVE] | PM | AR-02 | No — included in base price | No
AS-01 | Revisions | Revision round 1 | Implement in-scope revisions from round 1; send summary of changes | 6 | Medium | 2–8 h | Change summary + commits | Yes | [MUST HAVE] | FE/Design | AR-03 | No — included in base price | No
AS-02 | Revisions | Revision round 2 | Final in-scope round | 3 | Low | 1–4 h | Change summary | Yes | [RECOMMENDED] | FE/Design | AS-01 | No — included in base price | No
AS-03 | Revisions | Revision count notice | Tell client when included rounds are used and how further changes are billed | 1 | Low | 10 min | Sent message | No | [MUST HAVE] | PM | AS-01 | No — included in base price | No
AT-01 | Scope Changes | Log change request | Record requested change: description, requester, date, reason, priority | 1 | Low | 10–15 min | CR form | No | [MUST HAVE] | PM | E-07 | No — included in base price | No
AT-02 | Scope Changes | Change impact assessment | Estimate effort, cost, timeline and risk impact; note dependencies | 1 | Low | 0.5–1 h | CR form | No | [MUST HAVE] | PM/Dev | AT-01 | No — included in base price | No
AT-03 | Scope Changes | Change order approval and invoice | Client approves CR in writing (price, timeline shift); add to invoice schedule | 1 | Low | 15–30 min | Signed CR/email | Yes | [MUST HAVE] | PM | AT-02 | Yes — separate line item | No
AU-01 | Deployment | CI/CD pipeline | Automated build/test/deploy from main branch to staging/prod (host-native or CI) | 2 | Medium | 1–3 h | Pipeline run log | No | [RECOMMENDED] | DevOps | J-04 | No — included in base price | Yes
AU-02 | Deployment | Production build and environment variables | Set production env vars in host secret store; build with production settings | 1 | Low | 0.5–1 h | Checklist (names only) | No | [MUST HAVE] | DevOps | W-02 | No — included in base price | No
AU-03 | Deployment | Deploy to production | Deploy tagged release; record version, time, deployer | 1 | Low | 0.5–1 h | Deploy log + release tag | No | [MUST HAVE] | DevOps | AU-02, BA-01 | No — included in base price | Yes
AU-04 | Deployment | Rollback plan | Documented and tested way to revert to previous release and restore DB | 1 | Low | 0.5–1 h | Doc + test note | No | [RECOMMENDED] | DevOps | AU-01 | No — included in base price | Yes
AV-01 | Domain | Domain registration or ownership confirmation | Domain registered by client (their registrar account, client as registrant) or client confirms existing ownership; record expiry date | 1 | Low | 0.5–1 h | WHOIS/registrar screenshot, invoice in client name | Yes | [MUST HAVE] | PM | D-05 | No — included in base price | Yes
AV-02 | Domain | Registrar account security | Client enables MFA, registrar lock, auto-renew, valid recovery email/phone | 1 | Low | 0.5 h | Settings screenshots | Yes | [MUST HAVE] | Client + PM | AV-01 | No — included in base price | Yes
AV-03 | Domain | Record renewal dates | Record domain, SSL (if manual), hosting, licence renewals in register and reminders | 1 | Low | 15–30 min | Register | No | [MUST HAVE] | PM | AV-01 | No — included in base price | Yes
AW-01 | DNS | DNS record inventory and plan | Export current DNS (MX, TXT, SPF, DKIM, verification, subdomains) before changes; plan new records; lower TTL 24–48 h ahead | 1 | Low | 0.5–1 h | Export file | No | [MUST HAVE] | DevOps | AV-01 | No — included in base price | No
AW-02 | DNS | DNS cutover | Apply records (A/AAAA/CNAME) in client-controlled DNS | 1 | Low | 0.5 h | Before/after lookup output | Yes | [MUST HAVE] | DevOps | AW-01, AU-03 | No — included in base price | No
AW-03 | DNS | Propagation check and cleanup | Verify from multiple resolvers; restore normal TTL; remove obsolete records | 1 | Low | 0.5 h | Lookup outputs | No | [MUST HAVE] | DevOps | AW-02 | No — included in base price | Yes
AX-01 | Hosting | Hosting selection and sizing | Choose host by stack, traffic, region, backups, support, cost, renewal price | 1 | Low | 0.5–1 h | ADR + price note | Yes | [MUST HAVE] | DevOps | L-04 | No — included in base price | No
AX-02 | Hosting | Hosting account in client's name | Client creates account and billing; developer invited as member/collaborator | 1 | Low | 0.5 h | Invite email, billing screenshot | Yes | [MUST HAVE] | Client + PM | AX-01 | No — included in base price | Yes
AX-03 | Hosting | Server hardening | For VPS: OS updates, firewall, SSH keys only, no root login, fail2ban/equivalent, automatic security updates | 8 | High | 3–8 h | Checklist + config | No | [CONDITIONAL] | DevOps | AX-01 | Yes — separate line item | Yes
AY-01 | SSL/HTTPS | TLS certificate issuance and auto-renewal | Issue certificate (host-managed or ACME) for apex and www; confirm auto-renew | 1 | Low | 0.5 h | Browser/SSL check | No | [MUST HAVE] | DevOps | AW-02 | No — included in base price | Yes
AY-02 | SSL/HTTPS | HTTPS and canonical host redirects | 301 HTTP→HTTPS and non-canonical host (www or apex) to canonical; HSTS when stable | 1 | Low | 0.5 h | curl/redirect test output | No | [MUST HAVE] | DevOps | AY-01 | No — included in base price | No
AY-03 | SSL/HTTPS | Mixed content check | Ensure all assets load over HTTPS | 1 | Low | 0.25 h | Console screenshot | No | [MUST HAVE] | QA | AY-02 | No — included in base price | No
AZ-01 | Production Environment | Production configuration review | Debug off, correct env, logging level, error pages, timezone, email sender | 1 | Low | 0.5 h | Checklist | No | [MUST HAVE] | DevOps | AU-02 | No — included in base price | No
AZ-02 | Production Environment | Storage permissions | Buckets private by default; public only for public assets; signed URLs for private files | 1 | Low | 0.5 h | Policy screenshot | No | [CONDITIONAL] | DevOps | W-08 | No — included in base price | Yes
AZ-03 | Production Environment | Uptime monitoring | Monitor homepage and key endpoint; alerts to client and/or maintainer | 1 | Low | 0.25–0.5 h | Monitor screenshot | No | [RECOMMENDED] | DevOps | AU-03 | No — included in base price | Yes
AZ-04 | Production Environment | Error monitoring | Capture frontend/backend errors with PII scrubbing | 1 | Low | 0.5–1 h | Dashboard screenshot | No | [OPTIONAL] | DevOps | AU-03 | No — included in base price | Yes
BA-01 | Launch | Run pre-launch checklist | Complete launch checklist (SEO, forms, analytics, legal pages, redirects, backups, robots) | 2 | Low | 1–2 h | Checklist file | No | [MUST HAVE] | QA/PM | AP-04 | No — included in base price | No
BA-02 | Launch | Final approval and launch window | Client gives written final approval; agree go-live date/time (avoid Friday evening, festivals) | 1 | Low | 15–30 min | Signed approval/email | Yes | [MUST HAVE] | PM | BA-01 | No — included in base price | No
BA-03 | Launch | Go-live | Execute deploy + DNS cutover per plan; monitor | 2 | Low | 1–2 h | Timestamped log | No | [MUST HAVE] | DevOps | BA-02, AU-03, AW-02 | No — included in base price | No
BA-04 | Launch | Staging lockdown | Ensure staging remains password-protected/noindexed or is taken down | 1 | Low | 0.25 h | Check result | No | [MUST HAVE] | DevOps | BA-03 | No — included in base price | No
BA-05 | Launch | Launch announcement support | Draft announcement post/email/WhatsApp status for client | 1 | Low | 0.5–1 h | File | Optional | [OPTIONAL] | Content | BA-03 | Yes — separate line item | No
BB-01 | Post-launch Testing | Production smoke test | Test key pages, navigation, mobile view, HTTPS on live domain | 1 | Low | 0.5–1 h | Checklist + screenshots | No | [MUST HAVE] | QA | BA-03 | No — included in base price | Yes
BB-02 | Post-launch Testing | Live forms, emails and payments test | Real submissions and (if applicable) small live payment + refund on production | 1 | Low | 0.5–1 h | Received emails, txn IDs | No | [MUST HAVE] | QA | BB-01 | No — included in base price | Yes
BB-03 | Post-launch Testing | Indexing check | Submit sitemap, inspect homepage URL in Search Console, confirm no noindex | 1 | Low | 0.25–0.5 h | Screenshot | No | [MUST HAVE] | Content | AI-11 | No — included in base price | Yes
BB-04 | Post-launch Testing | Post-launch monitoring review | Review errors, uptime, analytics, form deliveries, Search Console coverage over first 7–14 days | 2 | Low | 1–2 h | Note + screenshots | No | [RECOMMENDED] | DevOps/QA | BA-03 | No — included in base price | Yes
BC-01 | Handover | Prepare handover package | Assemble docs, account register, licence register, design files, source code access, backups, maintenance options | 4 | Medium | 2–4 h | Package folder | No | [MUST HAVE] | PM | BD-01, BD-02, BD-03, BD-04 | No — included in base price | No
BC-02 | Handover | Handover meeting | Walk through site, accounts, how to get help, what warranty covers, renewals | 2 | Low | 1–1.5 h | Meeting record | No | [MUST HAVE] | PM | BC-01 | No — included in base price | No
BC-03 | Handover | Handover acknowledgement | Client signs acknowledgement listing items received and access confirmed | 1 | Low | 15–30 min | Signed form | Yes | [MUST HAVE] | PM | BC-02 | No — included in base price | No
BD-01 | Documentation | Technical README | Setup, build, deploy steps, env var names (not values), architecture, dependencies, known issues | 2 | Medium | 1–3 h | Repo file | No | [MUST HAVE] | FE/BE | V-01 | No — included in base price | Yes
BD-02 | Documentation | Client user guide | How to edit content, add images, manage forms/leads, common tasks with screenshots | 2 | Low | 1–3 h | File | No | [RECOMMENDED] | Content | AD-04 | No — included in base price | No
BD-03 | Documentation | Account and asset register | Every account/service: owner, URL, purpose, who has access, renewal date, cost, where credentials are stored (not the credentials) | 2 | Low | 1–2 h | Register file | Yes | [MUST HAVE] | PM | D-05 | No — included in base price | Yes
BD-04 | Documentation | Third-party licence register | List fonts, images, icons, themes, plugins, libraries with licence type, licensee, proof, renewal | 2 | Low | 1–2 h | Register + licence files | No | [MUST HAVE] | PM | O-04, AD-05, V-03 | No — included in base price | Yes
BE-01 | Training | CMS/admin training session | Live training on content edits and admin tasks; record with consent | 2 | Low | 1–2 h | Recording link | No | [RECOMMENDED] | Content/FE | BD-02 | No — included in base price | No
BE-02 | Training | Training follow-up | Answer follow-up questions within agreed window | 1 | Low | 0.5–1 h | Messages | No | [OPTIONAL] | Either | BE-01 | No — included in base price | No
BF-01 | Final Payment | Final invoice | Invoice remaining balance plus approved change orders, less advance | 1 | Low | 15–30 min | Invoice file | No | [MUST HAVE] | PM | BA-02 | No — included in base price | No
BF-02 | Final Payment | Final payment confirmation | Confirm bank credit, issue receipt, update ledger | 1 | Low | 15 min | Bank ref + receipt | No | [MUST HAVE] | PM | BF-01 | No — included in base price | No
BF-03 | Final Payment | Collect TDS certificate | Request TDS certificate for amounts deducted; reconcile with AIS/26AS | 1 | Low | 15 min | File | No | [CONDITIONAL] | PM | I-04 | No — included in base price | No
BG-01 | Ownership Transfer | Domain control confirmation | Confirm client is registrant and sole account holder; developer removed from registrar; if transfer needed, initiate with auth code (TAC/EPP) securely | 1 | Low | 0.5–2 h | WHOIS/RDAP + registrar screenshots | Yes | [MUST HAVE] | PM + Client | BF-02 | No — included in base price | No
BG-02 | Ownership Transfer | Hosting/cloud ownership transfer | Transfer project/team ownership or confirm client-owned account; downgrade/remove developer access | 1 | Low | 0.5–2 h | Owner screenshot | Yes | [MUST HAVE] | DevOps + Client | BF-02 | No — included in base price | No
BG-03 | Ownership Transfer | Repository transfer | Transfer repo to client org/account or deliver full archive; confirm client admin; remove developer collaborator if not maintaining | 1 | Low | 0.5–1 h | Repo settings screenshot | Yes | [MUST HAVE] | FE/BE | BF-02, BD-01 | No — included in base price | No
BG-04 | Ownership Transfer | Analytics and Search Console ownership | Confirm client is GA Administrator and verified Search Console owner; remove developer tokens/access or downgrade | 1 | Low | 0.5 h | Access screenshots | Yes | [MUST HAVE] | DevOps | BF-02 | No — included in base price | No
BG-05 | Ownership Transfer | Third-party accounts transfer | For each service in register: confirm client owner, billing, API key ownership; transfer anything created by developer | 2 | Medium | 1–3 h | Register with 'transferred' status | Yes | [MUST HAVE] | PM | BD-03 | No — included in base price | No
BG-06 | Ownership Transfer | Credential rotation | Rotate all passwords/keys the developer knew: admin, DB, SMTP, API keys, webhooks secrets; update env vars; test | 2 | Medium | 1–3 h | Checklist with dates (no secrets) | Yes | [MUST HAVE] | DevOps + Client | BG-01, BG-02, BG-03, BG-04, BG-05 | No — included in base price | No
BG-07 | Ownership Transfer | Developer access removal or downgrade | Remove or reduce developer access per maintenance agreement; document what remains and why | 1 | Low | 0.5–1 h | Access list screenshots | Yes | [MUST HAVE] | PM | BG-06 | No — included in base price | No
BG-08 | Ownership Transfer | Execute copyright assignment/licence | Sign assignment for commissioned deliverables (specifying work, rights, duration, territory, consideration) and licence for pre-existing/reusable components | 1 | Low | 0.5–1 h | Signed document | Yes | [MUST HAVE] | PM | BF-02 | No — included in base price | No
BG-09 | Ownership Transfer | Ownership transfer confirmation | Client signs checklist confirming each item transferred and tested | 1 | Low | 15–30 min | Signed form | Yes | [MUST HAVE] | PM | BG-01, BG-02, BG-03, BG-04, BG-05, BG-06, BG-07, BG-08 | No — included in base price | No
BH-01 | Maintenance | Maintenance agreement proposal | Offer AMC tiers: updates, backups, monitoring, content edit hours, response times, exclusions, price; separate contract | 2 | Low | 1–2 h | Signed AMC or declined note | Yes | [RECOMMENDED] | PM | BC-02 | Yes — separate line item | Yes
BH-02 | Maintenance | Monthly updates | Update dependencies/CMS/plugins on staging, test, deploy | 2 | Medium | 1–3 h/month | Changelog + commits | No | [POST-LAUNCH] | FE/BE | BH-01 | Yes — separate line item | Yes
BH-03 | Maintenance | Backup verification | Confirm backups ran; quarterly test restore | 1 | Low | 0.5 h/month | Screenshot/log | No | [POST-LAUNCH] | DevOps | X-07 | Yes — separate line item | Yes
BH-04 | Maintenance | Monitoring review | Review uptime, errors, security alerts, form delivery | 1 | Low | 0.5–1 h/month | Report | No | [POST-LAUNCH] | DevOps | AZ-03 | Yes — separate line item | Yes
BH-05 | Maintenance | Renewal reminders | Remind client 30/14/7 days before domain, hosting, licence renewals | 1 | Low | 10 min/month | Messages | No | [POST-LAUNCH] | PM | AV-03 | No — included in base price | Yes
BH-06 | Maintenance | Monthly maintenance report | Summary: updates, uptime, backups, issues, hours used, recommendations | 1 | Low | 0.5–1 h/month | Sent report | No | [POST-LAUNCH] | PM | BH-02, BH-03, BH-04 | Yes — separate line item | Yes
BI-01 | Support | Warranty/defect period support | Fix defects reported within warranty window (e.g., 30 days) that are genuine bugs in delivered work | 1 | Varies | Varies | Tickets + commits | No | [MUST HAVE] | FE/BE | BA-03 | No — included in base price | Yes
BI-02 | Support | Support ticket handling | Log requests, classify (defect/AMC/billable), respond within agreed times | 1 | Low | Varies | Tickets | No | [POST-LAUNCH] | Either | BH-01 | Conditional — depends on scope | Yes
BI-03 | Support | Small content edits | Content edits within AMC hours; beyond that billed | 1 | Low | 0.25–1 h each | Tickets | No | [POST-LAUNCH] | Content | BH-01 | Conditional — depends on scope | Yes
BJ-01 | Project Closure | Project retrospective | Partners review estimate vs actual, what went well/badly, update templates and default points | 1 | Low | 1 h | Notes | No | [RECOMMENDED] | Either (both) | BG-09 | No — included in base price | No
BJ-02 | Project Closure | Final contribution calculation and sign-off | Freeze tasks/points, resolve open disputes, both partners approve contribution percentages | 1 | Low | 0.5–1 h | App lock + both approvals | No | [MUST HAVE] | Either (both) | BJ-01 | No — included in base price | No
BJ-03 | Project Closure | Profit distribution record | Calculate net profit (revenue − expenses − reserves − taxes set aside), distribute per statement, record payments | 1 | Low | 0.5–1 h | Bank refs | No | [MUST HAVE] | PM | BJ-02, BF-02 | No — included in base price | No
BJ-04 | Project Closure | Archive project records | Archive contract, approvals, invoices, CRs, handover docs, evidence per retention policy | 1 | Low | 0.5–1 h | Archive location record | No | [MUST HAVE] | PM | BJ-03 | No — included in base price | No
BJ-05 | Project Closure | Testimonial and portfolio permission | Request testimonial/review and written permission to show the work | 1 | Low | 15–30 min | Email/message | Optional | [RECOMMENDED] | Sales | BG-09 | No — included in base price | No
BJ-06 | Project Closure | Close project and revoke internal access | Close tasks, archive board, remove temporary accounts/vault items no longer needed | 1 | Low | 0.5 h | App status | No | [MUST HAVE] | PM | BJ-04 | No — included in base price | No
BK-01 | Legal & Compliance Pages (added) | Privacy notice (client-owned) | Obtain privacy notice from client (ideally lawyer-reviewed) covering what forms/analytics collect, purposes, contact; publish and link | 1 | Low | 0.5–1 h (dev) | Page URL + client approval | Yes | [MUST HAVE] | Client + PM | AB-01 | No — included in base price | Yes
BK-02 | Legal & Compliance Pages (added) | Terms of use (client-owned) | Publish client-provided website terms | 1 | Low | 0.5 h (dev) | Page URL | Yes | [RECOMMENDED] | Client + PM | P-05 | No — included in base price | No
BK-03 | Legal & Compliance Pages (added) | Cookie/tracker notice | Explain cookies/trackers used; link from consent banner | 1 | Low | 0.5 h | Page URL | Yes | [CONDITIONAL] | Client + PM | V-23 | No — included in base price | Yes
BK-04 | Legal & Compliance Pages (added) | Refund, cancellation and shipping policies | Publish client-provided policies for e-commerce/paid bookings; link at checkout | 1 | Low | 0.5–1 h | URLs | Yes | [CONDITIONAL] | Client + PM | AF-01, AG-01 | No — included in base price | Yes
BK-05 | Legal & Compliance Pages (added) | Contact and grievance details | Display business legal name, address, contact channels; grievance officer where required | 1 | Low | 0.25 h | Screenshot | Yes | [MUST HAVE] | Client + PM | P-05 | No — included in base price | Yes
BL-01 | Backup & Recovery (added) | Backup policy and schedule | Define what (files, DB, CMS uploads), how often, retention, where (separate account/region), who restores | 1 | Low | 0.5–1 h | Doc | Yes | [MUST HAVE] | DevOps | X-07 | No — included in base price | Yes
BL-02 | Backup & Recovery (added) | Off-site/second copy | Keep a copy outside the primary host, owned by client | 1 | Low | 0.5–1 h | Log | No | [RECOMMENDED] | DevOps | BL-01 | Conditional — depends on scope | Yes
BL-03 | Backup & Recovery (added) | Restore drill | Restore to a test environment and verify site works | 2 | Medium | 1–2 h | Report | No | [RECOMMENDED] | DevOps | BL-01 | No — included in base price | Yes
BM-01 | Localisation (added) | Language strategy | Decide languages, URL structure (subfolders), language switcher, hreflang, who translates | 1 | Low | 0.5–1 h | Doc | Yes | [CONDITIONAL] | PM | E-03 | Yes — separate line item | No
BM-02 | Localisation (added) | Implement internationalisation | Translation files/CMS fields, hreflang, lang attributes, Indic font support | 7 | Medium | 3–8 h | Commits | No | [CONDITIONAL] | FE | BM-01 | Yes — separate line item | Yes
BM-03 | Localisation (added) | Translation QA | Native speaker reviews rendered pages | 2 | Low | 1–2 h | Checklist | Yes | [CONDITIONAL] | Content | BM-02 | Yes — separate line item | No
BN-01 | Internal Finance & Tax Admin (added) | Project P&L sheet | Track revenue, GST collected (if registered), TDS, expenses, reserves, net profit | 1 | Low | 0.5 h/month | Sheet | No | [MUST HAVE] | PM | I-01 | No — included in base price | No
BN-02 | Internal Finance & Tax Admin (added) | Tax records and CA handoff | Provide invoices, expenses, TDS data to CA for GST returns/income tax as applicable | 1 | Low | 0.5–1 h/month | Sent pack | No | [CONDITIONAL] | PM | I-01, I-02, I-03, I-04, I-05, I-06 | No — included in base price | No
BN-03 | Internal Finance & Tax Admin (added) | Partner expense reimbursement | Reimburse partner-paid business expenses against bills before profit split | 1 | Low | 15 min | Bank refs | No | [MUST HAVE] | PM | I-06 | No — included in base price | No
BO-01 | Partner Governance (added) | Contribution dispute review | Structured review of disputed task claims using evidence; decide per dispute rules | 1 | Low | 0.5–2 h | Dispute record | No | [CONDITIONAL] | Either (both) | BJ-02 | No — included in base price | No
BO-02 | Partner Governance (added) | Points calibration review | Quarterly compare points vs actual effort across projects; adjust defaults going forward only | 1 | Low | 1–2 h | Changelog of defaults | No | [RECOMMENDED] | Either (both) | BJ-01 | No — included in base price | No

## Category Summary
Code | Category | Tasks | MUST HAVE tasks | Default points (all) | Points (MUST HAVE only) | Share of all points
A | Lead Generation | 4 | 1 | 6 | 1 | 0.8955%
B | Client Outreach | 4 | 1 | 4 | 1 | 0.597%
C | Sales | 5 | 1 | 7 | 1 | 1.045%
D | Discovery | 5 | 5 | 8 | 8 | 1.194%
E | Requirements Gathering | 7 | 6 | 10 | 9 | 1.493%
F | Scope Definition | 5 | 5 | 6 | 6 | 0.8955%
G | Proposal/Quotation | 6 | 3 | 11 | 8 | 1.642%
H | Contract/Agreement | 6 | 4 | 7 | 5 | 1.045%
I | Payment/Invoice | 6 | 5 | 6 | 5 | 0.8955%
J | Project Setup | 8 | 8 | 11 | 11 | 1.642%
K | Client Communication | 5 | 1 | 6 | 1 | 0.8955%
L | Research | 5 | 2 | 11 | 3 | 1.642%
M | Competitor Research | 3 | 0 | 6 | 0 | 0.8955%
N | Brand Assets | 4 | 2 | 29 | 2 | 4.328%
O | Content Collection | 6 | 5 | 9 | 8 | 1.343%
P | Copywriting | 6 | 1 | 19 | 2 | 2.836%
Q | UX | 4 | 1 | 7 | 2 | 1.045%
R | Wireframes | 3 | 0 | 8 | 0 | 1.194%
S | UI Design | 6 | 3 | 21 | 15 | 3.134%
T | Design System | 5 | 0 | 9 | 0 | 1.343%
U | Client Design Approval | 4 | 3 | 7 | 6 | 1.045%
V | Frontend Development | 25 | 16 | 62 | 39 | 9.254%
W | Backend Development | 10 | 4 | 33 | 8 | 4.925%
X | Database | 7 | 1 | 10 | 2 | 1.493%
Y | Authentication | 6 | 0 | 21 | 0 | 3.134%
Z | APIs | 3 | 1 | 8 | 1 | 1.194%
AA | Third-party Integrations | 6 | 1 | 11 | 1 | 1.642%
AB | Forms | 6 | 5 | 7 | 6 | 1.045%
AC | Email | 5 | 2 | 8 | 2 | 1.194%
AD | CMS | 5 | 0 | 10 | 0 | 1.493%
AE | Admin Dashboard | 4 | 0 | 25 | 0 | 3.731%
AF | E-commerce | 7 | 0 | 36 | 0 | 5.373%
AG | Booking Systems | 4 | 0 | 8 | 0 | 1.194%
AH | Payments | 5 | 0 | 17 | 0 | 2.537%
AI | SEO | 11 | 8 | 15 | 9 | 2.239%
AJ | Analytics | 4 | 2 | 5 | 2 | 0.7463%
AK | Accessibility | 8 | 6 | 11 | 8 | 1.642%
AL | Performance | 7 | 2 | 9 | 3 | 1.343%
AM | Security | 9 | 6 | 13 | 8 | 1.94%
AN | Responsive Design | 3 | 3 | 5 | 5 | 0.7463%
AO | Cross-browser Testing | 3 | 3 | 6 | 6 | 0.8955%
AP | QA | 5 | 4 | 10 | 9 | 1.493%
AQ | Bug Fixing | 3 | 3 | 3 | 3 | 0.4478%
AR | Client Review | 3 | 2 | 3 | 2 | 0.4478%
AS | Revisions | 3 | 2 | 10 | 7 | 1.493%
AT | Scope Changes | 3 | 3 | 3 | 3 | 0.4478%
AU | Deployment | 4 | 2 | 5 | 2 | 0.7463%
AV | Domain | 3 | 3 | 3 | 3 | 0.4478%
AW | DNS | 3 | 3 | 3 | 3 | 0.4478%
AX | Hosting | 3 | 2 | 10 | 2 | 1.493%
AY | SSL/HTTPS | 3 | 3 | 3 | 3 | 0.4478%
AZ | Production Environment | 4 | 1 | 4 | 1 | 0.597%
BA | Launch | 5 | 4 | 7 | 6 | 1.045%
BB | Post-launch Testing | 4 | 3 | 5 | 3 | 0.7463%
BC | Handover | 3 | 3 | 7 | 7 | 1.045%
BD | Documentation | 4 | 3 | 8 | 6 | 1.194%
BE | Training | 2 | 0 | 3 | 0 | 0.4478%
BF | Final Payment | 3 | 2 | 3 | 2 | 0.4478%
BG | Ownership Transfer | 9 | 9 | 11 | 11 | 1.642%
BH | Maintenance | 6 | 0 | 8 | 0 | 1.194%
BI | Support | 3 | 1 | 3 | 1 | 0.4478%
BJ | Project Closure | 6 | 4 | 6 | 4 | 0.8955%
BK | Legal & Compliance Pages (added) | 5 | 2 | 5 | 2 | 0.7463%
BL | Backup & Recovery (added) | 3 | 1 | 4 | 1 | 0.597%
BM | Localisation (added) | 3 | 0 | 10 | 0 | 1.493%
BN | Internal Finance & Tax Admin (added) | 3 | 2 | 3 | 2 | 0.4478%
BO | Partner Governance (added) | 2 | 0 | 2 | 0 | 0.2985%
| TOTAL | 343 | 179 | 670 | 277 | 100%